## Data_-_Pipeline
Reference No.	Business area	Short description	Contract title	Commercial strategy	Existing contract end date	Next business case stage	Planned date for next business case stage	Procurement start date	Contract commencement date	New contract end date (excl. options)	Value of new contract £ (excl. options)	Procurement sourcing route	Competition process	Spend category - Level 1	Spend category - Level 2	Supply chain tiering	Existing supplier	Main contact email
PP-20-1042	DSRL	Operations Directorate Maintenance & Engineering Support	Collaborative Procurement - Hire Cars	Re-Procurement (same scope)	28/02/2020	N/A	N/A	01/09/2020	28/02/2021	27/02/2023	>£100k to <£500k	Framework	Mini Competition	Professional Services	Support Services	3	Enterprise-rent-a-car	debbie.weir@dounreay.com
DSRL/1200	DSRL	Business Services Directorate	Sharepoint based ISO Certified QMS Design & Build (Stage 2)	New Requirement	N/A	N/A	N/A	11/02/2021	08/03/2021	30/07/2021	>£500k to <£1m	Framework	Mini Competition	Supply Contracts	IT Hardware/Software	3	N/A	louise.gunn.contracts@dounreay.com
PP-20-1082	DSRL	Operations Directorate Waste	Supply of Two Tractors	New requirement	N/A	N/A	N/A	15/01/2021	11/03/2021	31/03/2021	>£100k to <£500k	Under Threshold	Competed	Supply Contracts	Plant & Equipment	4	N/A	lauren.mackay.commercial@dounreay.com
PP-18-1029	DSRL	Business Services Directorate	Framework Agreement for Lifting	Re-Procurement (same scope)	30/09/2018	N/A	N/A	04/09/2020	15/03/2021	31/03/2023	>£500k to <£1m	Find a Tender Service	Competitive	Engineering and Construction	Support Services	3	JGC	lesley-ann.sutherland@dounreay.com
PP-21-1021	DSRL	Operations Directorate Maintenance & Engineering Support	Supply, Installation and Maintenance of Replacement Laundry Equpment	New requirement	N/A	N/A	N/A	09/02/2021	25/03/2021	24/03/2026	>£100k to <£500k	Under Threshold	Competed	Supply Contracts	Plant & Equipment	3	N/A	pauline.mill@dounreay.com
PP-20-1088	DSRL	Strategic Programme Directorate	D3100 Rock Slope Maintenance Works	New requirement	N/A	N/A	N/A	05/02/2021	29/03/2021	14/05/2021	>£100k to <£500k	Under Threshold	Competed	Engineering and Construction	Building and Civil	3	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1065	DSRL	Operations Directorate Maintenance & Engineering Support	Framework Agreement for Design Services (Minor)	Re-procurement (same scope)	31/03/2021	N/A	N/A	24/08/2020	01/04/2021	31/03/2023	>£1m to <£5m	Find a Tender Service	Competitive	Professional Services	Design Services/Support	3	Arch Henderson / WA Fairhurst / WSP / Contec Design Services / M5Tec / Envision Engineering & Design	carly.erridge@dounreay.com
PP-19-1005	DSRL	Operations Directorate Reactors	PFR Upgrade of Fans 1, 2, 3, 5, 7, IFBS and New Stack	New Requirement	N/A	N/A	N/A	02/09/2020	01/04/2021	TBC	>£1m to <£5m	Framework	Mini Competition	Engineering and Construction	Engineering	2	N/A	leisa.swanson@dounreay.com
DSRL/1211	DSRL	Operations Directorate Maintenance & Engineering Support	Protection Coordination Study & Arc Flash Study on the Dounreay Site Electrical Distribution System	New requirement	N/A	N/A	N/A	26/01/2021	01/04/2021	30/06/2021	<£100k	Framework	Mini-competition	Professional Services	Design Services/Support	3	N/A	emma.gordon@dounreay.com
DSRL/1218	DSRL	Organisational Excellence Directorate	Skills Audit Mini-Competition through BATS	New requirement	N/A	N/A	N/A	15/02/2021	01/04/2021	31/10/2021	>£100k to <£500k	Framework	Mini-competition	Professional Services	Support Services	3	N/A	samantha.angus@dounreay.com
DSRL/1212	DSRL	Operations Directorate Reactors	PFR LC15 Periodic Review of Decommissioning Safety Case	New Requirement	N/A	N/A	N/A	01/03/2021	01/04/2021	30/06/2021	<£100k	Framework	Mini-competition	Professional Services	Consultancy	3	N/A	leisa.swanson@dounreay.com
PP-20-1071	DSRL	Programe Delivery Directorate Shaft & Silo	Vibrating Screen - Shaft & Silo	New requirement	N/A	N/A	N/A	01/02/2021	05/04/2021	03/09/2021	<£100k	Under Threshold	Competed	Supply Contracts	Engineering	3	N/A	alex.wood@dounreay.com
DSRL/1207	DSRL	Strategic Programme Directorate	FCAN FRFRP Decommissioning Strategy	New Requirement	N/A	N/A	N/A	19/10/2020	05/04/2021	TBC	>£1m to <£5m	Framework	Mini Competition	Professional Services	Engineering	3	N/A	josh.terry@dounreay.com
DSRL-1217	DSRL	Strategic Programme Directorate	Site Services Desktop Study	New requirement	N/A	N/A	N/A	29/01/2021	05/04/2021	04/07/2021	>£100k to <£500k	Framework	Mini-competition	Professional Services	Design Services/Support	3	n/a	josh.terry@dounreay.com
DSRL/1177	DSRL	Operations Directorate Waste	Non-Active Drains Survey	New requirement	N/A	N/A	N/A	08/02/2021	05/04/2021	31/08/2021	>£100k to <£500k	Framework	Mini-competition	Professional Services	Consultancy	3	N/A	lauren.mackay.commercial@dounreay.com
DSRL/1210	DSRL	Strategic Programme Directorate	Fabrication of Shutters	New requirement	N/A	N/A	N/A	15/02/2021	05/04/2021	08/09/2021	<£100k	Framework	Mini-competition	Engineering and Construction	Waste Management, Disposal & Storage	3	N/A	lauren.mackay.commercial@dounreay.com
DSRL/1173	DSRL	Strategic Programme Directorate	Provision of Gated Assurance Reviews	New Requirement	N/A	N/A	N/A	22/02/2021	12/04/2021	11/04/2026	>£100k to <£500k	Find a Tender Service	Competitive	Professional Services	Consultancy	3	N/A	janet.rosie.contracts@dounreay.com
PP-21-0999	DSRL	Operations Directorate Waste	D3000 Switchboard	New requirement	N/A	N/A	N/A	22/02/2021	19/04/2021	31/07/2021	<£100k	Under Threshold	Competed	Supply Contracts	Plant & Equipment	3	N/A	lauren.mackay.commercial@dounreay.com
PP-21-1006	DSRL	Operations Directorate Waste	WMC/DN060 Waste Services Contract	New requirement	N/A	N/A	N/A	08/03/2021	01/05/2021	30/04/2023	>£100k to <£500k	Under Threshold	Competed	Engineering and Construction	Waste Management, Disposal & Storage	3	N/A	lauren.mackay.commercial@dounreay.com
DSRL/1156	DSRL	Programme Delivery Directorate	Demolition of Buildings DN024, DN026 and DN029	New Requirement	N/A	N/A	N/A	01/03/2021	01/05/2021	30/10/2021	<£100k	Framework	Mini Competition	Engineering and Construction	Decommissioning, Demolition & Deplant	3	N/A	adam.scott@dounreay.com
PP-20-1073	DSRL	Programe Delivery Directorate Shaft & Silo	Liquid Filtration System - Shaft & Silo	New requirement	N/A	N/A	N/A	01/03/2021	01/05/2021	TBC	>£100k to <£500k	Framework	Mini-competition	Engineering and Construction	Engineering	3	N/A	alex.wood@dounreay.com
PP-20-1072	DSRL	Programe Delivery Directorate Shaft & Silo	SST/Mixing Station - Shaft & Silo	New requirement	N/A	N/A	N/A	01/03/2021	01/05/2021	TBC	>£100k to <£500k	Framework	Mini-competition	Engineering and Construction	Engineering	3	N/A	alex.wood@dounreay.com
PP-18-1011	DSRL	Programe Delivery Directorate Shaft & Silo	500L Drum Handling/Export System Design and Manufacture	New Requirement	N/A	Planning/strategy development	Q4 FY20/21	25/08/2020	07/05/2021	10/10/2025	>£5m to <£10m	Framework	Mini Competition	Engineering and Construction	Construction	2	N/A	alex.wood@dounreay.com
PP-19-1033	DSRL	Programme Delivery Directorate	Non Active Drain Optimisation Project	New Requirement	N/A	N/A	N/A	22/02/2021	26/05/2021	24/06/2022	>£1m to <£5m	Find a Tender Service	Competed	Engineering and Construction	Construction	3	N/A	adam.scott@dounreay.com
PP-20-1067	DSRL	Operations Directorate Labs & Analytical Support	Supply design, manufacture and delivery of DPTE equipment	New requirement	N/A	N/A	N/A	01/04/2021	01/06/2021	31/12/2021	<£100k	Under Threshold	Competed	Supply Contracts	Plant & Equipment	3	N/A	sheena.mclachlan@dounreay.com
OMNI-20-000115	DSRL	Operations Directorate Maintenance & Engineering Support	D1203 Roof Void	New Requirement	N/A	N/A	N/A	31/03/2021	01/06/2021	31/12/2021	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Construction	3	N/A	emma.gordon@dounreay.com
PP-20-1079	DSRL	Programme Delivery Directorate	Production of PDSR - DMTR	New requirement	N/A	N/A	N/A	01/04/2021	01/06/2021	TBC	<£100k	Framework	Mini-competition	Professional Services	Consultancy	3	N/A	adam.scott@dounreay.com
PP-20-1086	DSRL	Operations Directorate Reactors	PFR ETP Pipework Replacement and Performance Upgrades	New Requirement	N/A	N/A	N/A	01/04/2021	01/06/2021	31/05/2022	>£1m to <£5m	Framework	Mini-competition	Engineering and Construction	Engineering	3	N/A	leisa.swanson@dounreay.com
PP-19-1001	DSRL	Operations Directorate Reactors	PFR Scheme, Detail Design and Safety Case for PCTL Vessel and PCT Basket Mods	New Requirement	N/A	N/A	N/A	01/04/2021	01/06/2021	TBC	>£100k to <£500k	Framework	Mini Competition	Professional Services	Consultancy	3	N/A	leisa.swanson@dounreay.com
DSRL/1202	DSRL	Strategic Programme Directorate	Provision and Emplacement of Backfill	New requirement	N/A	N/A	N/A	05/04/2021	01/06/2021	31/08/2021	>£100k to <£500k	Framework	Mini-competition	Engineering and Construction	Building and Civil	3	N/A	lauren.mackay.commercial@dounreay.com
PP-19-1027	DSRL	Operations Directorate Labs & Analytical Support	Design and Supply of a Containerised Air Handling Unit Package	New Requirement	N/A	N/A	N/A	01/04/2021	25/06/2021	31/03/2022	>£100k to <£500k	Under Threshold	Competed	Supply Contracts	Engineering	3	N/A	sheena.mclachlan@dounreay.com
PP-19-1026	DSRL	Operations Directorate Labs & Analytical Support	Design and Supply of a Containerised Wet Services Plant	New Requirement	N/A	N/A	N/A	01/04/2021	25/06/2021	31/03/2022	>£100k to <£500k	Under Threshold	Competed	Supply Contracts	Engineering	3	N/A	sheena.mclachlan@dounreay.com
PP-19-1025	DSRL	Operations Directorate Waste	Fume Cupboards D1310 * 10	New Requirement	N/A	N/A	N/A	01/04/2021	25/06/2021	31/03/2022	<£100k	Under Threshold	Competed	Engineering and Construction	Engineering	3	N/A	sheena.mclachlan@dounreay.com
PP-20-1033	DSRL	Operations Directorate Fuel Cycle Area	D2001 Carbon Bed Feasibility Study	New Requirement	N/A	N/A	N/A	01/03/2021	25/06/2021	31/03/2022	>£100k to <£500k	Framework	Mini Competition	Professional Services	Design Services/Support	3	N/A	sheena.mclachlan@dounreay.com
PP-20-1081	DSRL	Operations Directorate Labs & Analytical Support	D1215 PAL Glovebox Design	New Requirement	N/A	N/A	N/A	01/04/2021	25/06/2021	31/03/2022	>£100k to <£500k	Framework	Mini Competition	Professional Services	Design Services/Support	3	N/A	sheena.mclachlan@dounreay.com
PP-20-1025	DSRL	Operations Directorate Labs & Analytical Support	Lab 21, 25 and Ladies & Gents Toilets Refurbishment	New Requirement	N/A	N/A	N/A	01/04/2021	25/06/2021	31/03/2022	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	sheena.mclachlan@dounreay.com
PP-20-1027	DSRL	Operations Directorate Labs & Analytical Support	Manufacture & Install HVAC Modules	New Requirement	N/A	N/A	N/A	01/04/2021	25/06/2021	31/03/2022	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Building and Civil	3	N/A	sheena.mclachlan@dounreay.com
OMNI-20-000114	DSRL	Operations Directorate Fuel Cycle Area	D1208 Fire Escape	New Requirement	N/A	N/A	N/A	31/03/2021	30/06/2021	31/12/2021	>£100k to <£500k	Under Threshold	Competed	Engineering and Construction	Construction	3	N/A	sheena.mclachlan@dounreay.com
DSRL/1215	DSRL	Strategic Programme Directorate	Replace Timber Posts & Rails in High Level Access Walkway Between Vaults	New requirement	N/A	N/A	N/A	03/05/2021	01/07/2021	31/07/2021	<£100k	Framework	Mini-competition	Engineering and Construction	Maintenance	3	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1023	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Sub-Assay/ Cluster Handling Scheme and Detailed Design	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	05/04/2021	09/07/2021	TBC	>£100k to <£500k	Framework	Mini Competition	Professional Services	Design Services/Support	3	N/A	nathan.carrick@dounreay.com
PP-20-1035	DSRL	Operations Directorate Maintenance & Engineering Support	Provision of Cleaning Service	Re-procurement (same scope)	31/07/2021	N/A	N/A	28/02/2021	01/08/2021	31/07/2026	>£1m to <£5m	Find a Tender Service	Competed	Engineering and Construction	Facilities Management	3	OCS	debbie.weir@dounreay.com
PP-20-1032	DSRL	Operations Directorate Maintenance & Engineering Support	Provision of Catering Services	Re-procurement (same scope)	31/07/2021	N/A	N/A	01/04/2021	01/08/2021	31/07/2026	>£500k to <£1m	Find a Tender Service	Competed	Engineering and Construction	Facilities Management	3	Compass	debbie.weir@dounreay.com
PP-20-1043	DSRL	Operations Directorate Fuels	Thorium Nitrate Scheme and Detailed Design	New Requirement	N/A	N/A	N/A	01/06/2021	01/08/2021	30/06/2022	>£100k to <£500k	Framework	Mini Competition	Professional Services	Design Services/Support	3	N/A	robert.mcdonald@dounreay.com
PP-20-1012	DSRL	Strategic Programme Directorate	FCA North RHILW Design	New Requirement	N/A	N/A	N/A	15/03/2021	02/08/2021	TBC	>£1m to <£5m	Framework	Mini Competition	Professional Services	Engineering	2	N/A	josh.terry@dounreay.com
PP-21-1022	DSRL	Operations Directorate Maintenance & Engineering Support	Collaborative Procurement - Travel	Re-procurement (same scope)	31/08/2021	N/A	N/A	29/01/2021	01/09/2021	31/08/2024	>£100k to <£500k	Framework	Mini-competition	Professional Services	Business Travel	3	Capita Travel, Diversity, Calder Conferences, Trainline.com	pauline.mill@dounreay.com
PP-21-1003	DSRL	Strategic Programme Directorate	Waste Treatment Plant - Scheme Design & Safety Assessment	New requirement	N/A	N/A	N/A	21/06/2021	01/09/2021	30/09/2022	>£100k to <£500k	Framework	Mini-competition	Professional Services	Consultancy	3	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1010	DSRL	Strategic Programme Directorate	FCAN Design	New Requirement	N/A	N/A	N/A	01/07/2021	01/09/2021	TBC	>£1m to <£5m	Framework	Mini Competition	Professional Services	Engineering	2	N/A	josh.terry@dounreay.com
PP-20-1009	DSRL	Strategic Programme Directorate	FCAN Development Support 1	New Requirement	N/A	N/A	N/A	01/07/2021	01/09/2021	TBC	>£1m to <£5m	Framework	Mini Competition	Professional Services	Engineering	2	N/A	josh.terry@dounreay.com
PP-20-1013	DSRL	Strategic Programme Directorate	FCAN Consultancy	New Requirement	N/A	N/A	N/A	01/07/2021	01/09/2021	TBC	>£1m to <£5m	Framework	Mini Competition	Professional Services	Engineering	2	N/A	josh.terry@dounreay.com
PP-20-1051	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Martensitic Handling Scheme and Detailed Design	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	22/07/2021	06/09/2021	02/11/2022	<£100k	Framework	Mini Competition	Professional Services	Design Services/Support	2	N/A	nathan.carrick@dounreay.com
PP-20-1045	DSRL	Operations Directorate Fuels	Thorium Nitrate Pre-Build Activities	New Requirement	N/A	N/A	N/A	05/07/2021	13/09/2021	TBC	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Plant & Equipment	3	N/A	robert.mcdonald@dounreay.com
PP-20-1022	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Loose Pin Rig and Furniture Scheme Design	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	24/06/2021	20/09/2021	08/03/2022	>£100k to <£500k	Framework	Mini Competition	Professional Services	Design Services/Support	3	N/A	nathan.carrick@dounreay.com
PP-20-1047	DSRL	Operations Directorate Fuels	D1203 Vent Manufacture, Installation and Commission	New Requirement	N/A	N/A	N/A	01/06/2021	01/10/2021	31/12/2022	>£1m to <£5m	Framework	Mini Competition	Engineering and Construction	Plant & Equipment	3	N/A	robert.mcdonald@dounreay.com
PP-18-1026	DSRL	Programe Delivery Directorate Shaft & Silo	Process Cell and Waste Transfer System	New requirement	N/A	Planning/strategy development	Q4 FY20/21	29/03/2021	04/10/2021	28/03/2026	>£5m to <£10m	Framework	Mini-competition	Engineering and Construction	Construction	2	N/A	alex.wood@dounreay.com
DSRL/1216	DSRL	Operations Directorate Maintenance & Engineering Support	Provision of Mechanical Draughting Support	Re-procurement (same scope)	03/11/2021	N/A	N/A	07/09/2021	04/11/2021	03/11/2021	>£100k to <£500k	Framework	Mini-competition	Professional Services	Support Services	3	Nuvia	lauren.mackay.commercial@dounreay.com
PP-20-1024	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Container Detailed Design	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	25/08/2021	22/12/2021	27/06/2022	>£100k to <£500k	Framework	Mini Competition	Professional Services	Design Services/Support	3	N/A	nathan.carrick@dounreay.com
PP-20-1046	DSRL	Operations Directorate Fuels	Thorium Nitrate Installation and Commissioning	New Requirement	N/A	N/A	N/A	04/10/2021	10/01/2022	TBC	<£100k	Framework	Mini Competition	Engineering and Construction	Construction	3	N/A	robert.mcdonald@dounreay.com
PP-20-1017	DSRL	Strategic Programme Directorate	D2001 Irradiated Fuels IF Containers Manufacture	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	02/02/2022	02/05/2022	01/09/2023	>£1m to <£5m	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	donna.stewart@dounreay.com
PP-18-1008	DSRL	Operations Directorate Reactors	PFR Removal of Redundant Main and IFBS Stacks	New Requirement	N/A	N/A	N/A	01/04/2022	01/06/2022	TBC	>£500k to <£1m	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	leisa.swanson@dounreay.com
PP-18-1016	DSRL	Operations Directorate Reactors	PFR Tank Farm Cut and Remove 2 Tanks	New Requirement	N/A	N/A	N/A	01/04/2022	01/06/2022	TBC	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	leisa.swanson@dounreay.com
PP-20-1049	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Loose Pin Rig and Furniture Detailed Design, Manufacture and Offsite Commission	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	22/04/2022	21/06/2022	TBC	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	nathan.carrick@dounreay.com
PP-20-1050	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Sub-Assay/ Cluster Handling Manufacture and Offsite Commissioning	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	02/05/2022	13/07/2022	TBC	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	nathan.carrick@dounreay.com
PP-20-1053	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels EC&I Concept, Scheme and Detailed Design	New requirement	N/A	N/A	N/A	09/06/2022	21/07/2022	TBC	>£100k to <£500k	Framework	Mini-competition	Professional Services	Design Services/Support	2	N/A	nathan.carrick@dounreay.com
PP-20-1060	DSRL	Business Services Directorate	Payroll, HR & Finance Services Framework Agreement	Re-procurement (same scope)	31/08/2022	N/A	N/A	03/05/2022	31/08/2022	31/08/2029	>£100k to <£500k	Framework	Mini-competition	Professional Services	IT Hardware/Software	3	CGI IT Limited	samantha.angus@dounreay.com
PP-15-1001	DSRL	Strategic Programme Directorate	Irradiated Fuels Project - Manufacture IF Containers, Inner Containers and Internal Furniture	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	01/07/2022	26/09/2022	31/01/2024	>£1m to <£5m	Find a Tender Service	Competitive	Engineering and Construction	Plant & Equipment	2	N/A	nathan.carrick@dounreay.com
PP-20-0999	DSRL	Programme Delivery Directorate	PFR ILWSRF Scheme, Detail Design and Build	New Requirement	N/A	Planning/strategy development	Q4 FY 20/21	01/07/2022	31/10/2022	TBC	>£10m to <£25m	Framework	Mini Competition	Engineering and Construction	Construction	2	N/A	nathan.carrick@dounreay.com
PP-20-1028	DSRL	Operations Directorate Labs & Analytical Support	Sample Analysis	New requirement	N/A	N/A	N/A	01/12/2021	01/11/2022	31/10/2025	>£100k to <£500k	Find a Tender Service	Competed	Professional Services	Regulatory	3	N/A	emma.gordon@dounreay.com
PP-20-1015	DSRL	Strategic Programme Directorate	D2001 Irradiated Fuels Detailed Design and Build	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	02/05/2022	15/11/2022	TBC	>£10m to <£25m	Framework	Mini Competition	Engineering and Construction	Engineering	2	N/A	donna.stewart@dounreay.com
PP-20-1020	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Detailed Design and Build	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	24/08/2022	29/11/2022	TBC	>£10m to <£25m	Framework	Mini Competition	Engineering and Construction	Construction	2	N/A	nathan.carrick@dounreay.com
PP-20-1003	DSRL	Strategic Programme Directorate	Waste Treatment Plant - Detail Design & Build	New requirement	N/A	N/A	N/A	30/07/2022	30/11/2022	30/04/2026	>£5m to <£10m	Framework	Mini-competition	Engineering and Construction	Construction	2	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1052	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels Martensitic Handling Manufacture and Offsite Commissioning	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	01/12/2022	20/02/2023	16/05/2023	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	nathan.carrick@dounreay.com
PP-15-1004	DSRL	Strategic Programme Directorate	Manufacture of the Irradiated Fuels Transportation Flask	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	18/11/2022	19/04/2023	10/12/2025	>£10m to <£25m	Find a Tender Service	Competitive	Engineering and Construction	Plant & Equipment	2	N/A	nathan.carrick@dounreay.com
PP-20-1054	DSRL	Strategic Programme Directorate	PFR Irradiated Fuels EC&I Installation and Commissioning	New Requirement	N/A	Planning/strategy development	Q3 FY21/22	22/03/2023	03/07/2023	TBC	>£100k to <£500k	Framework	Mini Competition	Engineering and Construction	Engineering	3	N/A	nathan.carrick@dounreay.com
PP-20-1056	DSRL	Operations Directorate Waste	LLW Metals Diversion contract	New Requirement	N/A	N/A	N/A	01/06/2021	FY 21/22	FY 21/22	>£500k to <£1m	Framework	Mini Competition	Professional Services	Support Services	3	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1057	DSRL	Operations Directorate Waste	LLW Optioneering contract	New Requirement	N/A	N/A	N/A	01/06/2021	FY 21/22	FY 21/22	>£500k to <£1m	Framework	Mini-competition	Professional Services	Support Services	3	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1055	DSRL	Operations Directorate Waste	Voidage & container assessments	New requirement	N/A	N/A	N/A	01/06/2021	FY 21/22	FY 21/22	>£100k to <£500k	Framework	Mini Competition	Professional Services	Support Services	3	N/A	lauren.mackay.commercial@dounreay.com
PP-21-1004	DSRL	Strategic Programme Directorate	Purchase of a Welfare Unit	New requirement	N/A	N/A	N/A	FY21/22	FY21/22	FY21/22	>£100k to <£500k	Under Threshold	Competed	Supply Contracts	Plant & Equipment	4	N/A	lauren.mackay.commercial@dounreay.com
PP-21-1000	DSRL	Strategic Programme Directorate	Supply of a Crane for ADU Floc	New requirement	N/A	N/A	N/A	FY21/22	FY21/22	FY21/22	>£100k to <£500k	Under Threshold	Competed	Supply Contracts	Plant & Equipment	4	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1070	DSRL	Programe Delivery Directorate Shaft & Silo	Shaft & Silo Construction Works (CS&A, Mechanical, Electrical)	New Requirement	N/A	Planning/strategy development	Q4 FY20/21	FY21/22	FY21/22	TBC	>£25m to <£50m	Framework	Mini-competition	Engineering and Construction	Construction	2	N/A	alex.wood@dounreay.com
DSRL/1214	DSRL	Strategic Programme Directorate	Installation of Crane for ADU Floc	New requirement	N/A	N/A	N/A	FY21/22	FY21/22	FY21/22	<£100k	Framework	Mini-competition	Engineering and Construction	Engineering	3	N/A	lauren.mackay.commercial@dounreay.com
PP-20-1076	DSRL	Programe Delivery Directorate Shaft & Silo	Bill of Quantites Production	New requirement	N/A	N/A	N/A	Q2 21/22	Q2 21/22	TBC	>£100k to <£500k	Framework	Mini-competition	Professional Services	Consultancy	3	N/A	alex.wood@dounreay.com

## 'http://ndahqewc01/Users/HB47/AppData/Local/Microsoft/Windows/Temporary%20Internet%20Files/Content.Outlook/I6CTBKVL/Pipeline%20Master.xlsx'#Definitions_&_Descriptors1
Clinical_Medical
Communications
Construction
Defence
Emergency_Rescue
Energy_Fuels
Engineering_Goods
Facilities
Fleet
ICT
Industrial_Services
Learning_Development
Legal_Aid
Logistics
Office_Solutions
Operational_Goods
Personnel_Related
Print_Print_Management
Professional_Services_CCL
Professional_Services_Other
Research
Social_Care
Travel
Waste_Management
Welfare_to_Work
World_Programmes

## 'http://ndahqewc01/Users/HB47/AppData/Local/Microsoft/Windows/Temporary%20Internet%20Files/Content.Outlook/I6CTBKVL/Pipeline%20Master.xlsx'#Definitions_&_Descriptors
Clinical_Medical