## Procurement_Plan
Dounreay, a division of Magnox Limited - Procurement pipeline July 2023
For further information contact Dounreay at commercial.services@dounreay.com
☆ Record Ref	Business Unit	Sourcing to Contract: Record Name	☆ Published Description	Procurement Route (If Known)	Desired Contract Start Date	Desired Contract End Date	Value Range	Contract Owner	Previous Contract Ref	Status
C14622	Commercial	Commercial Delivery Support for Commercial Services	Commercial Delivery Support for Commercial Services	Framework - Direct Award	07/08/2023	31/07/2027	≥ £1m to <£5m	Robert McDonald	3300017896	Live
C8621	Operations - Waste	Low Level Waste Pits Resurfacing and Provision of Cover Building	Low Level Waste Pits Resurfacing and Provision of Cover Building	Below Threshold - Competitive Tender	16/08/2023	16/11/2023	≥ £100k to <£500k	Janet Rosie		Live
C6616	Operations - FCA Decommissioning	Reserved Procurement - Removal of Redundant Fuel Cycle Area Pipe Bridge	Note: Reserved Contract.	Below Threshold - Competitive Tender	18/08/2023	18/08/2025	< £100k	Dawn Sewell		Live
C15036	Operations - FCA Decommissioning	DN141 Supply Duct Repairs	DN141 Supply Duct Repairs	Below Threshold - Competitive Tender	28/08/2023	23/02/2024	< £100k	Jade Plowman		Live
C12554	Organisational Excellence	Culture Development	Culture Development for the Dounreay Site's workforce	Framework - Further Competition	01/09/2023	31/05/2024	≥ £500k to <£1m	Debbie Weir	3300026316	Pre-Plan
C14928	Operations - Maintenance & Engineering Support	Servicing of the Fire Alarm System at PFR	Servicing of the Fire Alarm System at PFR on the Dounreay Site	Below Threshold - Competitive Tender	01/09/2023	31/08/2026	< £100k	Emma Gordon	3300013785	Planned
C14467	Operations - Maintenance & Engineering Support	Electrical Design For the Removal/Replacement of Substation Reyrolle HH Frames	Electrical Design For the Removal/Replacement of Substation Reyrolle HH Frames and Rationalisation of Substation Local Electrical Supplies	Framework - Further Competition	01/09/2023	31/10/2023	< £100k	Fraser Bruce		Live
C14836	Operations - FCA Decommissioning	D1204 Safety Case and Shielding Specialist Consultancy	D1204 Safety Case and Shielding Specialist Consultancy	Framework - Further Competition	01/09/2023	31/08/2025	≥ £100k to <£500k	Erica Innes	3300009932	Planned
C12620	Security and Resilience	Ambulance Technician Training	Contract which covers various training courses, including Ambulance Technician Training, carried out by the Scottish Ambulance Service.	Direct Award - Below Threshold	01/09/2023	31/08/2024	< £100k	Lauren J Mackay		Planned
C12623	Security and Resilience	Firefighter and Officer Related Training	Firefighter and Officer Related Training	Open Procedure	01/09/2023	31/08/2027	≥ £100k to <£500k	Lauren J Mackay		Pre-Plan
C1121	Operations - Reactor	Prototype Fast Reactor Effluent Treatment Plant Pipework Replacement and Perform	Prototype Fast Reactor Effluent Treatment Plant Pipework Replacement and Performance Upgrades	Open Procedure	01/09/2023	31/10/2024	≥ £1m to <£5m	Lynsey Will		Planned
C15063	Operations - Waste	Waste Safety Case Officer	Waste Safety Case Officer	Framework - Further Competition	04/09/2023	06/09/2024	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C14411	Operations - FCA Decommissioning	D1206 Breathing Air Containerised System	D1206 Breathing Air Containerised System	Open Procedure	04/09/2023	05/02/2024	≥ £100k to <£500k	Jade Plowman		Planned
C9866	Operations - Waste	Area 400 External Ventilation - North Stack to DN253	Area 400 External Ventilation - North Stack to DN253	Direct Award - Below Threshold	04/09/2023	01/12/2023	≥ £100k to <£500k	Sonja Sinclair		Planned
C1134	Strategic Programme	Supply of Aggregate	Supply of Aggregate	Below Threshold - Competitive Tender	08/09/2023	06/09/2024	< £100k	Heidi Warner		Planned
C8637	Operations - Waste	Dounreay Cementation Plant Engineering Substantiation	Dounreay Cementation Plant Engineering Substantiation	Framework - Further Competition	11/09/2023	31/12/2024	≥ £100k to <£500k	Donna Stewart		Planned
C1095	Operations - Waste	Mechanical Site Project Engineer	Mechanical Site Project Engineer	Framework - Further Competition	11/09/2023	31/03/2025	≥ £100k to <£500k	Hannah Budge		Planned
C9874	Operations - Waste	Area 500 - Internal Secondary Steelwork	Area 500 - Internal Secondary Steelwork	Direct Award - Below Threshold	12/09/2023	06/11/2023	< £100k	Sonja Sinclair		Planned
C1173	Strategic Programme	Design of Steelwork Repair	Design of Steelwork Repair	Framework - Further Competition	14/09/2023	14/03/2024	≥ £100k to <£500k	Heidi Warner		Planned
C10996	Operations - Maintenance & Engineering Support	Reserved Procurement - Provision of Plant/Machinery to Support Projects	This procurement is to establish a call-off Contract to enable the hire of plant/machinery on an ad hoc basis to support projects on the Dounreay site.	Below Threshold - Competitive Tender	15/09/2023	14/09/2026	< £100k	Declan Gunn		Live
C11914	Operations - Waste	D1208 Licence Condition 15 Safety Case and Engineering Substantiation	D1208 Licence Condition 15 Safety Case and Engineering Substantiation	Framework - Further Competition	18/09/2023	28/03/2025	≥ £500k to <£1m	Janet Rosie		Planned
C1129	Operations - FCA Decommissioning	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility for Testing	Below Threshold - Competitive Tender	19/09/2023	30/03/2024	≥ £100k to <£500k	Alex Wood		Planned
C15230	Security and Resilience	Provision of Canine Support Services - Explosive Search Capability	Provision of Canine Support Services - Explosive Search Capability	Direct Award - PCR Single Source (Reg 32)	20/09/2023	19/09/2026	≥ £100k to <£500k	Lauren J Mackay	3300022930	Planned
C9885	Operations - Waste	D1208 East Fire Escape Scaffold, Removal & Installation	D1208 East Fire Escape Scaffold, Removal & Installation	Below Threshold - Competitive Tender	21/09/2023	21/01/2024	≥ £100k to <£500k	Ilona Unger-Russell		Live
C1221	Operations - Waste	Shielded High Resolution Gamma Spectrometry Portable System	Shielded High Resolution Gamma Spectrometry Portable System	Direct Award - PCR Single Source (Reg 32)	25/09/2023	31/05/2024	≥ £100k to <£500k	Donna Stewart		Planned
C1076	Operations - FCA Decommissioning	D1206 Safety Case Documentation	D1206 Safety Case Documentation	Framework - Further Competition	30/09/2023	30/09/2025	≥ £100k to <£500k	Alex Wood		Planned
C14697	Operations - Waste	Reserved Procurement - Crushing and Screening of Concrete for D6500	RESERVED PROCUREMENT / Crushing and Screening of Concrete for D6500	Below Threshold - Competitive Tender	01/10/2023	30/11/2023	< £100k	Carly Erridge		Planned
C1222	Operations - Maintenance & Engineering Support	Prototype Fast Reactor Transformers	Prototype Fast Reactor Transformers	Below Threshold - Competitive Tender	01/10/2023	31/08/2024	≥ £100k to <£500k	Fraser Bruce		Planned
C1151	Strategic Programme	Low Level Waste Pits - Review and development of the Environmental Safety Case	Low Level Waste Pits - Review and development of the Environmental Safety Case	Framework - Further Competition	01/10/2023	30/05/2025	< £100k	Emma Gordon		Pre-Plan
C14037	Operations - Maintenance & Engineering Support	Mainsaver Upgrade and Maintenance	Mainsaver Upgrade and Maintenance	Direct Award - PCR Single Source (Reg 32)	01/10/2023	30/09/2025	≥ £100k to <£500k	Kelsey Bain	3300003958	Planned
C1125	Operations - FCA Decommissioning	D1217 Modular Units	D1217 Modular Units	Below Threshold - Competitive Tender	02/10/2023	31/10/2025	< £100k	Alex Wood		Planned
C12886	Operations - Waste	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	Framework - Further Competition	02/10/2023	21/06/2024	< £100k	Donna Stewart		Pre-Plan
C1250	Operations - Waste	D1215 Inductively Coupled Plasma - Optical Emission Spectrometer	D1215 Inductively Coupled Plasma - Optical Emission Spectrometer - High resolution (parts per billion) - Two off	Direct Award - Below Threshold	02/10/2023	31/03/2025	≥ £100k to <£500k	Donna Stewart		Planned
C13986	Operations - Waste	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Below Threshold - Competitive Tender	02/10/2023	29/03/2024	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C1122	Operations - Waste	D3000 Switchboard	D3000 Switchboard	Open Procedure	02/10/2023	02/08/2024	≥ £100k to <£500k	Donna Stewart		Planned
C13987	Operations - Waste	D3000 Generator	D3000 Generator	Below Threshold - Competitive Tender	02/10/2023	01/03/2024	< £100k	Donna Stewart		Planned
C9096	Operations - Waste	Waste Framework Agreement – Provision of Waste Skips to Support Waste Generation	Waste Framework Agreement – Provision of Waste Skips to Support Waste Generation	Framework Agreement – Set up of a new Framework	02/10/2023	30/09/2027	≥ £500k to <£1m	Janet Rosie		Planned
C10735	Finance	Provision of Cost Engineer, Planner & Estimator Resources	Provision of Cost Engineer, Planner & Estimator Resources	Framework - Further Competition	02/10/2023	30/09/2026	≥ £1m to <£5m	Lauren Mackay	3300020556	Live
C12419	Finance	Business Case Development for the Dounreay Site	Professional support required to deliver Dounreay's critical business cases.	Framework - Further Competition	02/10/2023	30/09/2028	≥ £500k to <£1m	Louise Gunn		Planned
C8608	Strategic Programme	iCase Sponsorship	iCase Sponsorship	Direct Award - Below Threshold	02/10/2023	31/05/2024	< £100k	Lesley-Ann Crombie		Pre-Plan
C13373	Operations - Waste	Waste Characterisation Support	Waste Characterisation Support	Framework - Further Competition	02/10/2023	27/09/2024	≥ £500k to <£1m	Sarah McCaughey	3300023206 / 3300023205 / 3300023254 / 3300023207	Planned
C12385	Operations - Waste	Dounreay Cementation Plant Peer Review	Dounreay Cementation Plant Peer Review	Framework - Further Competition	09/10/2023	28/03/2025	< £100k	Donna Stewart		Pre-Plan
C1109	Operations - Fuel	Reserved Procurement - D1203 Ventilation System	The Manufacture and Installation and Site Acceptance of the D1203 Ventilation System	Below Threshold - Competitive Tender	09/10/2023	30/06/2025	≥ £1m to <£5m	Alex Wood		Live
C15210	Assurance	Provision of Management Certification Services	Provision of Management Certification Services	Direct Award - Below Threshold	12/10/2023	11/10/2026	< £100k	Kelsey Bain	3300016843	Planned
C1093	Operations - Waste	16 Fume Cupboards - D1310 and D1215 Upgrade Projects	16 Fume Cupboards - D1310 and D1215 Upgrade Projects	Below Threshold - Competitive Tender	16/10/2023	31/05/2024	≥ £100k to <£500k	Donna Stewart		Planned
C15173	Operations - Waste	Reserved Procurement - Air Handling Unit Design	Reserved Procurement - Air Handling Unit Design	Below Threshold - Competitive Tender	16/10/2023	31/01/2024	< £100k	Donna Stewart		Planned
C12750	Operations - Fuel	Irradiated Fuels Sub-Assembly Handling Scheme and Detailed Design	Irradiated Fuels Sub-Assembly Handling Scheme and Detailed Design	Framework - Further Competition	31/10/2023	31/07/2024	< £100k	Stephen Plummer		Live
C6606	Operations - Maintenance & Engineering Support	Upgrade / Replace D1403 Emergency Generator	Upgrade / Replace D1403 Emergency Generator	Open Procedure	01/11/2023	30/06/2024	≥ £100k to <£500k	Fraser Bruce		Planned
C1168	Strategic Programme	Waste Optimisation - Waste Optimisation Improvements	Waste Optimisation - Waste Optimisation Improvements	Framework - Further Competition	01/11/2023	01/10/2024	< £100k	Janet Rosie		Planned
C6605	Operations - Maintenance & Engineering Support	Replacement Cladding on North West Wall Prototype Fast Reactor Steam Generation	Replacement Cladding on North West Wall Prototype Fast Reactor Steam Generation	Open Procedure	01/11/2023	31/12/2024	≥ £1m to <£5m	Jade Plowman		Live
C14389	Strategic Programme	Behaviour and transport of industrial particles in sand beds mobilised by waves	Behaviour and transport of industrial particles in sand beds mobilised by waves	Direct Award - Below Threshold	01/11/2023	31/10/2025	≥ £100k to <£500k	Fraser Bruce		Planned
C1133	Strategic Programme	Plant Hire	Plant Hire	Below Threshold - Competitive Tender	03/11/2023	08/11/2024	< £100k	Heidi Warner		Planned
C14046	Operations - Waste	D1208 Peer Review	D1208 Peer Review	Framework - Further Competition	20/11/2023	28/03/2025	< £100k	Donna Stewart		Pre-Plan
C1106	Operations - FCA Decommissioning	Unirradiated Fuels Carbon Bed Feasibility Study	Unirradiated Fuels Carbon Bed Feasibility Study	Framework - Further Competition	23/11/2023	09/08/2024	≥ £100k to <£500k	Stephen Plummer		Planned
C6607	Operations - Maintenance & Engineering Support	Radiation Protection Instrumentation (RPI) Calibration Off Site	Radiation Protection Instrumentation (RPI) Calibration Off Site	Below Threshold - Competitive Tender	01/12/2023	30/06/2024	≥ £100k to <£500k	Fraser Bruce		Planned
C1149	Strategic Programme	Site Closure and Environmental Restoration - Peer Review	Site Closure and Environmental Restoration - Peer Review	Framework - Further Competition	01/12/2023	30/09/2024	< £100k	Emma Gordon		Pre-Plan
C1128	Operations - FCA Decommissioning	D1217 - Cell Floor Block Lifting Bags	D1217 - Cell Floor Block Lifting Bags	Below Threshold - Competitive Tender	04/12/2023	24/06/2024	< £100k	Alex Wood		Planned
C9887	Operations - Waste	Area 400 Internal Ventilation	To be coordinated with the installation of Area 300 and Area 400 Fan and Filter Rooms	Direct Award - Below Threshold	05/12/2023	17/01/2024	< £100k	Sonja Sinclair		Planned
C13981	Operations - Waste	Low Level Waste Effluent Treatment Plant Sampler	Low Level Waste Effluent Treatment Plant Sampler	Below Threshold - Competitive Tender	11/12/2023	31/05/2024	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C12890	Operations - Waste	D1215 Ductwork Manufacturing and Delivery	D1215 Ductwork Manufacturing and Delivery	Below Threshold - Competitive Tender	20/12/2023	28/06/2024	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C12887	Operations - Waste	D1215 Glove box Manufacturing and Delivery	D1215 Glove box Manufacturing and Delivery	Below Threshold - Competitive Tender	20/12/2023	28/06/2024	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C12888	Operations - Waste	D1215 Red Extract System Fan Pair Manufacturing and Delivery	D1215 Red Extract System Fan Pair Manufacturing and Delivery	Below Threshold - Competitive Tender	20/12/2023	28/06/2024	< £100k	Donna Stewart		Pre-Plan
C12889	Operations - Waste	D1215 Red Extract System Filters and Dampers Manufacturing and Delivery	D1215 Red Extract System Filters and Dampers Manufacturing and Delivery	Below Threshold - Competitive Tender	20/12/2023	28/06/2024	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C12892	Operations - Waste	Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Below Threshold - Competitive Tender	20/12/2023	28/06/2024	< £100k	Donna Stewart		Pre-Plan
C1246	Operations - Maintenance & Engineering Support	The supply of Cameras, Camera Encoders & Server Upgrade & supporting maintenance	- The supply and delivery of Cameras, Camera Encoders and Server Upgrade. / - Maintenance of Titan Vision Control Equipment.	Direct Award - PCR Single Source (Reg 32)	01/01/2024	30/06/2028	≥ £1m to <£5m	Kelsey Bain		Planned
C1156	Operations - Maintenance & Engineering Support	Maintenance and Calibration of Weigh Scales	Maintenance and Calibration of Weigh Scales	Below Threshold - Competitive Tender	01/01/2024	31/12/2028	≥ £100k to <£500k	Kelsey Bain	3300025052	Planned
C1160	Operations - Maintenance & Engineering Support	Annual Maintenance (2 Visits per Annum) of AC12 Security Alarm Panels	Annual Maintenance (2 Visits per Annum) of AC12 Security Alarm Panels	Below Threshold - Competitive Tender	05/01/2024	31/03/2029	< £100k	Kelsey Bain		Planned
C1150	Strategic Programme	Development of Individual Component Environmental Safety Cases	Development of Individual Component Environmental Safety Cases	Framework - Further Competition	08/01/2024	31/07/2024	< £100k	Emma Gordon		Pre-Plan
C1172	Strategic Programme	Repair of Steelwork	Repair of Steelwork	Below Threshold - Competitive Tender	02/02/2024	07/02/2025	≥ £100k to <£500k	Heidi Warner		Planned
C1107	Operations - Fuel	Thorium Nitrate Scheme and Detailed Design	Thorium Nitrate Scheme and Detailed Design	Framework - Further Competition	01/03/2024	31/10/2025	≥ £100k to <£500k	Stephen Plummer		Planned
C1096	Strategic Programme	Non Active Drain Water Treatment Plant Works	Non Active Drain Water Treatment Plant Works	Below Threshold - Competitive Tender	01/04/2024	28/02/2025	≥ £1m to <£5m	Adam Scott		Planned
C10537	Security and Resilience	Purchase of Fire Appliance	Purchase of Fire Appliance	Open Procedure	01/04/2024	30/09/2025	≥ £100k to <£500k	Debbie Weir		Pre-Plan
C15129	Assurance	Supply of Electronic Personal Dosimeters	Supply of Electronic Personal Dosimeters	Direct Award - PCR Single Source (Reg 32)	01/04/2024	31/03/2026	≥ £500k to <£1m	Emma Gordon		Pre-Plan
C1140	Strategic Programme	Laboratory Analysis Services	Laboratory Analysis Services	Open Procedure	01/04/2024	31/03/2034	≥ £5m to <£10m	Kelsey Bain	3300029029	Live
C14956	Operations - Waste	Provision of Ad-hoc Haulage Services	Provision of ad-hoc haulage services	Below Threshold - Competitive Tender	01/04/2024	31/03/2025	< £100k	Janet Rosie		Pre-Plan
C1208	Strategic Programme	Environmental Safety Case Maintenance and Support	Environmental Safety Case Maintenance and Support	Framework - Further Competition	01/04/2024	30/11/2024	≥ £100k to <£500k	Heidi Warner		Planned
C14394	Assurance	Provision of Criticality Software MONK & Visual Workshop	Provision of Criticality Software MONK & Visual Workshop	Direct Award - PCR Single Source (Reg 32)	01/04/2024	31/03/2029	≥ £100k to <£500k	Kelsey Bain	3300031908	Planned
C14907	Strategic Programme	Detection, Mapping and Retrieval of Radioactive Particles from Beach Environment	Detection, Mapping and Retrieval of Radioactive Particles from Beach Environments and Environmental Monitoring	Open Procedure	01/04/2024	31/03/2034	≥ £10m to <£25m	Fraser Bruce	3300020535	Planned
C15245	Finance	IT Hardware Procurement	IT End User Hardware Refresh- 250 x Laptop and Docking Stations	Framework - Further Competition	01/04/2024	01/05/2024	≥ £100k to <£500k	Louise Gunn	3300020765	Pre-Plan
C9903	Operations - Waste	Electrical Control and Instrumentation Services	Electrical Control and Instrumentation Services	Framework - Further Competition	01/04/2024	31/03/2025	≥ £100k to <£500k	Sonja Sinclair		Planned
C9905	Operations - Waste	Mechanical Design Services	Mechanical Design Services	Direct Award - Below Threshold	01/04/2024	31/03/2025	≥ £100k to <£500k	Sonja Sinclair		Planned
C6404	Operations - Waste	Stillage Transfer System- Civil and groundworks	Civil and groundworks including levelling at DN253 and foundations for gantry crane	Below Threshold - Competitive Tender	01/04/2024	02/09/2024	< £100k	Sonja Sinclair		Planned
C9897	Operations - Waste	Stillage Transfer System - Control System Modifications	Control system Modifications design and implementation	Below Threshold - Competitive Tender	01/04/2024	11/11/2024	< £100k	Sonja Sinclair		Planned
C9890	Operations - Waste	Stillage Transfer System- Gantry Crane & Frame	Works on the Stillage Transfer System- the Gantry Crane and Frame only	Open Procedure	01/04/2024	11/11/2024	≥ £100k to <£500k	Sonja Sinclair		Planned
C9877	Operations - Waste	Area 300 Main Immobilisation Line installation	Area 300 Main Immobilisation Line installation	Below Threshold - Competitive Tender	01/04/2024	01/10/2024	≥ £100k to <£500k	Sonja Sinclair		Planned
C9900	Operations - Waste	Area 500 Electrical Equipment Procurement	Area 500 Electrical Equipment Procurement	Below Threshold - 3 Quotes	01/04/2024	01/05/2024	< £100k	Sonja Sinclair		Planned
C1142	Operations - Waste	Manufacture and Design Ammonium Dirurante Floc Transport Stillage Lifting Beam	Manufacture and Design of Ammonium Dirurante Floc Transport Stillage Lifting Beam	Below Threshold - Competitive Tender	01/04/2024	11/11/2024	≥ £100k to <£500k	Sonja Sinclair		Planned
C1239	Operations - Waste	65 tonne Bogie Modifications Package	65 tonne Bogie Modifications Package	Below Threshold - Competitive Tender	01/04/2024	16/08/2024	≥ £100k to <£500k	Sonja Sinclair		Planned
C9919	Operations - Waste	Stillage Transfer System - Changing Room	Stillage Transfer System - Changing Room	Below Threshold - Competitive Tender	01/04/2024	11/11/2024	< £100k	Sonja Sinclair		Planned
C9871	Operations - Waste	Area 600 Caustic Line D2700 to DN253	Area 600 Caustic Line D2700 to DN253	Direct Award - Below Threshold	06/04/2024	31/12/2024	< £100k	Sonja Sinclair		Planned
C12769	Operations - Fuel	Irradiated Fuel Replacement Grabs Design	Irradiated Fuel Replacement Grabs Design	Framework - Further Competition	09/04/2024	08/10/2024	< £100k	Stephen Plummer		Planned
C10405	Operations - Waste	50 tonne Forklift Replacement	50 tonne Forklift Replacement	Open Procedure	15/04/2024	30/11/2024	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C1143	Operations - FCA Decommissioning	Raffinate Room Concept Design and Safety and Environmental Overview Report	Raffinate Room Concept Design and Safety and Environmental Overview Report	Framework - Further Competition	30/04/2024	06/05/2025	< £100k	Stephen Plummer		Pre-Plan
C8624	Operations - Waste	Low Level Waste Effluent Treatment Plant Ventilation System Upgrade	Low Level Waste Effluent Treatment Plan Ventilation System Upgrade	Below Threshold - Competitive Tender	01/05/2024	30/09/2024	< £100k	Donna Stewart		Planned
C1157	Operations - Maintenance & Engineering Support	Maintenance of Air Compressors	Maintenance of Air Compressors	Open Procedure	01/05/2024	30/04/2027	≥ £100k to <£500k	Fraser Bruce	3300024069	Planned
C1171	Strategic Programme	Lower Activity Waste - Strategy Support	Lower Activity Waste - Strategy Support	Framework - Further Competition	01/05/2024	30/04/2025	< £100k	Janet Rosie		Planned
C1247	Operations - Waste	Alpha Spectrometry Analyst Controller Units	Alpha Spectrometry Analyst Controller Units (1 and 6 Dual Packs Alpha Spectrometer)	Direct Award - Below Threshold	11/05/2024	17/11/2024	< £100k	Donna Stewart		Planned
C1248	Operations - Waste	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Direct Award - PCR Single Source (Reg 32)	11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart		Planned
C1211	Operations - Waste	D1310 - Gas Chromatography - Mass Spectrometer	D1310 - Gas Chromatography - Mass Spectrometer	Below Threshold - Competitive Tender	11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart		Planned
C1254	Operations - Waste	D2176 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	D2176 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	Direct Award - Below Threshold	11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart		Planned
C8927	Strategic Programme	Shaft & Silo Main Construction Works	Dounreay are currently in the process of preparing / approval of a Business Case for this procurement. Updates to the supply chain will be provided in due course. / To register please accept this opportunity and email commercialprojects@dounreay.com	Competitive Procedure with Negotiation (CPN)	17/05/2024	19/05/2028	≥ £50m to <£100m	Heidi Warner		Planned
C15213	Operations - Maintenance & Engineering Support	Van Hire (x 8 Vehicles)	Van Hire (x 8 Vehicles)	Open Procedure	01/06/2024	31/05/2028	≥ £100k to <£500k	Kelsey Bain	3300008297, 3300008492, 3300008493, 3300008494, 3300008501, 3300008502, 3300008503, 3300009430	Pre-Plan
C13682	Organisational Excellence	Provide a Graduate & Apprentice Learning & Development Programme	Provide a Graduate & Apprentice Learning & Development Programme at Loch Eil	Direct Award - Below Threshold	01/06/2024	31/10/2024	< £100k	Lauren J Mackay	3300030924	Pre-Plan
C1164	Security and Resilience	Purchase of Fence	Purchase of Fence	Below Threshold - Competitive Tender	03/06/2024	06/12/2024	≥ £100k to <£500k	Debbie Weir		Planned
C1182	Security and Resilience	Purchase of Anti-Pedestrian Gates	Purchase of Anti-Pedestrian Gates	Below Threshold - Competitive Tender	03/06/2024	06/12/2024	≥ £100k to <£500k	Debbie Weir		Planned
C1184	Security and Resilience	Purchase of Vehicle Access Gates	Purchase of Vehicle Access Gates	Below Threshold - Competitive Tender	03/06/2024	06/12/2024	< £100k	Debbie Weir		Planned
C13963	Security and Resilience	Fence Maintenance	Fence Maintenance	Below Threshold - Competitive Tender	03/06/2024	02/08/2024	≥ £100k to <£500k	Debbie Weir		Pre-Plan
C1183	Security and Resilience	Purchase of Pedestrian Gates	Purchase of Pedestrian Gates	Below Threshold - Competitive Tender	03/06/2024	06/12/2024	< £100k	Debbie Weir		Planned
C12893	Operations - Waste	Fit-out and Commissioning of Glovebox and Extract Systems	Electrical, Control and Instrumentation Fit-out and Commissioning of Glovebox and Extract Systems	Open Procedure	05/06/2024	06/06/2025	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C1238	Operations - Waste	Lid Lifting Frame and Bedplate Frame Package including castel key interlocking	Lid Lifting Frame and Bedplate Frame Package including castel key interlocking	Below Threshold - Competitive Tender	14/06/2024	31/12/2024	< £100k	Sonja Sinclair		Planned
C12897	Operations - Waste	Mechanical Fit-out and Commissioning of Glovebox and extract systems	Mechanical Fit-out and Commissioning of Glovebox and extract systems	Open Procedure	03/07/2024	04/07/2025	≥ £100k to <£500k	Donna Stewart		Pre-Plan
C1165	Strategic Programme	Remote Handled Intermediate Level Waste Letter of Compliance (Ion Exchange)	Remote Handled Intermediate Level Waste Letter of Compliance (Ion Exchange)	Framework - Direct Award	03/07/2024	31/07/2025	< £100k	Robert McDonald		Planned
C1193	Security and Resilience	Purchase of Consoles	Purchase of Consoles	Below Threshold - Competitive Tender	07/08/2024	03/03/2025	< £100k	Debbie Weir		Planned
C1200	Operations - Reactor	Prototype Fast Reactor Manufacture Prototype Containment and Cutting Tool	Prototype Fast Reactor Manufacture Prototype Containment and Cutting Tool for Argon Gas Blanket	Below Threshold - Competitive Tender	17/08/2024	31/10/2024	≥ £100k to <£500k	Lynsey Will		Planned
C10632	Assurance	Replacement of the Whole Body Monitor, Wound Monitor and Supporting Equipment	This procurement is to supply a replacement Whole Body Monitor, Wound Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Open Procedure	01/09/2024	31/08/2025	≥ £100k to <£500k	Emma Gordon		Pre-Plan
C1114	Operations - Waste	Low Level Waste Metals Diversion Projects	Low Level Waste Metals Diversion Projects	Framework - Further Competition	02/09/2024	31/03/2025	≥ £100k to <£500k	Carly Erridge		Planned
C1113	Operations - Waste	Voidage and Container Assessments	Voidage and Container Assessments	Framework - Further Competition	02/09/2024	31/08/2025	≥ £100k to <£500k	Donna Stewart		Planned
C1102	Operations - Fuel	Irradiated Fuels Multi-functional Rig and Fixtures Scheme	Irradiated Fuels Multi-functional Rig and Fixtures Scheme	Framework - Further Competition	30/09/2024	30/10/2025	≥ £500k to <£1m	Stephen Plummer		Planned
C9673	Operations - Waste	Telehandler	Telehandler	Below Threshold - Competitive Tender	01/10/2024	31/01/2025	< £100k	Donna Stewart		Pre-Plan
C1177	Operations - FCA Decommissioning	Design for Active Filter Change Replacement Robot Implementation	Design for Active Filter Change Replacement Robot Implementation	Framework - Further Competition	01/10/2024	02/11/2025	< £100k	Alex Wood		Planned
C1249	Operations - Waste	D1310 Auto-Analyser Spectrophotometers - Gallery - 2 off	D1310 Auto-Analyser Spectrophotometers - Gallery - 2 off	Direct Award - Below Threshold	23/10/2024	31/03/2025	≥ £100k to <£500k	Donna Stewart		Planned
C1110	Operations - Fuel	Irradiated Fuels Consolidated Furniture Scheme and Detail	Irradiated Fuels Consolidated Furniture Scheme and Detail	Framework - Further Competition	29/11/2024	27/06/2025	≥ £100k to <£500k	Stephen Plummer		Planned
C1118	Operations - Reactor	Prototype Fast Reactor Detailed Design and Implementation of Cranes Upgrade	Prototype Fast Reactor Detailed Design and Implementation of Cranes Upgrade	Below Threshold - Competitive Tender	11/01/2025	25/12/2026	≥ £100k to <£500k	Lynsey Will		Planned
C1224	Operations - Maintenance & Engineering Support	Provision of a Gamma Calibration Jig	Provision of a Gamma Calibration Jig	Open Procedure	01/04/2025	31/12/2025	≥ £100k to <£500k	Fraser Bruce		Planned
C15131	Operations - Maintenance & Engineering Support	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement – Set up of a new Framework	01/05/2025	30/04/2029	≥ £1m to <£5m	Carly Erridge	CFA/21/0002-0010	Pre-Plan
C1155	Operations - Waste	Supply of Heavy Weight Towing Vehicle	Supply of Heavy Weight Towing Vehicle	Open Procedure	01/05/2025	01/04/2026	≥ £100k to <£500k	Carly Erridge	3300028934	Planned
C1167	Strategic Programme	Fuel Cycle Area North Concept Decommissioning Planning	Fuel Cycle Area North Concept Decommissioning Planning	Framework - Further Competition	01/05/2025	30/05/2026	≥ £1m to <£5m	Robert McDonald		Planned
C1120	Strategic Programme	Framework Agreement for the Manufacture and Supply of Half Height ISO Low Level	Framework Agreement for the Manufacture and Supply of Half Height ISO Low Level Waste Containers	Framework Agreement – Set up of a new Framework	01/07/2025	30/06/2029	≥ £10m to <£25m	Janet Rosie	CFA/12/0048 - CFA/12/0049	Planned
C11262	Finance	U4BW Software as a Service (SaaS)	Unit4 Business World (U4BW) Software as a Service (SaaS)	Framework - Direct Award	01/07/2025	30/06/2028	≥ £500k to <£1m	Louise Gunn	3300026361	Pre-Plan
C13988	Operations - Waste	Gravity Receipt Tank Ladder Replacement	Gravity Receipt Tank Ladder Replacement	Below Threshold - Competitive Tender	08/07/2025	08/01/2026	< £100k	Donna Stewart		Planned