## External Plan Format
Magnox Limited Procurement Plan as at end of March 2022
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded | STATUS
ASM 0698 | Asset Management | Chapelcross | R1, R2, R3 & R4 - Replace windows and frames with cladding | Construction | sukyee.hermon@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-04-06 | (f) | 2022-07-05 | (f) | Tend: Celadon, Nuvia, Doosan Keltbray, Squibb | 03. Call off from existing contract/ framework
ASM 0859 | Asset Management | Enablers | LC28 Inspections 2023/24+ for All Sites | Support Services | sue.i.mattravers@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2022-07-05 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
ASM 0984 | Asset Management | Hinkley | Hinkley wireless Fire detection system | Support Services | steven.j.lock@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2022-04-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 07. ITT in preparation
ASM 1065 | Asset Management | Oldbury | Oldbury Site Fire System Maintenance | Maintenance | steven.j.lock@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | n/a | 2021-10-08 | (a) | 2022-01-06 | (a) | Siemens Plc | 12. Contract in place
ASM 1083 | Asset Management | Trawsfynydd | Purchase & Installation of liquid scintillation counter (A511001NS TRI-CARB 5110TR 220 V W/O SRC) | Engineering | sian.draper@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-12-07 | (a) | 2022-01-06 | (a) | PerkinElmer LAS (UK) Ltd | 12. Contract in place
ASM 1084 | Asset Management | Harwell | Independent Assurance Review of Harwell SSPs´ -2,3,5,8,910 - in accordance with the attached Frazer Nash proposal Services / Value for FY 2022/23, | Design services/support | cathryn.m.pritchard@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-12-07 | (a) | 2022-01-06 | (a) | Frazer Nash Consultancy Ltd | 12. Contract in place
ASM 1086 | Asset Management | Dungeness | ORTEC Integrated Cryocooling System, for PopTop Detector | Plant & Equipment & Materials | steven.j.lock@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-11-07 | (a) | 2022-02-05 | (a) | AMETEK (GB) Limited | 12. Contract in place
ASM 1087 | Asset Management | Enablers | Bristol HUB: Tenants Access Control, Builders Work for Access Control, Tenants CCTV Work Station, Fuse Upgrade 2&3 Floors, Additional AC Door F12’ & Fixtures & fittings, furniture | Maintenance | kelly.sutherland@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2022-01-06 | (a) | 2022-03-07 | (a) | TSB Bank plc | 11. Contract awarded
ASM 1088 | Asset Management | Enablers | Bristol HUB: Rental Charges | Utilities | kelly.sutherland@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-12-07 | (a) | 2022-02-05 | (a) | Avison Young (UK) Ltd t/a Avison Young (NDA Property Rent/Services) | 12. Contract in place
ASM 1089 | Asset Management | Harwell | Civil Nuclear Constabulary costs at Harwell Site for 2022/23 | Maintenance | paul.grant@magnoxsites.com | Sole Source - No Choice | £5m to £10m | n/a | 2022-01-06 | (a) | 2022-03-07 | (a) | Civil Nuclear Constabulary | 11. Contract awarded
ASM 1090 | Asset Management | Oldbury | Portable Office Unit Hire for Oldbury | Support Services | charlotte.waller@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-11-07 | (a) | 2022-03-07 | (a) | Portable Offices | 12. Contract in place
DEC 0012 | Decommissioning | Trawsfynydd | Height Reduction - Capping Roof walls | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | Other - No Competition | £500k to £1m | 2022-04-04 | 2022-04-06 | (f) | 2022-06-05 | (f) | Not yet confirmed
DEC 0016 | Decommissioning | Harwell | LETP Land Re-instatement & SUDS system (Package 8b) | Construction | sally.j.dive@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2023-01-01 | (f) | 2023-05-11 | (f) | Not yet confirmed
DEC 0140 | Decommissioning | Sizewell | Deplant Crane Grab | Engineering | sarah.j.deeble@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2023-01-15 | 2023-02-10 | (f) | 2023-04-11 | (f) | Not yet confirmed
DEC 0181 | Decommissioning | Winfrith | Disposal of concrete lined drums | Waste management, disposal & storage | Jed.Bonsor@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2022-06-05 | (f) | 2022-11-02 | (f) | Tend: Inutec Limited | 02. Strategy being developed
DEC 0409 | Decommissioning | Oldbury | Construction Joints/Voids | Construction | louise.x.brown@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2023-01-01 | (f) | 2023-04-11 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0411 | Decommissioning | Wylfa | Electrical Overlay System (EOS) Phase 2 - On Site Distribution | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-05-28 | 2021-08-09 | (a) | 2022-04-06 | (f) | Tend: Ansaldo Nuclear,LCA Group, Morsons Projects, UK Power Networks | 10. Identification of preferred bidder
DEC 0418 | Decommissioning | Dungeness | DNA Boilers - Turbine Hall Infill | Construction | richard.sadd@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-05-05 | 2022-05-06 | (f) | 2022-07-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0419 | Decommissioning | Dungeness | DNA Boilers - Deplant & demolition of ancilliary buildings | Construction | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | n/a | 2022-04-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0439 | Decommissioning | Oldbury | Turbine Hall Demolition | Decommissioning, Demolition & Deplant | pauline.z.mackemsley@magnoxsites.com | Mini Competition F/W | £10m to £25m | 2023-01-06 | 2023-01-01 | (f) | 2023-04-11 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0446 | Decommissioning | Sizewell | Turbine Hall Demolition and removal of Boiler House Legacy Scaffolding | Decommissioning, Demolition & Deplant | danielle.staples@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2022-02-05 | (a) | 2022-06-05 | (f) | Tend: KDC, Erith, Keltbray | 03. Call off from existing contract/ framework
DEC 0469 | Decommissioning | Dungeness | Active Drains Reception Tank (ADRT) pipework supply & installation | Construction | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0486 | Decommissioning | Dungeness | Design & install blockwork for sealing the flask passages for R1 and R2 | Construction | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-05-06 | (f) | 2022-07-05 | (f) | Tend: IDC, Kaefer, Altrad, OBR Construction | 07. ITT in preparation
DEC 0492 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-10-28 | 2022-11-02 | (f) | 2023-01-01 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0520 | Decommissioning | Maentwrog | Reservoir Inspections and Dam Movement Survey - new contract - August 22 | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-04-06 | (f) | 2022-09-03 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0523 | Decommissioning | Trawsfynydd | Concrete and Brick Sampling and characterisation for Ponds Down Project | Engineering | ruth.cox@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2022-06-05 | (f) | 2022-08-04 | (f) | Tend: LLWR | 02. Strategy being developed
DEC 0529 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Divers | Engineering | Shelley.Lawrence@magnoxsites.com | OJEU/FTS Open | £1m to £5m | 2022-08-23 | 2022-10-03 | (f) | 2023-03-12 | (f) | Not yet confirmed | 01. On the horizon
DEC 0530 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Electrical Works | Engineering | Shelley.Lawrence@magnoxsites.com | OJEU/FTS Open | £100k to £500k | 2022-08-23 | 2022-10-03 | (f) | 2023-03-12 | (f) | Not yet confirmed | 01. On the horizon
DEC 0531 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Mechanical Works | Plant & Equipment & Materials | Shelley.Lawrence@magnoxsites.com | OJEU/FTS Open | £100k to £500k | 2022-08-23 | 2022-10-03 | (f) | 2023-03-12 | (f) | Not yet confirmed | 01. On the horizon
DEC 0532 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Ventilation | Plant & Equipment & Materials | Shelley.Lawrence@magnoxsites.com | OJEU/FTS Open | £100k to £500k | 2022-08-23 | 2022-10-03 | (f) | 2023-03-12 | (f) | Not yet confirmed | 01. On the horizon
DEC 0538 | Decommissioning | Sizewell | AB/CD Boiler Houses Asbestos Removal | Hazardous materials removal | sarah.j.deeble@magnoxsites.com | Mini Competition F/W | £25m to £50m | 2023-04-08 | 2023-05-11 | (f) | 2023-07-10 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0560 | Decommissioning | Dungeness | DNA Boilers - Boilers main option - preparation of Works Information | Construction | david.m.sanderson@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2022-02-05 | (a) | 2022-03-07 | (a) | Jacobs Ltd | 12. Contract in place
DEC 0569 | Decommissioning | Harwell | POCO and Characterisation | Construction | sally.j.dive@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-02-05 | (a) | 2022-05-06 | (f) | Tend: Doosan Keltbray Nuvia NSG | 03. Call off from existing contract/ framework
DEC 0597 | Decommissioning | Trawsfynydd | Safestores Weather Enveliope (EXECUTION phase) | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | OJEU/FTS Comp Procedure with Negotiation | £25m to £50m | 2023-01-30 | 2023-02-10 | (f) | 2024-08-03 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0607 | Decommissioning | Wylfa | WP1 Demolition of Buildings North End of Site at Wylfa (inc CO2 Plant) - Execution Phase of works | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-11-07 | (a) | 2022-01-06 | (a) | KDC Contractors Ltd | 12. Contract in place
DEC 0620 | Decommissioning | Winfrith | Replacement of the SGHWR Ventilation HEPA Filter Banks and Fans | Engineering | christine.huckin@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-03-12 | (a) | 2022-03-07 | (a) | Exyte Hargreaves | 11. Contract awarded
DEC 0622 | Decommissioning | Winfrith | Car Park Works for SGHWR | Construction | Jed.Bonsor@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-06-10 | (a) | 2022-06-05 | (f) | Tend: MITIE | 03. Call off from existing contract/ framework
DEC 0625 | Decommissioning | Trawsfynydd | Performance Agreement with Snowdonia National Park Authority | Manpower | ruth.cox@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-08-09 | (a) | 2022-05-06 | (f) | Tend: Snowdonia National Park Authority | 10. Identification of preferred bidder
DEC 0643 | Decommissioning | Trawsfynydd | Ponds Crane Re-inspections | Plant & Equipment & Materials | ruth.cox@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2022-07-05 | (f) | 2022-09-03 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0644 | Decommissioning | Winfrith | Rail Extenstion to Building at Winfrith | Construction | janet.smith@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-04-11 | (a) | 2022-04-06 | (f) | Not yet confirmed | 10. Identification of preferred bidder
DEC 0674 | Decommissioning | Dungeness | Traffic Management Initial works implementation | Construction | richard.sadd@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-04-11 | (a) | 2022-06-05 | (f) | Tend: IDC | 10. Identification of preferred bidder
DEC 0679 | Decommissioning | Dungeness | DNA Boilers - Characterisation non-radioactive sample analysis (laboratory works) - all other plant areas but not boilers - NON-RAD Batch 4 | Waste management, disposal & storage | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2022-02-05 | (a) | 2022-03-07 | (a) | i2 Analytical | 11. Contract awarded
DEC 0683 | Decommissioning | Sizewell | Purchase of Proportional Sampler in support of AETP | Plant & Equipment & Materials | sarah.j.deeble@magnoxsites.com | Other - No Competition | £100k to £500k | 2022-05-05 | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0701 | Decommissioning | Dungeness | DNA Boilers - New Stores Building | Construction | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-04-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0703 | Decommissioning | Trawsfynydd | Access & Insulation Support to Ponds Deplant Project | Construction | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2022-03-07 | (a) | 2022-04-06 | (f) | Altrad | 03. Call off from existing contract/ framework
DEC 0708 | Decommissioning | Dungeness | Dismantle A Frame Crane & Remove Skip Mast | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | OJEU/FTS Open | <£100K | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0709 | Decommissioning | Dungeness | DNA Boilers - Supply of DAMAL Laboratory Building | Construction | david.m.sanderson@magnoxsites.com | OJEU/FTS Restricted | £500k to £1m | n/a | 2022-03-07 | (a) | 2022-05-06 | (f) | Tend: CCS Framework Providers under RM6014 - Lot 6 | 08. ITT issued
DEC 0712 | Decommissioning | Oldbury | Rolling Programme of Decommissiioning (RPD) Enablers FY 21-22 - Graphite Archiving | Manpower | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-10-08 | (a) | 2022-01-06 | (a) | NNL | 12. Contract in place
DEC 0720 | Decommissioning | Trawsfynydd | Ponds Complex Demolition - Execution | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | OJEU/FTS Comp Procedure with Negotiation | £5m to £10m | 2023-09-13 | 2023-11-07 | (f) | 2024-04-05 | (f) | Not yet confirmed
DEC 0731 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning (RPD) Enablers FY 22-23 - Digital Engineering Requirements | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2023-01-01 | (f) | 2023-04-11 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0733 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning (RPD) Enablers FY 21-22 - Feasibility Study - Graphite Treatment | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-04-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0738 | Decommissioning | Winfrith | Winfrith Sea Pipeline - Marine Engineering (civil) Consultant | Engineering | Jed.Bonsor@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-04-27 | 2022-09-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 01. On the horizon
DEC 0760 | Decommissioning | Harwell | Project Enabling Works Optioneering (line 2) (PHASE 2) | Engineering | Shelley.Lawrence@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-11-07 | (a) | 2022-02-05 | (a) | Jacobs | 12. Contract in place
DEC 0764 | Decommissioning | Harwell | Project Enabling Works Electrical Overlay (line 6) (PHASE TBC) | Engineering | Shelley.Lawrence@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-08-04 | (f) | 2022-12-02 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0770 | Decommissioning | Harwell | BEPO Reactor Decommissioning_scheme design | Design services/support | Jed.Bonsor@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2020-12-12 | (a) | 2022-02-05 | (a) | James Fisher Nuclear Ltd | 12. Contract in place
DEC 0773 | Decommissioning | Winfrith | EIA Support for Winfrith Sea Pipeline (Terrestrial Section) removal | Design services/support | Jed.Bonsor@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-12-02 | (f) | 2023-06-10 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0780 | Decommissioning | Maentwrog | Traws Reservoir- Butterfly Valve Vibration Testing | Engineering | lindsay.gibson@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-12-07 | (a) | 2022-01-06 | (a) | Wood Group UK Limited | 12. Contract in place
DEC 0785 | Decommissioning | Dungeness | DNA Boilers - Waste Clearance Facility - fit-out | Construction | richard.sadd@magnoxsites.com | Other - No Competition | <£100K | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0789 | Decommissioning | Dungeness | DNA Boilers - Installation of C&I to three site buildings (DAMAL, New stores, Waste Clearance Facility) | Engineering | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0790 | Decommissioning | Harwell | Characterisation Execution | Engineering | Shelley.Lawrence@magnoxsites.com | OJEU/FTS Open | £5m to £10m | n/a | 2023-06-10 | (f) | 2023-12-07 | (f) | Not yet confirmed
DEC 0801 | Decommissioning | Dungeness | DNA Boilers - Scope production for Demo of Reactor Build Annexes & Boilers - 2022-23 | Design services/support | david.m.sanderson@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2022-02-05 | (a) | 2022-03-07 | (a) | Jacobs | 12. Contract in place
DEC 0802 | Decommissioning | Dungeness | DNA Ponds - Supply & Deliver reconditioned portacabin | Construction | david.m.sanderson@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2022-03-07 | (a) | 2022-03-07 | (a) | Portakabin | 11. Contract awarded
DEC 0804 | Decommissioning | Trawsfynydd | Rolling Programme of Deccommissioning (RPD) - Scheme Design - Reactor Break In | Design services/support | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-08-04 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0805 | Decommissioning | Trawsfynydd | Rolling Programme of Deccommissioning (RPD) - Scheme Design - Out of Core Components & In Core Furniture | Design services/support | claire.scott@magnoxsites.com | OJEU/FTS Restricted | £1m to £5m | 2022-06-02 | 2022-07-05 | (f) | 2022-12-02 | (f) | Not yet confirmed
DEC 0806 | Decommissioning | Trawsfynydd | Rolling Programme of Deccommissioning (RPD) - Scheme Design - Retrievals & Processing Equipment (Waste) | Design services/support | claire.scott@magnoxsites.com | OJEU/FTS Restricted | £1m to £5m | n/a | 2022-09-03 | (f) | 2023-03-12 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0807 | Decommissioning | Trawsfynydd | Rolling Programme of Deccommissioning (RPD) - Scheme Design - Building Modifications | Design services/support | claire.scott@magnoxsites.com | OJEU/FTS Restricted | £500k to £1m | n/a | 2023-02-10 | (f) | 2023-08-09 | (f) | Not yet confirmed
DEC 0809 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning (RPD) - Enablers FY 21-22 Collamater Heads for Characterisation | Consumables | claire.scott@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2022-02-05 | (a) | 2022-03-07 | (a) | Chapell Engineering | 11. Contract awarded
ENA 0451 | Enablers | Enablers | ePIT (Electronic Periodic Inspection & Testing System) | IT hardware/software | debbie.collin@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2022-03-07 | 2022-05-06 | (f) | 2022-08-04 | (f) | Not yet confirmed | 05. Advert published
ENA 0651 | Enablers | Enablers | NSAN Memebership - Annual Renewal Fee | Support Services | angharad.williams@magnoxsites.com | Sole Source - No Choice | <£100K | 2021-11-24 | 2021-12-07 | (a) | 2022-02-05 | (a) | National Skills Academy for Nuclear Ltd | 12. Contract in place
FRM 0016 | Technical Services | Multi Site Framework | Laundry & Decontamination Services 2021+ | Facilities Management | katie.bateman@magnoxsites.com | Sole Source - No Choice | £10m to £25m | n/a | 2021-10-08 | (a) | 2022-01-06 | (a) | UniTech Services Group Ltd | 12. Contract in place
FRM 0034 | People | Collaborative Framework | Health Physics Resources CP 3 (2022 - 2028) | Health & Safety | andrew.mclellan@magnoxsites.com | Collaborative (NDA Estate - Gold & Silver) | £50m to £100m | n/a | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') now open for supplier registration and pre-qualification | 11. Contract awarded
FRM 0054 | Technical Services | Multi Site Framework | Stack Characterisation & Evaluation and Dispersed Oil Particulate Filter Testing New: 2022-2027 | Engineering | castel.x.fairlie@magnoxsites.com | OJEU/FTS Open | £500k to £1m | n/a | 2021-12-07 | (a) | 2022-03-07 | (a) | Ricardo-AEA Ltd | 11. Contract awarded
FRM 0070 | Technical Services | Multi Site Framework | Calibration & Maintenance of Radiological Measuring Instruments 2022+ (Metrology) | Engineering | caroline.j.milner@magnoxsites.com | OJEU/FTS Open | £5m to £10m | n/a | 2022-05-06 | (f) | 2022-09-03 | (f) | Not yet confirmed | 07. ITT in preparation
FRM 0091 | Technical Services | Collaborative Framework | Statutory Examinations Post 2022 | Engineering | caroline.j.milner@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | 2021-10-14 | 2021-10-08 | (a) | 2022-03-07 | (a) | BUREAU VERITAS (C) | 11. Contract awarded
FRM 0093 | Decommissioning F | Multi Site Framework | DAR: Decommissioning, Asbestos & Removal [ex Deplant & Demolition Framework] | Construction | nicola.j.smith-lee@magnoxsites.com | OJEU/FTS Restricted | £250m plus | 2021-10-28 | 2022-04-06 | (f) | 2023-02-10 | (f) | Not yet confirmed | 06. EoIs being assessed
FRM 0100 | Technical Services | Multi Site Framework | Dosimetry 2022+ | Engineering | caroline.j.milner@magnoxsites.com | OJEU/FTS Open | £5m to £10m | 2022-05-16 | 2022-05-06 | (f) | 2022-09-03 | (f) | Not yet confirmed
FRM 0116 | Technology | Collaborative Framework | MFD Copiers Support 2023+ | Plant & Equipment & Materials | isla.fray@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2022-07-05 | (f) | 2022-11-02 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0125 | Technology | Multi Site Framework | PMRS Project Controls Suite (2022-2025) | IT hardware/software | andrew.mclellan@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2022-02-05 | (a) | 2022-06-05 | (f) | Tend: Cavendish Nuclear | 09. Tenders being assessed
FRM 0126 | Technology | Multi Site Framework | COSSH Database (Replacement) | IT hardware/software | debbie.collin@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-07-03 | 2022-08-04 | (f) | 2022-11-02 | (f) | Not yet confirmed | 01. On the horizon
FRM 0129 | Asset Management F | Multi Site Framework | Site Security Systems 2023+ | Maintenance | paul.grant@magnoxsites.com | CCS F/W Call off | £25m to £50m | 2022-11-01 | 2022-12-02 | (f) | 2023-11-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
FRM 0130 | Asset Management F | Multi Site Framework | High Voltage Electricity Switchgear Maintenance (2023-2027) | Maintenance | paul.grant@magnoxsites.com | Sole Source - No Choice | £500k to £1m | 2022-10-29 | 2022-11-02 | (f) | 2023-01-01 | (f) | Tend: National Grid
FRM 0147 | Goods & Consumables | Collaborative Framework | Supply of Maintenance, Repair and Operations (MRO) consumables [2024+] | Consumables | castel.x.fairlie@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £10m to £25m | n/a | 2023-07-10 | (f) | 2024-01-06 | (f) | Not yet confirmed
FRM 0149 | Technical Services | Collaborative Framework | Engineering and EHS&Q Standards (on-line) 2022-2026 | Remediation & Environmental Services | katie.bateman@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2022-09-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 01. On the horizon
FRM 0151 | Technical Services | Collaborative Framework | Certification Services 2024-2028 | Remediation & Environmental Services | katie.bateman@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £100k to £500k | 2023-09-05 | 2023-11-07 | (f) | 2024-07-04 | (f) | Not yet confirmed
FRM 0152 | Technical Services | Collaborative Framework | IQA 2023+ | Engineering | caroline.j.milner@magnoxsites.com | Collaborative (NDA Estate - Gold & Silver) | £100k to £500k | 2022-08-01 | 2022-08-04 | (f) | 2023-09-08 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0157 | Decommissioning F | Berkeley | Berkeley Boiler House Remediation - Asbestos Removal and Demolition | Hazardous materials removal | sarah.j.deeble@magnoxsites.com | OJEU/FTS Comp Procedure with Negotiation | £10m to £25m | 2021-07-26 | 2021-09-08 | (a) | 2022-09-03 | (f) | Tend: Altrad Erith Doosan Babcock Nuvia Kaefer | 10. Identification of preferred bidder
FRM 0158 | Waste F | Berkeley | Berkeley Boiler House Remediation - Characterisation, Transportation and Disposal of Waste | Waste management, disposal & storage | sarah.j.deeble@magnoxsites.com | Direct Award F/W | £10m to £25m | n/a | 2021-11-07 | (a) | 2022-09-03 | (f) | Tend: Under LLWR Framework: AUGEAN CYCLIFE UNS WESTINGHOUSE TRADEBE | 03. Call off from existing contract/ framework
FRM 0159 | Goods & Consumables | Collaborative Framework | Tools and Consumables (2023 - 2027) | Consumables | james.hiller@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £10m to £25m | n/a | 2022-09-03 | (f) | 2023-05-11 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0166 | Corporate | Multi Site Framework | Business Travel 2021 + | Support Services | amy.vale@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2021-03-12 | (a) | 2022-02-05 | (a) | Click Travel | 12. Contract in place
FRM 0168 | People | Multi Site Framework | Legal Services [2022+] | Support Services | gissela.m.hughes@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
FRM 0170 | Technical Services | Multi Site Framework | Estates Management | Engineering | matt.p.eeley@magnoxsites.com | OJEU/FTS Open | £500k to £1m | 2021-11-08 | 2021-11-07 | (a) | 2022-04-06 | (f) | Not yet confirmed | 10. Identification of preferred bidder
FRM 0171 | Decommissioning F | Dungeness | Package 1: Demolition & Boiler and ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@magnoxsites.com | OJEU/FTS Comp Procedure with Negotiation | £50m to £100m | 2022-07-14 | 2022-09-03 | (f) | 2023-11-07 | (f) | Not yet confirmed
FRM 0176 | HR, Corp & Fleet | Multi Site Framework | Alternative Agency Supplied Workers Contract (2022 onwards) | Support Services | claire.jones@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | n/a | 2022-05-06 | (f) | 2022-09-03 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0182 | Technical Services | Multi Site Framework | Land Quality Services 2024+ | Remediation & Environmental Services | matt.p.eeley@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2023-06-12 | 2023-08-09 | (f) | 2024-01-06 | (f) | Not yet confirmed
WAS 0016 | Waste | Sizewell | AVDS Enabling Works and Services (Design and Build/Install) | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2023-02-10 | (f) | 2023-04-11 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0028 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - concept | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2022-11-09 | 2022-12-02 | (f) | 2023-06-10 | (f) | Not yet confirmed | 01. On the horizon
WAS 0060 | Waste | Sizewell | Design & Construction of Waste Transfer Area | Construction | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2022-12-02 | (f) | 2023-04-11 | (f) | Not yet confirmed
WAS 0065 | Waste | Oldbury | Waste Transfer Area (Design & Build) DV 26603 MCI | Construction | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-10-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0118 | Waste | Hinkley | Design & Build Waste Transfer Area | Engineering | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | 2022-11-26 | 2022-12-02 | (f) | 2023-04-11 | (f) | Not yet confirmed
WAS 0127 | Waste | Sizewell | Enablers for Filling House Access/Services | Waste management, disposal & storage | karen.maguire@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2022-06-05 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0340 | Waste | Hunterston | IONSIV Vacuum drying system | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | n/a | 2022-12-02 | (f) | 2023-04-11 | (f) | Not yet confirmed
WAS 0342 | Waste | Wylfa | MCI Phase 2 Charecterisation (FFAT) | Waste management, disposal & storage | suzanne.x.williams@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-12-07 | (a) | 2022-01-06 | (a) | LLWR | 12. Contract in place
WAS 0420 | Waste | Harwell | Extension of waste facility - Cat 1 | Construction | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-06-05 | (f) | 2022-12-02 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0447 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - development | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2022-07-04 | 2022-08-04 | (f) | 2023-02-10 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0448 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - execution | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £1m to £5m | 2022-07-04 | 2022-08-04 | (f) | 2023-02-10 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0463 | Waste | Oldbury | FED - Procurement and Manufacture of Sorting Equipment | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-10-15 | 2022-11-02 | (f) | 2023-01-01 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0464 | Waste | Oldbury | FED - Procurement of Temporary Structure for Sorting Facility | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-09-03 | 2022-10-03 | (f) | 2023-01-01 | (f) | Not yet confirmed | 01. On the horizon
WAS 0465 | Waste | Oldbury | Procurement of Design and BUILD Contract for WTA and OLA specific scope | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2022-10-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0507 | Waste | Wylfa | LAW/HAW Processing Facility Scheme Design | Waste management, disposal & storage | suzanne.macmillan@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | n/a | 2021-11-07 | (a) | 2022-04-06 | (f) | Tend: BATS | 10. Identification of preferred bidder
WAS 0525 | Waste | Hinkley | 5T FLT | Plant & Equipment & Materials | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-11-07 | (a) | 2022-03-07 | (a) | Briggs Eqpt UK | 11. Contract awarded
WAS 0526 | Waste | Hinkley | 15 Ltr bowsers (x2) | Consumables | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-08-09 | (a) | 2022-01-06 | (a) | Fuel Proof Ltd | 12. Contract in place
WAS 0544 | Waste | Multiple Sites | AVDS Service and Maint | Waste management, disposal & storage | mark.scales@magnoxsites.com | OJEU/FTS Restricted | £500k to £1m | n/a | 2022-06-05 | (f) | 2022-11-02 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0546 | Waste | Dungeness | Non Rad Waste Services four years | Waste management, disposal & storage | mark.scales@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-03-10 | 2022-05-24 | (f) | 2022-09-03 | (f) |  | 05. Advert published
WAS 0558 | Waste | Wylfa | LAW - Haw Facility Build | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2023-08-07 | 2023-09-08 | (f) | 2023-11-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0561 | Waste | Wylfa | MCI Facility | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2023-01-05 | 2023-01-01 | (f) | 2023-03-12 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0566 | Waste | Hinkley | Provision of basket (SIPA) | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2023-03-12 | (f) | 2023-06-10 | (f) | Not yet confirmed
WAS 0567 | Waste | Wylfa | Cross Site Transport | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2022-08-16 | 2022-09-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 01. On the horizon
WAS 0568 | Waste | Wylfa | B1 DSC4 Decontamination | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2022-07-05 | (f) | 2023-11-07 | (f) | Not yet confirmed
WAS 0570 | Waste | Oldbury | AVDS Enabling Works and Services (Design and Build/Install) | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2023-02-10 | (f) | 2023-04-11 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0589 | Waste | Hinkley | Compact Heavy Lift Truck - with boom attachement | Plant & Equipment & Materials | danielle.staples@magnoxsites.com | OJEU/FTS Open | £100k to £500k | n/a | 2022-06-05 | (f) | 2022-10-03 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0610 | Waste | Berkeley | Milwep Transition to Waste Ops | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2022-04-06 | (f) | 2022-05-06 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0624 | Waste | Multiple Sites | Mortuary Tube Structure - Furniture and grouting procurement | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | OJEU/FTS Open | £1m to £5m | n/a | 2022-05-06 | (f) | 2022-11-02 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0629 | Waste | Dungeness | Spacers (for use inside shielded drums) | Consumables | cheryl.d.downton@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0645 | Waste | Multiple Sites | General Radio Chemistry - Enviro and Effluent Lot 4 | Waste management, disposal & storage | mark.scales@magnoxsites.com | OJEU/FTS Open | £1m to £5m | n/a | 2022-04-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0646 | Waste | Wylfa | DCIC Storage Facility Detailed Design and Build New Store | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2023-09-08 | (f) | 2023-11-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0667 | Waste | Wylfa | Waste Compound Upgrade | Construction | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | 2022-03-17 | 2022-04-06 | (f) | 2022-07-05 | (f) | Not yet confirmed | 05. Advert published
WAS 0668 | Waste | Dungeness | Relocation of WWTF - design and execution | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-03-07 | (a) | 2022-06-05 | (f) | Tend: Celadon Doosan Keltbray Squibb LVI Nuvia | 03. Call off from existing contract/ framework
WAS 0676 | Waste | Harwell | Bulk Depleted Uranium Disposals @ Harwell | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | OJEU/FTS Open | £1m to £5m | n/a | 2022-08-04 | (f) | 2023-01-01 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0681 | Waste | Harwell | Tritium and C14 Monitoring Services - Compete services | Waste management, disposal & storage | mark.scales@magnoxsites.com | OJEU/FTS Open | £100k to £500k | n/a | 2022-04-06 | (f) | 2022-09-03 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0683 | Waste | Hinkley | Hinkley ISF Crane mods for 3m Boxes | Waste management, disposal & storage | fiona.pearse@magnoxsites.com | Sole Source - No Choice | £500k to £1m | n/a | 2021-11-07 | (a) | 2022-02-05 | (a) | Konecranes Demag UK Ltd | 12. Contract in place
WAS 0685 | Waste | Hinkley | HAI Phase 1b - Retrieval - Detailed Design, Manufacture and Installation | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £1m to £5m | n/a | 2022-10-03 | (f) | 2023-05-11 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0711 | Waste | Berkeley | Oxy Reduct - additional valves and pipework | Construction | karen.maguire@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-12-07 | (a) | 2022-02-05 | (a) | BOC | 12. Contract in place
WAS 0713 | Waste | Wylfa | Purchase of Fork Lift Truck | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-11-07 | (a) | 2022-02-05 | (a) | Impact Fork Trucks Ltd T/A Impact Handling | 12. Contract in place
WAS 0714 | Waste | Winfrith | Hire of a High Capacity Forklift Truck, (H30XD12) with a Safe Working Load of 30 Tonne, or similar. | Plant & Equipment & Materials | Kwadwo.Awuku@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-12-07 | (a) | 2022-02-05 | (a) | Briggs Eqpt UK | 12. Contract in place
WAS 0715 | Waste | Multiple Sites | Shielding and criticality technical support | Engineering | cheryl.d.downton@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-04-08 | 2022-04-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0718 | Waste | Multiple Sites | Walischmiller Spares - Renewal | Waste management, disposal & storage | mark.scales@magnoxsites.com | Sole Source - No Choice | £500k to £1m | 2022-11-22 | 2022-12-02 | (f) | 2023-02-10 | (f) | Walischmiller
WAS 0720 | Waste | Harwell | Site works at Harwell - X ray of 2 active 500L drums | Waste management, disposal & storage | kevin.l.sheppard@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2021-11-07 | (a) | 2022-01-06 | (a) | Oceaneering Int´l Services Ltd T/A Oceaneering OIS | 12. Contract in place
WAS 0721 | Waste | Hinkley | Fill Heads (for Resin skid) | Waste management, disposal & storage | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-04-11 | (a) | 2022-01-06 | (a) | Rhyal Engineering | 12. Contract in place
WAS 0722 | Waste | Multiple Sites | Grouting / Concrete of Mortuary Tubes into Concrete Boxes | Consumables | pauline.z.mackemsley@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2022-06-05 | (f) | 2022-08-04 | (f) | Tend: Amber Precast | 03. Call off from existing contract/ framework
WAS 0723 | Waste | Harwell | Transportation of Dragon and Gemini to Sellafiled | Transport of materials | pauline.z.mackemsley@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-12-07 | (a) | 2022-02-05 | (a) | Sellafield Ltd | 12. Contract in place
WAS 0724 | Waste | Hinkley | Pump Skid (for Bowsers) | Engineering | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-11-07 | (a) | 2022-03-07 | (a) | Tend: Penny Hydraulics Berry & Escott Mechatech | 11. Contract awarded
WAS 0726 | Waste | Winfrith | Disposal - Rad Waste | Waste management, disposal & storage | suzanne.x.williams@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-12-07 | (a) | 2022-02-05 | (a) | LLW Repository Ltd | 12. Contract in place
WAS 0727 | Waste | Dungeness | Site services - installation | Engineering | karen.maguire@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2022-04-06 | (f) | 2022-04-06 | (f) | Tend: Doosan Babcock | 03. Call off from existing contract/ framework