## External Plan Format
Magnox Limited Procurement Plan as at end of August 2021
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded | STATUS
ASM 0698 | Asset Management | Chapelcross | R1, R2, R3 & R4 - Replace windows and frames with cladding | Construction | mark.cullinane@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-10-08 | (f) | 2022-02-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
ASM 0706 | Asset Management | Wylfa | Station Transformer Tap Changer Maintenance | Engineering | adrian.h.williams@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-05-11 | (a) | 2021-06-10 | (a) | Tend: Transerv Europe Ltd | 12. Contract in place
ASM 0800 | Asset Management | Enablers | Asbestos Management - Assurance Contract (SEM) 2021, 2022, 2023, 2024 | Manpower | adrian.h.williams@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-03-12 | (a) | 2021-06-10 | (a) | Brunel University | 12. Contract in place
ASM 0812 | Asset Management | Chapelcross | Reactor Buildings - Replacement of Legacy Scaffolding and Access / Roofing & Handrails ACP-1428-CHX | Maintenance | mark.cullinane@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-09-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
ASM 0927 | Asset Management | Enablers | Concrete Defect Detection using AI | Support Services | sue.i.mattravers@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-04-11 | (a) | 2021-07-10 | (a) | MMI Engineering (Trading as Thornton Tomasetti) | 12. Contract in place
ASM 0970 | Asset Management | Enablers | Asbestos Management - Assurance Contract 2021, 2022, 2023, 2024 | Manpower | adrian.h.williams@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-07-10 | (a) | 2021-10-08 | (f) | Tend: HSE re Science & Research Centre | 08. ITT issued
ASM 0984 | Asset Management | Hinkley | Hinkley wireless Fire detection system | Support Services | mark.cullinane@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2021-11-07 | (f) | 2022-02-05 | (f) | Not yet confirmed | 02. Strategy being developed
ASM 1007 | Asset Management | Dungeness | Active and Foul Discharge Lines Maintenance and Inspections | Maintenance | sukyee.hermon@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-06-10 | (a) | 2021-09-08 | (f) | Tend: Falmouth Divers James Fisher Marine Services Seawork Marine Services | 09. Tenders being assessed
ASM 1020 | Asset Management | Enablers | Overhead Cranes Serve and Maint | Engineering | steven.j.lock@magnoxsites.com | OJEU/FTS Open | £1m to £5m | n/a | 2021-06-10 | (a) | 2021-10-08 | (f) | Not yet confirmed | 10. Identification of preferred bidder
ASM 1041 | Asset Management | Hunterston | Replacement of Degrading Chemistry Laboratory Assets | Engineering | sue.i.mattravers@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-08-09 | (a) | 2021-08-09 | (a) | AMETEK (GB) Limited | 11. Contract awarded
ASM 1043 | Asset Management | Enablers | Asbestos Management - Assurance Contract - Interim PO | Manpower | adrian.h.williams@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-08-09 | (a) | 2021-08-09 | (a) | HSE re Science & Research Centre | 11. Contract awarded
ASM 1044 | Asset Management | Wylfa | AETP Addressing Leaks Channel Works | Construction | adrian.h.williams@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-09-08 | (f) | 2021-09-08 | (f) | Tend: Balvac | 02. Strategy being developed
DEC 0016 | Decommissioning | Harwell | LETP Land Re-instatement & SUDS system (Package 8b) | Construction | sally.j.dive@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2021-09-08 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0140 | Decommissioning | Sizewell | Deplant Crane Grab | Engineering | sarah.j.deeble@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2023-01-15 | 2023-02-10 | (f) | 2023-04-11 | (f) | Not yet confirmed
DEC 0318 | Decommissioning | Oldbury | National Grid Sub Station hazard removal, deplant & demolition | Decommissioning, Demolition & Deplant | louise.x.brown@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2019-10-05 | (a) | 2021-06-10 | (a) | Celadon | 12. Contract in place
DEC 0408 | Decommissioning | Chapelcross | Decommissioning of Chapelcross Cooling Pond with the use of Nuclear Decommissioning Divers | Decommissioning, Demolition & Deplant | alison.cowan@magnoxsites.com | OJEU/FTS Open | £1m to £5m | n/a | 2021-11-07 | (f) | 2022-10-03 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0409 | Decommissioning | Oldbury | Construction Joints/Voids | Construction | louise.x.brown@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-02-05 | (f) | 2022-04-06 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0411 | Decommissioning | Wylfa | Electrical Overlay System Phase 2 | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-05-28 | 2021-08-09 | (a) | 2021-12-07 | (f) | Not yet confirmed | 08. ITT issued
DEC 0414 | Decommissioning | Wylfa | Deareator Floor - Asbestos Removal | Hazardous materials removal | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2020-12-12 | (a) | 2021-06-10 | (a) | ALtrad | 12. Contract in place
DEC 0418 | Decommissioning | Dungeness | SPCE - Turbine Hall Backfill | Construction | nicola.j.smith-lee@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0419 | Decommissioning | Dungeness | SPCE - Civil enablers including demolition of various buildings | Construction | nicola.j.smith-lee@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2022-01-24 | 2022-02-05 | (f) | 2022-05-06 | (f) | Not yet confirmed | 01. On the horizon
DEC 0426 | Decommissioning | Dungeness | SPCE - Standby Generator outage (hire of generators) | Engineering | nicola.j.smith-lee@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-09-08 | (f) | 2021-09-08 | (f) | Tend: Speedy Hire, Mona lift & Brigg | 07. ITT in preparation
DEC 0439 | Decommissioning | Oldbury | Turbine Hall Demolition | Decommissioning, Demolition & Deplant | sarah.j.deeble@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2022-01-01 | 2022-03-07 | (f) | 2022-08-04 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0446 | Decommissioning | Sizewell | Turbine Hall Decommissioning - enabling disconnection services. | Construction | sarah.j.deeble@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-10-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0455 | Decommissioning | Hunterston | Reactor Roof Repairs | Construction | mark.scales@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-02-26 | 2021-04-11 | (a) | 2021-09-08 | (f) | McConnell | 10. Identification of preferred bidder
DEC 0462 | Decommissioning | Sizewell | CD Boiler Houses - Scaffold Removal | Maintenance | sarah.j.deeble@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-12-07 | (f) | 2022-06-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0465 | Decommissioning | Maentwrog | Installation of a National Grid Platform for Ancillary Services (PAS) Interface System | IT hardware/software | claire.scott@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-01-03 | (a) | 2021-11-07 | (f) | Tend: TrueNorth | 10. Identification of preferred bidder
DEC 0469 | Decommissioning | Dungeness | Active Drains Reception Tank (ADRT) pipework supply & installation | Construction | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-10-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0486 | Decommissioning | Dungeness | Design & install blockwork for sealing the flask passages for R1 and R2 | Construction | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-04-06 | (f) | 2022-06-05 | (f) | Tend: IDC, Kaefer, Altrad, OBR Construction | 07. ITT in preparation
DEC 0492 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-10-28 | 2022-11-02 | (f) | 2023-01-01 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0494 | Decommissioning | Dungeness | SPCE - Filling of under ground structures | Construction | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2021-04-11 | (a) | 2021-09-08 | (f) | Tend: BAM, IDC, Kaymac and GSE | 10. Identification of preferred bidder
DEC 0498 | Decommissioning | Dungeness | SPCE - Fire Alarm System re-route cables around perimeter (phase 3) | Engineering | nicola.j.smith-lee@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-09-08 | (f) | 2021-10-08 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0520 | Decommissioning | Maentwrog | Reservoir Inspections and Dam Movement Survey - new contract - August 22 | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2021-11-26 | 2021-12-07 | (f) | 2022-09-03 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0523 | Decommissioning | Trawsfynydd | Concrete and Brick Sampling and characterisation for Ponds Down Project | Engineering | ruth.cox@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-10-08 | (f) | 2021-12-07 | (f) | Tend: LLWR | 02. Strategy being developed
DEC 0538 | Decommissioning | Sizewell | AB/CD Boiler Houses Asbestos Removal | Hazardous materials removal | sarah.j.deeble@magnoxsites.com | OJEU/FTS Restricted | £25m to £50m | 2021-11-22 | 2021-12-07 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0563 | Decommissioning | Maentwrog | Estate Management Call off Contract - NEW 4 year contract Nov 2021 | Maintenance | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-10-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0569 | Decommissioning | Harwell | POCO and Characterisation | Construction | sally.j.dive@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-11-07 | (f) | 2021-12-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0579 | Decommissioning | Dungeness | SPCE - DAMAL - Purchase temporary buildings and provide services connection | Support Services | nicola.j.smith-lee@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | n/a | 2021-10-08 | (f) | 2021-11-07 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0592 | Decommissioning | Hunterston | NEffTP skid mounted cartiridge filtration mechanical installation WP2 | Engineering | louise.x.brown@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-01-11 | (a) | 2021-06-10 | (a) | JGC Engineering & Technical Solutions | 12. Contract in place
DEC 0597 | Decommissioning | Trawsfynydd | Safestores Weather Enveliope (EXECUTION phase) | Engineering | ruth.cox@magnoxsites.com | OJEU/FTS Comp Procedure with Negotiation | £100m to £250m | 2022-12-02 | 2023-01-01 | (f) | 2023-06-10 | (f) | Not yet confirmed
DEC 0598 | Decommissioning | Hunterston | Weather Envelope | Engineering | alison.cowan@magnoxsites.com | OJEU/FTS Open | £25m to £50m | n/a | 2022-07-05 | (f) | 2023-01-01 | (f) | Not yet confirmed
DEC 0600 | Decommissioning | Dungeness | Reactor Void Water Diversion | Engineering | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2021-04-08 | 2021-05-11 | (a) | 2021-09-08 | (f) | Not yet confirmed | 10. Identification of preferred bidder
DEC 0607 | Decommissioning | Wylfa | WP1 Demolition of Buildings North End of Site at Wylfa (inc CO2 Plant) - Execution Phase of works | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-11-07 | (f) | 2022-01-06 | (f) | Tend: Celadon | 03. Call off from existing contract/ framework
DEC 0620 | Decommissioning | Winfrith | Replacement of the SGHWR Ventilation HEPA Filter Banks and Fans | Engineering | christine.huckin@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-03-12 | (a) | 2021-09-08 | (f) | Tend: Exyte Hargreaves, Gow's, Kaefer Ltd. Nuvia | 10. Identification of preferred bidder
DEC 0622 | Decommissioning | Winfrith | Car Park Works for SGHWR | Construction | Jed.Bonsor@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-06-10 | (a) | 2021-09-08 | (f) | Tend: MITIE | 03. Call off from existing contract/ framework
DEC 0625 | Decommissioning | Trawsfynydd | Performance Agreement with Snowdonia National Park Authority | Manpower | ruth.cox@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-08-09 | (a) | 2021-10-08 | (f) | Tend: Snowdonia National Park Authority | 08. ITT issued
DEC 0630 | Decommissioning | Dungeness | SPCE - Boilers radioactive sample/coupon taking for characterisation analysis (analysis not part of this scope) | Waste management, disposal & storage | kim.cook@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-06-10 | (a) | 2021-09-08 | (f) | Tend: Echo, corcut, BD Nuclear, Doosan, Jacobs, Ansaldo | 09. Tenders being assessed
DEC 0643 | Decommissioning | Trawsfynydd | Ponds Crane Re-inspections | Plant & Equipment & Materials | ruth.cox@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-06-10 | (a) | 2022-02-05 | (f) | Tend: Kone Crane Care | 10. Identification of preferred bidder
DEC 0644 | Decommissioning | Winfrith | Rail Extenstion to Building at Winfrith | Construction | janet.smith@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-04-11 | (a) | 2021-11-07 | (f) | Not yet confirmed | 10. Identification of preferred bidder
DEC 0656 | Decommissioning | Maentwrog | Outage Welding Support for Outage Period FY 21-22 | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-04-11 | (a) | 2021-06-10 | (a) | Mona Lifting Ltd | 12. Contract in place
DEC 0658 | Decommissioning | Dungeness | Traffic Management Design | Manpower | richard.sadd@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-04-11 | (a) | 2021-09-08 | (f) | Tend: IDC | 10. Identification of preferred bidder
DEC 0660 | Decommissioning | Maentwrog | Structural investigations of Dams at Trawsfynydd | Construction | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-06-10 | (a) | 2021-08-09 | (a) | Celtest | 11. Contract awarded
DEC 0665 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning (RPD) Enablers FY 21-22 - Feasibility Study Traws Boiler Removal | Engineering | claire.scott@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-07-10 | (a) | 2021-08-09 | (a) | Mammeot | 11. Contract awarded
DEC 0666 | Decommissioning | Multi Site | Rolling Programme of Decommissioning (RPD) Enablers FY 21-22- Knowledge Sharing | Engineering | claire.scott@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-07-10 | (a) | 2021-09-08 | (f) | James Fisher Nuclear Ltd | 09. Tenders being assessed
DEC 0667 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning (RPD) Enablers FY 21-22 - Digital Imaging of Drawings | IT hardware/software | claire.scott@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-07-10 | (a) | 2021-09-08 | (f) | Tend: Genus | 09. Tenders being assessed
DEC 0669 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning (RPD) Enablers FY 21-22 - Proposal for Maturity RCF | Manpower | claire.scott@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-06-10 | (a) | 2021-07-10 | (a) | Oxford Global Projects | 12. Contract in place
DEC 0674 | Decommissioning | Dungeness | Traffic Management Initial works implementation | Construction | richard.sadd@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-04-11 | (a) | 2021-09-08 | (f) | Tend: IDC | 10. Identification of preferred bidder
DEC 0677 | Decommissioning | Dungeness | Minor Civil Works to support Phase 2 | Construction | david.m.sanderson@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-09-08 | (f) | 2021-09-08 | (f) | Tend: IDC | 02. Strategy being developed
DEC 0678 | Decommissioning | Dungeness | SPCE - Characterisation non-radioactive sample analysis (laboratory works) - all other plant areas but not boilers (Batch 3) | Waste management, disposal & storage | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-09-08 | (f) | 2021-10-08 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0679 | Decommissioning | Dungeness | SPCE - Characterisation non-radioactive sample analysis (laboratory works) - all other plant areas but not boilers (Batch 4) | Waste management, disposal & storage | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-10-08 | (f) | 2021-11-07 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0683 | Decommissioning | Sizewell | Purchase of Proportional Sampler in support of AETP | Plant & Equipment & Materials | sarah.j.deeble@magnoxsites.com | Sole Source - No Choice | £100k to £500k | 2022-02-04 | 2022-02-05 | (f) | 2022-04-06 | (f) | Tend: NSG Environmental Ltd | 01. On the horizon
DEC 0686 | Decommissioning | Dungeness | SPCE - Project visulaisation/sequencing for Boilers demolition, crane build and lifting operations including enablers. | Manpower | richard.sadd@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-07-10 | (a) | 2021-09-08 | (f) | Tend: Tannahill Reay | 09. Tenders being assessed
DEC 0691 | Decommissioning | Winfrith | Provision of the 6m3 Box Encapsulation Plant for the Winfrith Site (Mini MILWEP) | Engineering | Jed.Bonsor@magnoxsites.com | Direct Award F/W | £5m to £10m | n/a | 2021-06-10 | (a) | 2021-06-10 | (a) | NSG Environmental | 12. Contract in place
DEC 0692 | Decommissioning | Dungeness | Secondment Costs | Manpower | lindsay.gibson@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2021-05-11 | (a) | 2021-06-10 | (a) | Nuclear Transport Services | 12. Contract in place
DEC 0698 | Decommissioning | Sizewell | Licence to Access Ground Investigation Works by EDF NGL at SZA | Construction | lindsay.gibson@magnoxsites.com | Other - No Competition | <£100K | n/a | 2021-05-11 | (a) | 2021-06-10 | (a) | EDF Energy Nuclear Generation Ltd | 12. Contract in place
DEC 0701 | Decommissioning | Dungeness | DAMAL Buildings new laboratory and stores facility | Construction | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | 2022-02-09 | 2022-03-07 | (f) | 2022-06-05 | (f) | Not yet confirmed | 01. On the horizon
DEC 0703 | Decommissioning | Trawsfynydd | Access & Insulation Support to Ponds Deplant Project | Construction | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2022-02-05 | (f) | 2022-04-06 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0704 | Decommissioning | Trawsfynydd | XRD Analysis of Concrete Fibres at Traws | Design services/support | ruth.cox@magnoxsites.com | Sole Source - No Choice | <£100K | 2021-05-27 | 2021-08-09 | (a) | 2021-08-09 | (a) | HSE | 11. Contract awarded
DEC 0705 | Decommissioning | Oldbury | PFP Civil Works | Construction | louise.x.brown@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-06-10 | (a) | 2021-08-09 | (a) | I D Corcoran | 11. Contract awarded
ENA 0446 | Enablers | Enablers | Pensions Admin 2021/22 | Support Services | sian.draper@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-04-11 | (a) | 2021-06-10 | (a) | Electricity Pensions Limited | 12. Contract in place
ENA 0451 | Enablers | Enablers | ePIT (Electronic Periodic Inspection & Testing System) | IT hardware/software | isla.fray@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2021-09-29 | 2021-11-07 | (f) | 2022-02-05 | (f) | Not yet confirmed | 02. Strategy being developed
ENA 0453 | Enablers | Enablers | Ortec TransSpec High Resolution Gamma Spectrometer (HGRS) | Health & Safety | sian.draper@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-04-11 | (a) | 2021-06-10 | (a) | AMETEK (GB) Limited | 12. Contract in place
ENA 0454 | Enablers | Enablers | Documents Archieving 2021/2022 | Manpower | annette.turner@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-04-11 | (a) | 2021-06-10 | (a) | NDA Archives Limited | 12. Contract in place
ENA 0464 | Enablers | Enablers | MS EA Licenses FY 23 24 | IT hardware/software | sian.draper@magnoxsites.com | CCS F/W Call off | £5m to £10m | 2021-02-12 | 2021-03-12 | (a) | 2021-07-10 | (a) | NDA | 12. Contract in place
ENA 0465 | Enablers | Enablers | Pensions Secretarial Support Services 2021/2022 | Support Services | annette.turner@magnoxsites.com | Sole Source - No Choice | <£100K | 2021-05-08 | 2021-06-10 | (a) | 2021-07-10 | (a) | Barnett Waddingham LLP | 12. Contract in place
ENA 0466 | Enablers | Enablers | Nuclear Graduate Costs - Cohort 15 - 2022/23 | Support Services | sian.draper@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-03-11 | 2021-04-11 | (a) | 2021-07-10 | (a) | Energus | 12. Contract in place
ENA 0467 | Enablers | Enablers | Permanent recruitment of Deputy Company Secretary | Support Services | alwena.owen@magnoxsites.com | Sole Source - No Choice | <£100K | 2021-05-22 | 2021-06-10 | (a) | 2021-08-09 | (a) | DMJ Recruitment LTD | 11. Contract awarded
ENA 0468 | Enablers | Enablers | Provision of LinkedIN Campaigns facility | Support Services | alwena.owen@magnoxsites.com | Sole Source - No Choice | <£100K | 2021-06-22 | 2021-07-10 | (a) | 2021-08-09 | (a) | Linkedin Ireland Unlimited Company | 11. Contract awarded
ENA 0471 | Enablers | Enablers | Pension Administration - Electricity Supply Pension Scheme | Support Services | annette.turner@magnoxsites.com | Sole Source - No Choice | £500k to £1m | n/a | 2021-06-10 | (a) | 2021-08-09 | (a) | RPMI Limited re EPAL | 11. Contract awarded
FRM 0016 | Engineering | Multi Site Framework | Laundry & Decontamination Services 2021+ | Facilities Management | katie.bateman@magnoxsites.com | Sole Source - No Choice | £10m to £25m | n/a | 2021-09-08 | (f) | 2022-01-06 | (f) | Tend: Unitech | 07. ITT in preparation
FRM 0034 | Prof Services | Collaborative Framework | Health Physics Resources CP 3 (2022 - 2028) | Health & Safety | andrew.mclellan@magnoxsites.com | Collaborative (NDA Estate - Gold & Silver) | £50m to £100m | n/a | 2022-02-05 | (f) | 2022-01-06 | (f) | Tend: Intention is via DPS, so no ITT etc | 02. Strategy being developed
FRM 0038 | HR, Corp & Fleet | Collaborative Framework | Lease Cars 2021+ | Support Services | holly.griffith@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | n/a | 2021-03-12 | (a) | 2021-06-10 | (a) | KINTO UK LTD | 12. Contract in place
FRM 0044 | Engineering | Multi Site Framework | PEACH (Plant Equip & Crane Hire | Plant & Equipment & Materials | matt.p.eeley@magnoxsites.com | OJEU/FTS Open | £1m to £5m | 2022-03-05 | 2022-04-06 | (f) | 2022-10-03 | (f) | Not yet confirmed
FRM 0048 | Engineering | Collaborative Framework | Supply of PPE & Workwear (2021 - 2025) | Consumables | james.hiller@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | n/a | 2020-11-12 | (a) | 2021-07-10 | (a) | Romar(C); | 12. Contract in place
FRM 0054 | Engineering | Multi Site Framework | HEPA Filter Testing and Stack Sampling (Har/Winf) New: 2022-2027 | Engineering | castel.x.fairlie@magnoxsites.com | OJEU/FTS Open | £100k to £500k | n/a | 2021-10-08 | (f) | 2022-02-05 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0058 | Engineering | Collaborative Framework | Supply of Lab Consumables and Chemicals NEW: 2021-2025 | Consumables | castel.x.fairlie@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2021-02-10 | (a) | 2021-10-08 | (f) | Not yet confirmed | 10. Identification of preferred bidder
FRM 0070 | Engineering | Multi Site Framework | Calibration & Maintenance of Radiological Measuring Instruments 2022+ (Metrology) | Engineering | caroline.j.milner@magnoxsites.com | OJEU/FTS Open | £5m to £10m | n/a | 2021-10-08 | (f) | 2022-03-07 | (f) | Not yet confirmed | 07. ITT in preparation
FRM 0091 | Engineering | Collaborative Framework | Statutory Examinations Post 2022 | Engineering | caroline.j.milner@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | 2021-09-07 | 2021-09-08 | (f) | 2022-01-06 | (f) | Not yet confirmed
FRM 0093 | Decommissioning F | Multi Site Framework | DAR: Decommissioning, Asbestos & Removal [ex Deplant & Demolition Framework] | Construction | nicola.j.smith-lee@magnoxsites.com | OJEU/FTS Restricted | £250m plus | 2021-09-20 | 2021-12-07 | (f) | 2023-01-01 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0100 | Engineering | Multi Site Framework | Dosimetry 2022+ | Engineering | caroline.j.milner@magnoxsites.com | OJEU/FTS Open | £5m to £10m | 2021-09-30 | 2021-10-08 | (f) | 2022-01-06 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0105 | Prof Services | Multi Site Framework | Project Controls 2022+ | Manpower | michelle.a.edwards@magnoxsites.com | CCS F/W Call off | £25m to £50m | n/a | 2021-05-11 | (a) | 2021-09-08 | (f) | Tend: Turner & Townsend Gleeds | 03. Call off from existing contract/ framework
FRM 0107 | HR, Corp & Fleet | Collaborative Framework | Learning & Development services 2022+ | Support Services | holly.griffith@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £5m to £10m | 2021-03-12 | 2021-05-11 | (a) | 2021-09-08 | (f) | Tend: Babcock Training Ltd SOPRA Group Ltd LRTT Ltd | 10. Identification of preferred bidder
FRM 0108 | Asset Management F | Multi Site Framework | Asbestos Analytical Services 2021 + | Hazardous materials removal | steven.j.lock@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2020-09-28 | 2021-01-11 | (a) | 2021-06-10 | (a) | Tend: BV; Element; Environtech Ltd; Lucion Environmental Ltd; Santia Asbestos Management Ltd; SOCOTEC UK LTD | 12. Contract in place
FRM 0113 | HR, Corp & Fleet | Multi Site Framework | Occupational Health (Next Contract) | Support Services | annette.turner@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2021-06-10 | (a) | 2021-09-08 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
FRM 0116 | IT | Collaborative Framework | MFD Copiers Support 2023+ | Plant & Equipment & Materials | isla.fray@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2022-03-07 | (f) | 2022-11-02 | (f) | Not yet confirmed | 01. On the horizon
FRM 0125 | IT | Multi Site Framework | PMRS Project Controls Suite (Replacement) | IT hardware/software | andrew.mclellan@magnoxsites.com | Sole Source - No Choice | £1m to £5m | 2022-01-02 | 2022-02-05 | (f) | 2022-03-07 | (f) | Not yet confirmed | 01. On the horizon
FRM 0126 | IT | Multi Site Framework | COSSH Database (Replacement) | IT hardware/software | andrew.mclellan@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-07-03 | 2022-08-04 | (f) | 2022-11-02 | (f) | Not yet confirmed
FRM 0129 | Asset Management F | Multi Site Framework | Site Security Systems (2022-2026) | Maintenance | amanda.j.clark@magnoxsites.com | OJEU/FTS Restricted | £5m to £10m | 2021-12-14 | 2022-02-05 | (f) | 2022-07-05 | (f) | Not yet confirmed | 01. On the horizon
FRM 0130 | Asset Management F | Multi Site Framework | High Voltage Electricity Switchgear Maintenance (2023-2027) | Maintenance | amanda.j.clark@magnoxsites.com | Sole Source - No Choice | £500k to £1m | 2022-10-29 | 2022-11-02 | (f) | 2023-01-01 | (f) | Tend: National Grid
FRM 0149 | Engineering | Collaborative Framework | Engineering and EHS&Q Standards (on-line) 2022-2026 | Remediation & Environmental Services | katie.bateman@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2022-09-03 | (f) | 2022-12-02 | (f) | Not yet confirmed
FRM 0152 | Engineering | Collaborative Framework | IQA 2023+ | Engineering | caroline.j.milner@magnoxsites.com | Collaborative (NDA Estate - Gold & Silver) | £100k to £500k | 2022-08-01 | 2022-08-04 | (f) | 2023-09-08 | (f) | Not yet confirmed
FRM 0154 | Waste F | Multi Site Framework | Additional Mosaiks and On-Going Maintenance | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2020-12-12 | (a) | 2021-09-08 | (f) | GNS | 10. Identification of preferred bidder
FRM 0155 | Engineering | Multi Site Framework | Machining, Fabrication & Installation | Engineering | matt.p.eeley@magnoxsites.com | OJEU/FTS Restricted | £5m to £10m | 2022-01-15 | 2022-02-05 | (f) | 2022-07-05 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0157 | Decommissioning F | Berkeley | Berkeley Boiler House Remediation - Asbestos Removal and Demolition | Hazardous materials removal | sarah.j.deeble@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2021-07-26 | 2021-09-08 | (f) | 2022-07-05 | (f) | Not yet confirmed | 05. Advert published
FRM 0158 | Waste F | Berkeley | Berkeley Boiler House Remediation - Characterisation, Transportation and Disposal of Waste | Waste management, disposal & storage | sarah.j.deeble@magnoxsites.com | Direct Award F/W | £10m to £25m | n/a | 2021-11-07 | (f) | 2022-06-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
FRM 0159 | Engineering | Collaborative Framework | Tools and Consumables (2023 - 2027) | Consumables | james.hiller@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £10m to £25m | 2022-07-05 | 2022-09-03 | (f) | 2023-05-11 | (f) | Not yet confirmed
FRM 0166 | HR, Corp & Fleet | Multi Site Framework | Business Travel 2021 + | Support Services | amy.vale@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2021-03-12 | (a) | 2021-10-08 | (f) | Tend: Click, Clarity, Travel Planet | 03. Call off from existing contract/ framework
FRM 0168 | HR, Corp & Fleet | Multi Site Framework | Legal Services [2022+] | Support Services | gissela.m.hughes@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2021-10-08 | (f) | 2022-03-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
FRM 0170 | Engineering | Multi Site Framework | Estates Management | Engineering | matt.p.eeley@magnoxsites.com | OJEU/FTS Open | £500k to £1m | 2021-09-07 | 2021-09-08 | (f) | 2022-04-06 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0171 | Decommissioning F | Dungeness | Package 1: Demolition & Boiler and ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@magnoxsites.com | OJEU/FTS Comp Procedure with Negotiation | £50m to £100m | 2022-05-06 | 2022-06-05 | (f) | 2023-10-08 | (f) | Not yet confirmed | 01. On the horizon
WAS 0028 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - concept | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2022-11-09 | 2022-12-02 | (f) | 2023-06-10 | (f) | Not yet confirmed
WAS 0036 | Waste | Hinkley | FED Procurement of Pre Conditioning Facility - Installation LOT 7 | Plant & Equipment & Materials | fiona.pearse@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2020-11-12 | (a) | 2021-06-10 | (a) | Cavendish Nuclear Limited | 12. Contract in place
WAS 0060 | Waste | Sizewell | Design & Construction of Waste Transfer Area | Construction | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2022-12-02 | (f) | 2023-04-11 | (f) | Not yet confirmed
WAS 0065 | Waste | Oldbury | Waste Transfer Area (Design & Build) DV 26603 MCI | Construction | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-10-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0118 | Waste | Hinkley | Design & Build Waste Transfer Area | Engineering | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | 2022-11-26 | 2022-12-02 | (f) | 2023-04-11 | (f) | Not yet confirmed
WAS 0237 | Waste | Hinkley | FED Hinkley - Dry Vaults Retrieval, HAI Wet Vaults Retrieval & MOSAIK Loading facility Detailed design and execution | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2021-07-10 | (a) | 2022-05-06 | (f) | Tend: Jacobs Clean Energy Cavendish Nuclear | 03. Call off from existing contract/ framework
WAS 0238 | Waste | Hinkley | Concrete Box Loading facility - detailed design and build | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £5m to £10m | n/a | 2020-11-12 | (a) | 2021-07-10 | (a) | Cavendish Nuclear Limited | 12. Contract in place
WAS 0310 | Waste | Berkeley | A frame crane | Plant & Equipment & Materials | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2020-09-17 | 2021-03-12 | (a) | 2021-08-09 | (a) | Konecranes | 11. Contract awarded
WAS 0311 | Waste | Berkeley | New charging garage | Construction | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-09-08 | (f) | 2021-11-07 | (f) | Tend: ID Corcoran Spencer | 07. ITT in preparation
WAS 0340 | Waste | Hunterston | IONSIV Vacuum drying system | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-12-02 | (f) | 2023-04-11 | (f) | Not yet confirmed
WAS 0341 | Waste | Chapelcross | Sludge & Sand retrieval | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Direct Award F/W | £5m to £10m | n/a | 2021-03-12 | (a) | 2021-06-10 | (a) | NSG Environmental Ltd | 12. Contract in place
WAS 0342 | Waste | Wylfa | MCI Phase 2 Charecterisation | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-10-08 | (f) | 2021-11-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0420 | Waste | Harwell | Extension of waste facility - Cat 1 | Construction | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-06-05 | (f) | 2022-12-02 | (f) | Not yet confirmed | 01. On the horizon
WAS 0447 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - development | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2022-07-04 | 2022-08-04 | (f) | 2023-02-10 | (f) | Not yet confirmed
WAS 0448 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - execution | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £1m to £5m | 2022-07-04 | 2022-08-04 | (f) | 2023-02-10 | (f) | Not yet confirmed
WAS 0456 | Waste | Dungeness | Waste Transfer Area - building | Construction | karen.maguire@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2021-07-10 | (a) | 2021-10-08 | (f) | Tend: Graham Construction Henry Brothers ISG Construction Mace Limited McLaughlin & Harvey Tilbury Douglas Vinci Construction | 03. Call off from existing contract/ framework
WAS 0463 | Waste | Oldbury | FED - Procurement and Manufacture of Sorting Equipment | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-10-15 | 2022-11-02 | (f) | 2023-01-01 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0464 | Waste | Oldbury | FED - Procurement of Temporary Structure for Sorting Facility | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-09-03 | 2022-10-03 | (f) | 2023-01-01 | (f) | Not yet confirmed
WAS 0465 | Waste | Oldbury | Procurement of Design and BUILD Contract for WTA and OLA specific scope | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2022-10-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0507 | Waste | Wylfa | LAW/HAW Processing Facility Scheme Design | Waste management, disposal & storage | suzanne.macmillan@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | n/a | 2021-09-08 | (f) | 2021-11-07 | (f) | Tend: BATS | 07. ITT in preparation
WAS 0514 | Waste | Dungeness | 3nr waste facility buildings | Construction | karen.maguire@magnoxsites.com | CCS F/W Call off | £5m to £10m | n/a | 2021-07-10 | (a) | 2021-11-07 | (f) | Tend: Graham Construction Henry Brothers ISG Construction Mace Limited McLaughlin & Harvey Tilbury Douglas Vinci Construction | 03. Call off from existing contract/ framework
WAS 0525 | Waste | Hinkley | 5T FLT | Plant & Equipment & Materials | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-09-08 | (f) | 2021-11-07 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0526 | Waste | Hinkley | 15 Ltr bowsers (x2) | Consumables | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-09-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0531 | Waste | Hinkley | No Secondary Sort - detailed design & execution | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | Mini Competition F/W | £5m to £10m | n/a | 2021-01-11 | (a) | 2021-06-10 | (a) | Jacobs | 12. Contract in place
WAS 0533 | Waste | Hinkley | Drum Sorting Area refurbishment (Cladding around Forklift Area) | Construction | danielle.staples@magnoxsites.com | Other - No Competition | <£100K | 2021-03-24 | 2021-05-11 | (a) | 2021-07-10 | (a) | Miraclespan | 12. Contract in place
WAS 0542 | Waste | Hinkley | DCIC Purge Equipment | Waste management, disposal & storage | kevin.l.sheppard@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-10-08 | (f) | 2021-11-07 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0543 | Waste | Hinkley | Gamme Dose Monitoring Eqpt | Waste management, disposal & storage | kevin.l.sheppard@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-10-08 | (f) | 2021-11-07 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0544 | Waste | Multiple Sites | AVDS Service and Maint | Waste management, disposal & storage | mark.scales@magnoxsites.com | OJEU/FTS Restricted | £500k to £1m | n/a | 2022-01-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0546 | Waste | Dungeness | Non Rad Waste Services four years | Waste management, disposal & storage | mark.scales@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-08-09 | (a) | 2021-10-08 | (f) | Tend: Smartcube | 08. ITT issued
WAS 0547 | Waste | Hunterston | Overpacks | Waste management, disposal & storage | mark.scales@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-03-12 | (a) | 2021-08-09 | (a) | Penny Hydraulics Ltd | 11. Contract awarded
WAS 0549 | Waste | Chapelcross | Procurement of DAF CF450 Hook Loader | Waste management, disposal & storage | kim.cook@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-02-10 | (a) | 2021-09-08 | (f) | Tend: various truck suppliers | 10. Identification of preferred bidder
WAS 0555 | Waste | Multiple Sites | Supply of Cast Iron Containers (DCIC), Ass services and Tech Const | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2021-02-10 | (a) | 2021-09-08 | (f) | GNS | 10. Identification of preferred bidder
WAS 0556 | Waste | Oldbury | Fill House & Vacuum System | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-03-12 | (a) | 2021-06-10 | (a) | NSG Environmental Ltd | 12. Contract in place
WAS 0558 | Waste | Wylfa | LAW - Haw Facility Build | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Direct Award F/W | £1m to £5m | 2022-07-16 | 2022-08-04 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0561 | Waste | Wylfa | MCI Facility | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-07-09 | 2022-08-04 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0565 | Waste | Berkeley | AVDS upgrades | Waste management, disposal & storage | danielle.staples@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-07-10 | (a) | 2021-09-08 | (f) | Tend: MechaTech Services Limited | 09. Tenders being assessed
WAS 0566 | Waste | Hinkley | Provision of basket (SIPA) | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-09-08 | (f) | 2021-11-07 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0567 | Waste | Wylfa | Cross Site Transport | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2022-08-16 | 2022-09-03 | (f) | 2022-12-02 | (f) | Not yet confirmed
WAS 0568 | Waste | Wylfa | DSC4 Decontamination | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-09-26 | 2021-11-07 | (f) | 2022-02-05 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0570 | Waste | Oldbury | AVDS Enabling Works and Services (Design and Build/Install) | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2023-02-10 | (f) | 2023-04-11 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0571 | Waste | Harwell | Provision of project team | Design services/support | danielle.staples@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-08-09 | (a) | 2021-09-08 | (f) | Tend: Atkins Cavendish Nuclear Jacobs Nuvia | 03. Call off from existing contract/ framework
WAS 0585 | Waste | Chapelcross | Lifting Beam for Concrete Boxes MILWEP CX | Waste management, disposal & storage | suzanne.macmillan@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-06-10 | (a) | 2021-07-10 | (a) | JGC | 12. Contract in place
WAS 0586 | Waste | Chapelcross | welding/NDT resource | Waste management, disposal & storage | james.burrows@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | 2020-12-26 | 2021-03-12 | (a) | 2021-06-10 | (a) | Carrs Engineering T/A Bendalls | 12. Contract in place
WAS 0589 | Waste | Hinkley | Compact Heavy Lift Truck - with boom attachement | Plant & Equipment & Materials | danielle.staples@magnoxsites.com | OJEU/FTS Open | £100k to £500k | n/a | 2021-10-08 | (f) | 2022-04-06 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0607 | Waste | Hinkley | 3m3 Boxes - Hinkley | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Other - No Competition | £500k to £1m | n/a | 2021-09-08 | (f) | 2021-11-07 | (f) | Tend: NEOS Nuclear Limited | 02. Strategy being developed
WAS 0608 | Waste | Winfrith | Hyster H30XD-12 | Waste management, disposal & storage | Kwadwo.Awuku@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-06-10 | (a) | 2021-08-09 | (a) | Briggs Eqpt UK | 11. Contract awarded
WAS 0609 | Waste | Chapelcross | Chapelcross Legacy Waste | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Mini Competition F/W | £5m to £10m | 2021-09-08 | 2021-10-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0610 | Waste | Multiple Sites | Milwep Transition to Waste Ops | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2021-09-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0624 | Waste | Multiple Sites | Mortuary Tube Structure - Furniture and grouting procurement | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | OJEU/FTS Open | £500k to £1m | n/a | 2021-09-08 | (f) | 2022-01-06 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0626 | Waste | Multiple Sites | Inovation Programme | Waste management, disposal & storage | kevin.l.sheppard@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2021-06-10 | (a) | 2021-09-08 | (f) | Tend: Gamechangers | 09. Tenders being assessed
WAS 0643 | Waste | Harwell | Transfer Drum Assembly | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-05-11 | (a) | 2021-07-10 | (a) | Graham Engineering | 12. Contract in place
WAS 0645 | Waste | Multiple Sites | General Radio Chemistry - Enviro and Effluent Lot 4 | Waste management, disposal & storage | suzanne.x.williams@magnoxsites.com | OJEU/FTS Open | £1m to £5m | 2021-10-25 | 2021-12-07 | (f) | 2022-06-05 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0646 | Waste | Wylfa | DCIC Storage Facility Design and Build | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2022-03-07 | (f) | 2022-06-05 | (f) | Not yet confirmed
WAS 0648 | Waste | Berkeley | CCTV Systems | Waste management, disposal & storage | Kwadwo.Awuku@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-08-09 | (a) | 2021-09-08 | (f) | Tend: Monatarix and Scott Total Security | 08. ITT issued
WAS 0649 | Waste | Harwell | Quarterly payment | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-04-11 | (a) | 2021-06-10 | (a) | MIRION TECHNOLOGIES (CANBERRA UK) LIMITED | 12. Contract in place