## External Plan Format
Magnox Limited Procurement Plan as at end of February 2021
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded | STATUS
DEC 0412 | Decommissioning | Wylfa | Reactor Pile Cap Tile Removal - Asbestos | Hazardous materials removal | alison.cowan@magnoxsites.com | OJEU/FTS Restricted | £5m to £10m | n/a | 2021-08-09 | (f) | 2021-10-08 | (f) | Not yet confirmed | 01. On the horizon
DEC 0414 | Decommissioning | Wylfa | Deareator Floor - Asbestos Removal | Hazardous materials removal | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2020-12-12 | (a) | 2021-04-11 | (f) | Tend: Altrad | 03. Call off from existing contract/ framework
DEC 0189 | Decommissioning | Hunterston | Hunterston A Reactors 1 and 2 Deplanting | Construction | alison.cowan@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-05-11 | (f) | 2021-09-08 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0434 | Decommissioning | Hinkley | Turbine Hall Backfill | Decommissioning, Demolition & Deplant | sarah.j.deeble@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-08-27 | 2021-09-08 | (f) | 2022-01-06 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0446 | Decommissioning | Sizewell | Turbine Hall Decommissioning - enabling disconnection services. | Construction | richard.sadd@magnoxsites.com | Direct Award F/W | £1m to £5m | 2021-09-29 | 2021-10-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0318 | Decommissioning | Oldbury | National Grid Sub Station hazard removal, deplant & demolition | Decommissioning, Demolition & Deplant | louise.x.brown@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2019-10-05 | (a) | 2021-03-12 | (f) | Celadon | 03. Call off from existing contract/ framework
DEC 0016 | Decommissioning | Harwell | LETP Land Re-instatement & SUDS system (Package 8b) | Construction | sally.j.dive@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2021-09-08 | (f) | 2022-06-05 | (f) | Not yet confirmed | 01. On the horizon
DEC 0413 | Decommissioning | Wylfa | Minor De-planting Demolition outside RCA | Decommissioning, Demolition & Deplant | alison.cowan@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-08-09 | (f) | 2021-11-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0462 | Decommissioning | Sizewell | CD Boiler Houses - Scaffold Removal | Maintenance | richard.sadd@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-12-07 | (f) | 2022-06-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0419 | Decommissioning | Dungeness | SPCE - Civil enablers including demolition of various buildings | Construction | nicola.j.smith-lee@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-07-07 | 2021-08-09 | (f) | 2021-11-07 | (f) | Not yet confirmed | 01. On the horizon
DEC 0418 | Decommissioning | Dungeness | SPCE - Turbine Hall Backfill | Construction | nicola.j.smith-lee@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-05-06 | (f) | 2022-06-05 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0411 | Decommissioning | Wylfa | Electrical Overlay System Phase 2 | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2021-05-11 | (f) | 2021-12-07 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0445 | Decommissioning | Sizewell | Reactor Building Deferral period Preps - characterisation and preps | Plant & Equipment & Materials | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | 2021-07-28 | 2021-09-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 01. On the horizon
DEC 0216 | Decommissioning | Harwell | Supply Re-generated GAC Carbon and service Mobile Filter units for Ground Water Treatment Plant | Engineering | sally.j.dive@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2020-12-12 | (a) | 2021-04-11 | (f) | Not yet confirmed | 10. Identification of preferred bidder
DEC 0450 | Decommissioning | Maentwrog | Outage inspection& repairs to Maentwrog Low Pressure tunnels - NEW Contract 2021 | Engineering | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-03-12 | (f) | 2021-04-11 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0451 | Decommissioning | Maentwrog | Call-off provision for Maentwrog Estate Management -NEW 1 year Contract 2021 | Maintenance | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2020-12-12 | (a) | 2020-12-12 | (a) | John Roberts (Ffestiniog) Ltd | 12. Contract in place
DEC 0443 | Decommissioning | Oldbury | Turbine Hall Demolition - engineering support to draft the technical specification | Engineering | sarah.j.deeble@magnoxsites.com | Other - No Competition | <£100K | n/a | 2020-03-03 | (a) | 2021-03-12 | (f) | Jacobs | 10. Identification of preferred bidder
DEC 0465 | Decommissioning | Maentwrog | Installation of a National Grid Platform for Ancillary Services (PAS) Interface System | IT hardware/software | claire.scott@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-01-03 | (a) | 2021-06-10 | (f) | Tend: TrueNorth | 10. Identification of preferred bidder
DEC 0133 | Decommissioning | Sizewell | Drain POCO & Isolate/configure for interim dormant state (mechanical & electrical) | Decommissioning, Demolition & Deplant | richard.sadd@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-03-12 | (f) | 2021-05-11 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0436 | Decommissioning | Hinkley | Demolition of a building | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2020-12-12 | (a) | 2021-02-10 | (a) | L A Moore Ltd | 11. Contract awarded
DEC 0409 | Decommissioning | Oldbury | Construction Joints/Voids | Construction | louise.x.brown@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-05-11 | (f) | 2021-10-08 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0408 | Decommissioning | Chapelcross | Decommissioning of Chapelcross Cooling Pond with the use of Nuclear Decommissioning Divers | Decommissioning, Demolition & Deplant | alison.cowan@magnoxsites.com | OJEU/FTS Open | £1m to £5m | 2021-04-28 | 2021-06-10 | (f) | 2021-11-07 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0440 | Decommissioning | Berkeley | Safetsores - Asbestos removal, demolition of Blowerhouses and removal of primary circuit plant in Blowerhouses | Hazardous materials removal | sarah.j.deeble@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2021-06-04 | 2021-07-10 | (f) | 2022-01-06 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0439 | Decommissioning | Oldbury | Turbine Hall Demolition | Decommissioning, Demolition & Deplant | sarah.j.deeble@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2022-01-01 | 2022-03-07 | (f) | 2022-08-04 | (f) | Not yet confirmed
DEC 0455 | Decommissioning | Hunterston | Reactor Roof | Construction | mark.scales@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | 2021-02-26 | 2021-03-12 | (f) | 2021-05-11 | (f) | Not yet confirmed
DEC 0469 | Decommissioning | Dungeness | Active Drains Reception Tank (ADRT) pipework supply & installation | Construction | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-03-12 | (f) | 2021-05-11 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0486 | Decommissioning | Dungeness | Design & install blockwork for sealing the flask passages for R1 and R2 | Construction | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-04-11 | (f) | 2021-07-10 | (f) | Tend: IDC, Kaefer, Altrad, OBR Construction | 07. ITT in preparation
DEC 0492 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2021-07-08 | 2021-08-09 | (f) | 2021-10-08 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0494 | Decommissioning | Dungeness | SPCE - Turbine Hall steam pipe & cable tunnels | Construction | sarah.j.deeble@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2021-03-12 | (f) | 2021-06-10 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0495 | Decommissioning | Trawsfynydd | Provision of Advice by Natural Resources Wales (NRW) on proposed Decom Programmes for Traws and Wylfa | Manpower | ruth.cox@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2020-08-14 | (a) | 2021-03-12 | (f) | Tend: NRW | 10. Identification of preferred bidder
DEC 0498 | Decommissioning | Dungeness | SPCE - Fire Alarm System re-route & new system install | Engineering | nicola.j.smith-lee@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-02-10 | (a) | 2021-03-12 | (f) | Tend: Mitie | 08. ITT issued
DEC 0507 | Decommissioning | Multi Site | Rolling Programme of Decommissioning (RPD) Enablers - DAR 2 | Engineering | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2020-10-13 | (a) | 2020-12-12 | (a) | Cavendish Nuclear Limited, Atkins, Jacobs | 12. Contract in place
DEC 0514 | Decommissioning | Multi Site | Rolling Programme of Decommissioning (RPD) Enablers - Business Case Support | Manpower | claire.scott@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-11-12 | (a) | 2020-12-12 | (a) | PwC | 12. Contract in place
DEC 0520 | Decommissioning | Maentwrog | Reservoir Inspections and Dam Movement Survey - new contract - March 22 | Engineering | claire.scott@magnoxsites.com | OJEU/FTS Open | £100k to £500k | 2021-08-27 | 2021-10-08 | (f) | 2022-04-06 | (f) | Not yet confirmed | 01. On the horizon
DEC 0522 | Decommissioning | Trawsfynydd | Bioshield Core Characterisation and Sampling within SS1 | Engineering | ruth.cox@magnoxsites.com | Other - No Competition | <£100K | 2021-10-15 | 2021-11-07 | (f) | 2021-12-07 | (f) | Not yet confirmed
DEC 0523 | Decommissioning | Trawsfynydd | Concrete and Brick Sampling and characterisation for Ponds Down Project | Engineering | ruth.cox@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2021-10-08 | (f) | 2021-12-07 | (f) | Not yet confirmed
DEC 0538 | Decommissioning | Sizewell | AB/CD Boiler Houses Asbestos Removal | Hazardous materials removal | richard.sadd@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2021-11-22 | 2021-12-07 | (f) | 2022-06-05 | (f) | Not yet confirmed
DEC 0561 | Decommissioning | Winfrith | Provision of Engineering Resources to Winfrith Site | Manpower | janet.smith@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-01-11 | (a) | 2021-03-12 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0562 | Decommissioning | Winfrith | Provision of ILW Management Support | Manpower | janet.smith@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-01-11 | (a) | 2021-02-10 | (a) | Cavendish Nuclear | 11. Contract awarded
DEC 0563 | Decommissioning | Maentwrog | Estate Management Call off Contract - NEW 4 year contract Nov 2021 | Maintenance | claire.scott@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-09-08 | (f) | 2021-12-07 | (f) | Not yet confirmed | 01. On the horizon
DEC 0568 | Decommissioning | Wylfa | WP1 Demolition of Buildings North End of Site at Wylfa (inc CO2 Plant) - Initial Engagement phase (TCO) | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-03-12 | (f) | 2021-03-12 | (f) | Tend: Celadon | 03. Call off from existing contract/ framework
DEC 0569 | Decommissioning | Harwell | POCO and Characterisation | Construction | sally.j.dive@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-03-12 | (f) | 2021-06-10 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
DEC 0570 | Decommissioning | Harwell | Supply Bulkbags to LETP Project | Consumables | sally.j.dive@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2020-12-12 | (a) | 2021-01-11 | (a) | Smartlift Bulk Packaging Ltd | 11. Contract awarded
DEC 0579 | Decommissioning | Dungeness | SPCE - DAMAL - Purchase temporary buildings and provide services connection | Support Services | nicola.j.smith-lee@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2021-05-03 | 2021-06-10 | (f) | 2021-09-08 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0587 | Decommissioning | Dungeness | SPCE - Purchase of new Explorer kit (for active drains surveys) | Construction | nicola.j.smith-lee@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2020-12-12 | (a) | 2021-03-12 | (f) | Tend: RRL/Elecsis/KTE | 09. Tenders being assessed
DEC 0600 | Decommissioning | Dungeness | Reactor Void Water Diversion | Engineering | david.m.sanderson@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2021-03-08 | 2021-03-12 | (f) | 2021-06-10 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0609 | Decommissioning | Dungeness | Health Physics Services Support to the DNA Ponds Team | Health & Safety | david.m.sanderson@magnoxsites.com | OJEU/FTS Restricted | <£100K | n/a | 2021-03-12 | (f) | 2021-03-12 | (f) | Nuvia Ltd | 02. Strategy being developed
DEC 0610 | Decommissioning | Dungeness | Health Physics Services Support to the DNA Ponds Team | Health & Safety | david.m.sanderson@magnoxsites.com | OJEU/FTS Restricted | <£100K | n/a | 2021-03-12 | (f) | 2021-03-12 | (f) | Radwise | 02. Strategy being developed
DEC 0611 | Decommissioning | Dungeness | Access & Insulation Services Support to the DNA Ponds Team | Construction | david.m.sanderson@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | n/a | 2021-03-12 | (f) | 2021-03-12 | (f) | Altrad Services | 02. Strategy being developed
DEC 0590 | Decommissioning | Dungeness | Access & Insulation Services Support to the DNA Ponds Team | Construction | david.m.sanderson@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2019-01-26 | 2019-05-08 | (a) | 2020-12-12 | (a) | Altrad Services | 12. Contract in place
DEC 0592 | Decommissioning | Hunterston | NEffTP skid mounted cartiridge filtration mechanical installation WP2 | Engineering | louise.x.brown@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-01-11 | (a) | 2021-04-11 | (f) | Not yet confirmed | 08. ITT issued
DEC 0595 | Decommissioning | Oldbury | Accommodation Civil Works | Construction | louise.x.brown@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2020-08-14 | (a) | 2021-01-11 | (a) | I D Corcoran | 12. Contract in place
DEC 0598 | Decommissioning | Hunterston | Weather Envelope | Engineering | alison.cowan@magnoxsites.com | OJEU/FTS Open | £25m to £50m | 2021-05-29 | 2021-07-10 | (f) | 2022-01-06 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0604 | Decommissioning | Multi Site | Continuous Reactor Decommissioning - Characterisation - Reactor Activation Model improvements | Manpower | claire.scott@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-03-12 | (f) | 2021-04-11 | (f) | Tend: Jacobs | 07. ITT in preparation
DEC 0607 | Decommissioning | Wylfa | WP1 Demolition of Buildings North End of Site at Wylfa (inc CO2 Plant) - Execution Phase of works | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-04-11 | (f) | 2021-06-10 | (f) | Tend: Celadon | 03. Call off from existing contract/ framework
DEC 0616 | Decommissioning | Trawsfynydd | FEDT Coring for Ponds Down project | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | Sole Source - No Choice | <£100K | 2020-12-18 | 2021-02-10 | (a) | 2021-03-12 | (f) | Tend: OBR Construction | 08. ITT issued
ASM 0690 | Asset Management | Oldbury | Oldbury Reactor Tendon De-Stressing [Design, Manufacture and Comm of Equipment required for the De-Stressing Campaigns at Oldbury Site and De-Stressing Campaign 1 21/22, Campaign 2 in 23/24 and Campaign 3 in 26/27] | Plant & Equipment & Materials | adrian.h.williams@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2019-12-04 | (a) | 2020-12-12 | (a) | Balvac Ltd A Balfour Beatty Company | 12. Contract in place
ASM 0698 | Asset Management | Chapelcross | R1, R2, R3 & R4 - Replace windows and frames with cladding | Construction | mark.cullinane@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2021-07-10 | (f) | 2021-12-07 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
ASM 0706 | Asset Management | Wylfa | Station Transformer Tap Changer Maintenance | Engineering | adrian.h.williams@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-04-11 | (f) | 2021-07-10 | (f) | Tend: Transerv Europe Ltd | 07. ITT in preparation
ASM 0715 | Asset Management | Trawsfynydd | Sewage Treatment Plant Upgrade (Finalise Outline Design and Build) | Construction | adrian.h.williams@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2020-11-12 | (a) | 2021-04-11 | (f) | Tend: JN Bentley, OBR Construction, William Hughes Engineering, Jones Bros, Vinci, Alun Griffiths, Montgomery Watson | 10. Identification of preferred bidder
ASM 0800 | Asset Management | Enablers | Asbestos Management - Assurance Contract 2021, 2022, 2023 | Design services/support | adrian.h.williams@magnoxsites.com | Sole Source - No Choice | £500k to £1m | n/a | 2021-04-11 | (f) | 2021-05-11 | (f) | Tend: HSE & Brunel University | 02. Strategy being developed
ASM 0814 | Asset Management | Oldbury | Oldbury Site - Maintenance of Fire Detection Systems | Maintenance | mark.cullinane@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-11-12 | (a) | 2020-12-12 | (a) | Siemens plc | 12. Contract in place
ASM 0826 | Asset Management | Wylfa | Reactor Pressure Vessel Vibrating Wire Strain Gauge | Maintenance | adrian.h.williams@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-11-12 | (a) | 2020-12-12 | (a) | Intercole Systems Ltd | 12. Contract in place
ASM 0882 | Asset Management | Wylfa | Wylfa: Purchase of 1 off Argos 5AB whole body monitor, Installed Purged Detector and Proximity Card Reador, plus installation | Engineering | sue.i.mattravers@magnoxsites.com | Other - No Competition | <£100K | n/a | 2020-11-12 | (a) | 2020-12-12 | (a) | Mirion Technologies (Canberra UK) Ltd | 12. Contract in place
ASM 0884 | Asset Management | Hinkley | Hinkley Redundant ADT Pipework Foam Filling | Maintenance | sukyee.hermon@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2020-09-13 | (a) | 2021-02-10 | (a) | Steve Vick International | 11. Contract awarded
ASM 0885 | Asset Management | Wylfa | Mobius Cooler as per quote Q-57778-1 | Consumables | cathryn.m.pritchard@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-11-12 | (a) | 2021-01-11 | (a) | AMETEK (GB) Limited | 12. Contract in place
ASM 0902 | Asset Management | Hinkley | Genie Z80 - Complete with 4 wheel drive and generator | Plant & Equipment & Materials | sue.i.mattravers@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2020-11-12 | (a) | 2021-02-10 | (a) | Blade Access SP Ltd | 11. Contract awarded
ASM 0903 | Asset Management | Berkeley | Supply of New Modular Buildings | Plant & Equipment & Materials | cathryn.m.pritchard@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2020-11-12 | (a) | 2021-02-10 | (a) | Portable Offices (Hire) Ltd | 11. Contract awarded
ASM 0905 | Asset Management | Dungeness | 3 off - 32ft (9.6m) Anti Vandal Fire Rated Eco Lite Open Plan Office | Plant & Equipment & Materials | cathryn.m.pritchard@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2020-11-12 | (a) | 2021-02-10 | (a) | Wernick Buildings Ltd | 11. Contract awarded
WAS 0341 | Waste | Chapelcross | Sludge & Sand retrieval | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2021-03-12 | (f) | 2021-05-11 | (f) | NSG Environmental Ltd | 03. Call off from existing contract/ framework
WAS 0036 | Waste | Hinkley | FED Procurement of Pre Conditioning Facility - Installation LOT 7 | Plant & Equipment & Materials | fiona.pearse@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2020-11-12 | (a) | 2021-04-11 | (f) | Tend: ILW Framework Suppliers. NSG, Cavendish Nuclear, Nuvia, Jacobs & ATK | 10. Identification of preferred bidder
WAS 0052 | Waste | Harwell | Original Discharge Pipeline (ODP) Decontam and Disposal | Waste management, disposal & storage | suzanne.x.williams@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2020-12-12 | (a) | 2021-05-11 | (f) | Tend: LLWR Waste Services | 03. Call off from existing contract/ framework
WAS 0065 | Waste | Oldbury | Waste Transfer Area (Design & Build) DV 26603 MCI | Construction | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2022-10-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0129 | Waste | Sizewell | Procurement and Installation of Temp Shielding | Engineering | cheryl.d.downton@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-07-10 | (f) | 2022-04-06 | (f) | Not yet confirmed | 01. On the horizon
WAS 0096 | Waste | Multiple Sites | 6m3 Box Furniture - Filter Plates | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | OJEU/FTS Open | £500k to £1m | n/a | 2020-05-02 | (a) | 2020-12-12 | (a) | Porvair Filtration Group Ltd | 12. Contract in place
WAS 0237 | Waste | Hinkley | FED Hinkley - Dry Vaults Retrieval, HAI Wet Vaults Retrieval & MOSAIK Loading facility Detailed design and execution | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2021-04-11 | (f) | 2021-12-07 | (f) | Tend: Jacobs Clean Energy Cavendish Nuclear | 03. Call off from existing contract/ framework
WAS 0238 | Waste | Hinkley | Concrete Box Loading facility - detailed design and build | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2020-11-12 | (a) | 2021-05-11 | (f) | Tend: Cavendish Nuclear C Spencer Nuvia Jacobs Clean Energy | 03. Call off from existing contract/ framework
WAS 0244 | Waste | Sizewell | Sizewell WP1 Plant & Equipment (FED) | Waste management, disposal & storage | karen.maguire@magnoxsites.com | OJEU/FTS Open | £100k to £500k | n/a | 2021-10-08 | (f) | 2022-04-06 | (f) | Not yet confirmed | 01. On the horizon
WAS 0246 | Waste | Sizewell | Sizewell WP8 - Buffer Storage | Waste management, disposal & storage | karen.maguire@magnoxsites.com | OJEU/FTS Open | £100k to £500k | n/a | 2021-10-08 | (f) | 2022-04-06 | (f) | Not yet confirmed | 01. On the horizon
WAS 0308 | Waste | Dungeness | Super Shielded Drums & MCI Baskets | Waste management, disposal & storage | richard.sadd@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2021-10-08 | (f) | 2021-12-07 | (f) | Penny Hydraulics | 02. Strategy being developed
WAS 0310 | Waste | Berkeley | A frame crane | Plant & Equipment & Materials | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2020-09-17 | 2021-03-12 | (f) | 2021-07-10 | (f) | Not yet confirmed | 06. EoIs being assessed
WAS 0311 | Waste | Berkeley | New charging garage | Construction | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-03-12 | (f) | 2021-04-11 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0376 | Waste | Hinkley | FED Hinkley - Dry Vaults Retrieval, HAI Wet Vaults Retrieval & MOSAIK Loading facility: Concept Design | Design services/support | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2019-10-05 | (a) | 2021-03-12 | (f) | Cavendish Nuclear | 03. Call off from existing contract/ framework
WAS 0409 | Waste | Hinkley | SIPA - equipment design, supply and install (HPA Vaults) | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2022-07-05 | (f) | 2023-09-08 | (f) | Not yet confirmed
WAS 0420 | Waste | Harwell | Extension of waste facility - Cat 1 | Construction | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2022-06-05 | (f) | 2022-12-02 | (f) | Not yet confirmed
WAS 0445 | Waste | Hinkley | Provision of samplers (2 nr) | Engineering | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2020-01-03 | (a) | 2021-06-10 | (f) | Not yet confirmed | 10. Identification of preferred bidder
WAS 0447 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - development | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2022-07-04 | 2022-08-04 | (f) | 2023-02-10 | (f) | Not yet confirmed
WAS 0448 | Waste | Berkeley | Gravel, Amalgam & R2 POCO phase - execution | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | OJEU/FTS Restricted | £1m to £5m | 2022-07-04 | 2022-08-04 | (f) | 2023-02-10 | (f) | Not yet confirmed
WAS 0450 | Waste | Hinkley | Fill Heads (for Resin skid) | Waste management, disposal & storage | danielle.staples@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | 2021-02-28 | 2021-04-11 | (f) | 2021-08-09 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0453 | Waste | Hinkley | Cross site trailers (concrete box) | Waste management, disposal & storage | karen.maguire@magnoxsites.com | OJEU/FTS Open | £100k to £500k | 2017-10-26 | 2020-11-12 | (a) | 2020-12-12 | (a) | Lift Safe | 12. Contract in place
WAS 0463 | Waste | Oldbury | FED - Procurement and Manufacture of Sorting Equipment | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | 2022-10-15 | 2022-11-02 | (f) | 2023-01-01 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0464 | Waste | Oldbury | FED - Procurement of Temporary Structure for Sorting Facility | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-09-03 | 2022-10-03 | (f) | 2023-01-01 | (f) | Not yet confirmed
WAS 0465 | Waste | Oldbury | Procurement of Design and BUILD Contract for WTA and OLA specific scope | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2022-10-03 | (f) | 2022-12-02 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0468 | Waste | Multiple Sites | Ground Granulated Blast Furnace Slag Bulk Powder GGBS | Waste management, disposal & storage | suzanne.x.williams@magnoxsites.com | Sole Source - No Choice | £500k to £1m | n/a | 2021-03-12 | (f) | 2021-06-10 | (f) | Tend: Civil & Marine Hanson | 07. ITT in preparation
WAS 0502 | Waste | Hinkley | FED Hinkley - Dry Vaults Retrieval, HAI Wet Vaults Retrieval & MOSAIK Loading facility: Concept Design | Design services/support | karen.maguire@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2019-10-05 | (a) | 2021-03-12 | (f) | Jacobs Clean Energy | 03. Call off from existing contract/ framework
WAS 0507 | Waste | Wylfa | LAW/HAW Processing Facility Concept Design | Waste management, disposal & storage | suzanne.macmillan@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-07-10 | (f) | 2021-10-08 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0514 | Waste | Dungeness | 3nr waste facility buildings | Construction | karen.maguire@magnoxsites.com | CCS F/W Call off | £5m to £10m | 2021-05-14 | 2021-06-10 | (f) | 2021-10-08 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0525 | Waste | Hinkley | 5T FLT | Plant & Equipment & Materials | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | 2021-04-13 | 2021-05-11 | (f) | 2021-08-09 | (f) | Not yet confirmed
WAS 0526 | Waste | Hinkley | 15 Ltr bowsers (x2) | Consumables | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | 2021-03-25 | 2021-04-11 | (f) | 2021-08-09 | (f) | Not yet confirmed
WAS 0528 | Waste | Hinkley | R1 & R2 Turntable removal | Decommissioning, Demolition & Deplant | karen.maguire@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-02-10 | (a) | 2021-03-12 | (f) | Tend: L A Moore N&R | 08. ITT issued
WAS 0531 | Waste | Hinkley | No Secondary Sort - detailed design & execution | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | Mini Competition F/W | £5m to £10m | n/a | 2021-01-11 | (a) | 2021-06-10 | (f) | Tend: Jacobs, Cavendish Nuclear, Nuvia, Spencer Group | 03. Call off from existing contract/ framework
WAS 0532 | Waste | Hinkley | Design and Manufacture of 200ltr Waste Basket and Lifting Device | Waste management, disposal & storage | cheryl.d.downton@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2020-07-01 | (a) | 2020-12-12 | (a) | Penny Hydraulics | 12. Contract in place
WAS 0533 | Waste | Hinkley | Drum Sorting Area refurbishment | Construction | danielle.staples@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | 2021-02-04 | 2021-03-12 | (f) | 2021-06-10 | (f) | Not yet confirmed | 05. Advert published
WAS 0538 | Waste | Wylfa | HWM-400 with 50mm lead shielding - 1 manually door (incl. 30mm lead) | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2020-11-12 | (a) | 2020-12-12 | (a) | Ludlum GMBH | 12. Contract in place
WAS 0544 | Waste | Multiple Sites | AVDS Service and Maint | Waste management, disposal & storage | mark.scales@magnoxsites.com | OJEU/FTS Restricted | £500k to £1m | 2021-05-27 | 2021-07-10 | (f) | 2021-12-07 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0545 | Waste | Multiple Sites | Overhead Cranes Serve and Maint | Waste management, disposal & storage | mark.scales@magnoxsites.com | OJEU/FTS Open | £500k to £1m | 2021-05-20 | 2021-07-10 | (f) | 2021-12-07 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0546 | Waste | Dungeness | Non Rad Waste Services four years | Waste management, disposal & storage | mark.scales@magnoxsites.com | OJEU/FTS Restricted | £100k to £500k | n/a | 2021-03-12 | (f) | 2021-09-08 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0547 | Waste | Hunterston | Overpacks | Waste management, disposal & storage | mark.scales@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-03-12 | (f) | 2021-03-12 | (f) | Not yet confirmed | 02. Strategy being developed
WAS 0548 | Waste | Hinkley | Hydrogen Deflagration Trials | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2021-01-11 | (a) | 2021-04-11 | (f) | Tend: NNL, DNV & HSE | 09. Tenders being assessed
WAS 0549 | Waste | Chapelcross | Procurement of DAF CF450 Hook Loader | Waste management, disposal & storage | kim.cook@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2020-10-26 | 2021-02-10 | (a) | 2021-05-11 | (f) | Not yet confirmed | 08. ITT issued
WAS 0553 | Waste | Multiple Sites | Sites sources removal and disposal, | Waste management, disposal & storage | suzanne.x.williams@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | n/a | 2020-11-12 | (a) | 2021-03-12 | (f) | Tend: LLWR, Eckert & Ziegler, ACB | 10. Identification of preferred bidder
WAS 0554 | Waste | Hinkley | Prototype of Metal Tubular Structutre | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Non-OJEU/FTS Competition | <£100K | n/a | 2021-01-11 | (a) | 2021-03-12 | (f) | Tend: NIS, Babcock Deva | 08. ITT issued
WAS 0555 | Waste | Multiple Sites | Supply of Cat Iron Containers (DCIC), Ass services and Tech Const | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | n/a | (a) | 2021-03-12 | (f) | GNS
WAS 0557 | Waste | Wylfa | DSC4 Decontamination | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Direct Award F/W | £5m to £10m | 2022-07-16 | 2022-08-04 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0558 | Waste | Wylfa | LAW Facility | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Direct Award F/W | £1m to £5m | 2021-07-16 | 2021-08-09 | (f) | 2021-10-08 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0559 | Waste | Wylfa | DCIC Storage | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Direct Award F/W | £1m to £5m | 2021-07-16 | 2021-08-09 | (f) | 2021-10-08 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0560 | Waste | Wylfa | HAW Facility | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Direct Award F/W | £1m to £5m | 2022-07-16 | 2022-08-04 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0561 | Waste | Wylfa | MCI Facility | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | Direct Award F/W | £1m to £5m | 2022-07-16 | 2022-08-04 | (f) | 2022-10-03 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
WAS 0562 | Waste | Multiple Sites | Provision of Engineering Resources | Engineering | karen.maguire@magnoxsites.com | Mini Competition F/W | £5m to £10m | n/a | 2021-03-12 | (f) | 2021-04-11 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
ENA 0385 | Enablers | Enablers | Sizewell A: Cross charge Env Mon - Emerg for the annual programme | Design services/support | sian.draper@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-11-12 | (a) | 2021-01-11 | (a) | EDF Energy Nuclear Generation Ltd | 12. Contract in place
ENA 0386 | Enablers | Enablers | Environmental Monitoring 2020/21 | Design services/support | isobel.mcbain@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-12-12 | (a) | 2021-01-11 | (a) | EDF Energy Nuclear Generation Ltd | 12. Contract in place
ENA 0388 | Enablers | Enablers | Windows 10 Rollout Services | IT hardware/software | denise.colwell@magnoxsites.com | Non-OJEU/FTS Competition | £500k to £1m | n/a | 2020-10-13 | (a) | 2021-01-11 | (a) | H3O Digital Limited | 11. Contract awarded
ENA 0390 | Enablers | Enablers | Surface laptops | IT hardware/software | isla.fray@magnoxsites.com | Non-OJEU/FTS Competition | £1m to £5m | n/a | 2020-10-13 | (a) | 2021-02-10 | (a) | Computacenter (UK) Limited | 11. Contract awarded
ENA 0391 | Enablers | Enablers | Secondment to Magnox 01/04/21 to 10/01/2022 | Support Services | sian.draper@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2020-12-12 | (a) | 2021-02-10 | (a) | Nuclear Decommissioning Authority SLA Account | 11. Contract awarded
FRM 0129 | Asset Management F | Multi Site Framework | Site Security Systems (2022-2026) | Maintenance | amanda.j.clark@magnoxsites.com | OJEU/FTS Open | £5m to £10m | 2021-12-14 | 2022-01-06 | (f) | 2022-07-05 | (f) | Not yet confirmed
FRM 0092 | Asset Management F | Collaborative Framework | Site Security Guard Services - 2019-2024 2021-2024 | Support Services | steven.j.lock@magnoxsites.com | Collaborative (NDA Estate - Gold & Silver) | £25m to £50m | n/a | 2019-07-07 | (a) | 2021-04-11 | (f) | Tend: G4S, Mitie, Profile, ISS, Servest Group (dtt) | 10. Identification of preferred bidder
FRM 0130 | Asset Management F | Multi Site Framework | High Voltage Electricity Switchgear Maintenance (2023-2027) | Maintenance | amanda.j.clark@magnoxsites.com | Sole Source - No Choice | £500k to £1m | 2022-10-29 | 2022-11-02 | (f) | 2023-01-01 | (f) | Tend: National Grid
FRM 0016 | Engineering | Multi Site Framework | Laundry & Decontamination Services 2021+ | Facilities Management | katie.bateman@magnoxsites.com | OJEU/FTS Comp Procedure with Negotiation | £10m to £25m | n/a | 2021-03-12 | (f) | 2021-07-10 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0091 | Engineering | Collaborative Framework | Statutory Examinations Post 2022+ (Phase 1) | Engineering | caroline.j.milner@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £100k to £500k | 2021-06-21 | 2021-06-10 | (f) | 2022-02-05 | (f) | Not yet confirmed | 01. On the horizon
FRM 0152 | Engineering | Collaborative Framework | Statutory Examination & IQA 2023+ (Phase 2) | Engineering | caroline.j.milner@magnoxsites.com | Collaborative (NDA Estate - Gold & Silver) | £500k to £1m | 2022-08-01 | 2022-08-04 | (f) | 2023-09-08 | (f) | Not yet confirmed
FRM 0105 | Prof Services | Multi Site Framework | Project Controls 2022+ | Manpower | michelle.a.edwards@magnoxsites.com | CCS F/W Call off | £25m to £50m | n/a | 2021-03-12 | (f) | 2021-09-08 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
FRM 0034 | Prof Services | Collaborative Framework | Health Physics Resources CP 3 | Health & Safety | andrew.mclellan@magnoxsites.com | Collaborative (NDA Estate - Gold & Silver) | £50m to £100m | 2021-11-01 | 2021-11-07 | (f) | 2022-03-07 | (f) | Tend: Intention is via DPS | 02. Strategy being developed
FRM 0036 | HR, Corp & Fleet | Collaborative Framework | Hire Cars 2020+ | Support Services | annette.turner@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | n/a | 2020-09-13 | (a) | 2020-12-12 | (a) | ENTERPRISE(C) | 12. Contract in place
FRM 0038 | HR, Corp & Fleet | Collaborative Framework | Lease Cars 2021+ | Support Services | holly.griffith@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | n/a | 2021-03-12 | (f) | 2021-05-11 | (f) | Not yet confirmed | 07. ITT in preparation
FRM 0040 | HR, Corp & Fleet | Multi Site Framework | Payroll 2 | Support Services | holly.griffith@magnoxsites.com | OJEU/FTS Restricted | £500k to £1m | 2020-08-30 | 2020-10-13 | (a) | 2021-03-12 | (f) | Not yet confirmed | 10. Identification of preferred bidder
FRM 0044 | Engineering | Multi Site Framework | PEACH (Plant Equip & Crane Hire | Plant & Equipment & Materials | matt.p.eeley@magnoxsites.com | OJEU/FTS Open | £1m to £5m | 2022-03-05 | 2022-04-06 | (f) | 2022-10-03 | (f)
FRM 0046 | Engineering | Collaborative Framework | Supply of Air Filtration and Ancillary Equipment | Consumables | james.hiller@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2020-11-12 | (a) | 2021-03-12 | (f) | Not yet confirmed | 10. Identification of preferred bidder
FRM 0048 | Engineering | Collaborative Framework | Supply of PPE & Workwear | Consumables | james.hiller@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | n/a | 2020-11-12 | (a) | 2021-05-11 | (f) | Tend: Mini Comp via CCS Agreement | 10. Identification of preferred bidder
FRM 0054 | Engineering | Multi Site Framework | High efficiency particulate air (HEPA) Filter Testing New: 2022-2027 | Engineering | castel.x.fairlie@magnoxsites.com | OJEU/FTS Open | £100k to £500k | 2021-07-03 | 2021-08-09 | (f) | 2022-01-06 | (f) | Not yet confirmed | 01. On the horizon
FRM 0058 | Engineering | Collaborative Framework | Supply of Lab Consumables and Chemicals NEW: 2021-2025 | Consumables | castel.x.fairlie@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2021-02-10 | (a) | 2021-05-11 | (f) | Not yet confirmed | 08. ITT issued
FRM 0097 | HR, Corp & Fleet | Collaborative Framework | Stationery and office supplies 2020 + | Support Services | debbie.collin@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | n/a | 2020-11-12 | (a) | 2021-03-12 | (f) | Tend: ACE, ACS, Bates, Banner, Commercial, Lyreco | 10. Identification of preferred bidder
FRM 0107 | HR, Corp & Fleet | Collaborative Framework | Learning & Development services 2022+ | Support Services | holly.griffith@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £1m to £5m | 2021-03-01 | 2021-04-11 | (f) | 2021-09-08 | (f) | Not yet confirmed
FRM 0100 | Engineering | Multi Site Framework | Dosimetry 2022+ | Engineering | caroline.j.milner@magnoxsites.com | OJEU/FTS Open | £5m to £10m | 2021-06-04 | 2021-07-10 | (f) | 2022-01-06 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0070 | Engineering | Multi Site Framework | Calibration & Maintenance of Radiological Measuring Instruments 2022+ (Installed and Portable Metrology 2022+ ) | Engineering | caroline.j.milner@magnoxsites.com | OJEU/FTS Open | £5m to £10m | n/a | 2021-08-09 | (f) | 2022-03-07 | (f) |  | 01. On the horizon
FRM 0149 | Engineering | Collaborative Framework | Engineering and EHS&Q Standards (on-line) 2022-2026 | Remediation & Environmental Services | katie.bateman@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £500k to £1m | n/a | 2022-09-03 | (f) | 2022-12-02 | (f) | Not yet confirmed
FRM 0086 | Engineering | Collaborative Framework | Certification Services 2020-2024 | Remediation & Environmental Services | katie.bateman@magnoxsites.com | Collaborative (NDA Estate – Bronze) | £100k to £500k | 2019-11-15 | 2020-06-01 | (a) | 2020-12-12 | (a) | Lloyds Register - LRQA | 12. Contract in place
FRM 0093 | Decommissioning F | Multi Site Framework | DAR: Decommissioning, Asbestos & Removal [ex Deplant & Demolition Framework] | Construction | nicola.j.smith-lee@magnoxsites.com | OJEU/FTS Restricted | £250m plus | 2021-08-20 | 2021-11-07 | (f) | 2022-09-03 | (f) | Not yet confirmed
FRM 0108 | Asset Management F | Multi Site Framework | Asbestos Analytical Services 2021 + | Hazardous materials removal | adrian.h.williams@magnoxsites.com | OJEU/FTS Restricted | £10m to £25m | 2020-09-28 | 2021-01-11 | (a) | 2021-04-11 | (f) | Tend: BV; Element; Environtech Ltd; Lucion Environmental Ltd; Santia Asbestos Management Ltd; SOCOTEC UK LTD | 08. ITT issued
FRM 0113 | HR, Corp & Fleet | Multi Site Framework | Occupational Health (Next Contract) | Support Services | annette.turner@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2021-04-11 | (f) | 2021-07-10 | (f) | Not yet confirmed | 03. Call off from existing contract/ framework
FRM 0114 | IT | Multi Site Framework | IMAGES Upgrade & Support | IT hardware/software | andrew.mclellan@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2020-05-02 | (a) | 2021-04-11 | (f) | Tend: Cavendish Nuclear Ltd,(Incumbent) | 10. Identification of preferred bidder
FRM 0125 | IT | Multi Site Framework | PMRS Project Controls Suite (Replacement) | IT hardware/software | andrew.mclellan@magnoxsites.com | OJEU/FTS Restricted | £500k to £1m | 2022-01-02 | 2022-02-05 | (f) | 2022-03-07 | (f) | Not yet confirmed
FRM 0126 | IT | Multi Site Framework | COSSH Database (Replacement) | IT hardware/software | andrew.mclellan@magnoxsites.com | Non-OJEU/FTS Competition | £100k to £500k | 2022-07-03 | 2022-08-04 | (f) | 2022-11-02 | (f) | Not yet confirmed
FRM 0150 | Waste F | Multi Site Framework | ILW Retrieval and Processing | Waste management, disposal & storage | Lisa.Pagan@magnoxsites.com | OJEU/FTS Restricted | £50m to £100m | 2021-09-02 | 2021-11-07 | (f) | 2022-09-03 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0154 | Waste F | Multi Site Framework | Additional Mosaiks and On-Going Maintenance | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2020-12-12 | (a) | 2021-03-12 | (f) | GNS | 09. Tenders being assessed
FRM 0155 | Engineering | Multi Site Framework | Machining, Fabrication & Installation | Engineering | matt.p.eeley@magnoxsites.com | OJEU/FTS Restricted | £5m to £10m | 2021-05-28 | 2021-08-09 | (f) | 2022-01-06 | (f) | Not yet confirmed | 02. Strategy being developed