## External Plan Format
Magnox Limited Procurement Plan as at end of September 2024
1
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PIN or PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded | STATUS
C15220 | Decommissioning | Oldbury | Oldbury Turbine Hall - Data Quality Objective | Design services/support | paul.phillips@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2023-12-07 | (a) | 2024-09-02 | (a) | Amentum Clean Energy Limited | 11. Contract awarded
C15622 | Decommissioning | Harwell | Decommissioning and Demolition Building at Harwell | Decommissioning, Demolition & Deplant | Shelley.Lawrence@magnoxsites.com | FTS Comp Proc with Negotiation | £100m to £250m | n/a | 2025-07-09 | (f) | 2027-08-08 | (f) | Not yet confirmed
C15906 | Decommissioning | Oldbury | OTC Demolition | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2024-06-04 | (a) | 2024-10-02 | (f) | Tend: Altrad Support Services Limited,Costain Limited,KAEFER LIMITED,NSG Environmental Ltd,KDC Contractors Limited,KELTBRAY LIMITED | 10. Identification of preferred bidder
C15918 | Decommissioning | Trawsfynydd | Trawsfynydd - Reactor Retrievals SD4 Main Retrievals & Processing Facilities | Design services/support | claire.scott@magnoxsites.com | FTS Restricted | £1m to £5m | 2023-10-11 | 2024-02-05 | (a) | 2024-09-02 | (a) | AtkinsRealis, Nuvia Limited | 11. Contract awarded
C16013 | Decommissioning | Hinkley | Hinkley R1 & R2 Pipe Bridges | Decommissioning, Demolition & Deplant | rachel.thompson@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2024-06-04 | (a) | 2024-11-01 | (f) | Tend: Altrad Support Services Limited,Costain Limited,NSG Environmental Ltd,Nuvia Limited,KDC Contractors Limited,KELTBRAY LIMITED | 10. Identification of preferred bidder
C17680 | Decommissioning | Trawsfynydd | Reactor Retrievals Enablers - Environmental Impact Assessment | Design services/support | claire.scott@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2024-05-05 | (a) | 2024-09-02 | (a) | WSP UK Limited | 11. Contract awarded
C17960 | Decommissioning | Harwell | Early Remediation (Pathfinder) - Building at Harwell | Decommissioning, Demolition & Deplant | Shelley.Lawrence@magnoxsites.com | Mini Competition F/W | £5m to £10m | n/a | 2025-04-10 | (f) | 2025-10-07 | (f) | Not yet confirmed | 02. Strategy being developed
C21068 | Decommissioning | Winfrith | Scaffolding Design Support 24/25 | Design services/support | janet.smith@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2024-05-05 | (a) | 2024-08-03 | (a) | Independent Design House Ltd | 12. Contract in place
C21074 | Decommissioning | Winfrith | ILW Engineering Management Support 24/25 | Design services/support | janet.smith@magnoxsites.com | Other - No Competition | £500k to £1m | n/a | 2024-07-04 | (a) | 2024-08-03 | (a) | Cavendish Nuclear | 12. Contract in place
C21476 | Decommissioning | Winfrith | CS&A Support | Design services/support | janet.smith@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2024-08-03 | (a) | 2024-08-03 | (a) | Abbott Risk Consulting Ltd | 12. Contract in place
C21763 | Decommissioning | Sizewell | Sizewell AETP - C&I Works | Construction | richard.sadd@magnoxsites.com | DPS Set up | £100k to £500k | n/a | 2024-09-02 | (a) | 2024-10-02 | (f) | Not yet confirmed | 08. ITT issued
C21775 | Decommissioning | Trawsfynydd | Traws Reactor Retrievals Enablers - Camera Purchase | Consumables | claire.scott@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2024-09-02 | (a) | 2024-10-02 | (f) | Not yet confirmed | 08. ITT issued
DEC 0141 | Decommissioning | Sizewell | Install Modify Vent - Splitter Vane Store (SVS) | Construction | sarah.j.deeble@magnoxsites.com | Non-FTS Competition | <£100K | 2026-02-01 | 2026-04-05 | (f) | 2026-06-04 | (f) | Not yet confirmed
DEC 0439 | Decommissioning | Oldbury | Oldbury Turbine Hall Demolition | Decommissioning, Demolition & Deplant | danielle.staples@magnoxsites.com | Mini Competition F/W | £25m to £50m | n/a | 2025-04-10 | (f) | 2026-04-05 | (f) | Not yet confirmed | 01. On the horizon
DEC 0492 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2025-08-08 | (f) | 2026-02-04 | (f) | Not yet confirmed
DEC 0529 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Divers | Engineering | Shelley.Lawrence@magnoxsites.com | FTS Open | £1m to £5m | n/a | 2026-03-06 | (f) | 2026-09-12 | (f) | Not yet confirmed
DEC 0597 | Decommissioning | Trawsfynydd | Reactor Buildings Height Reduction (EXECUTION phase) | Decommissioning, Demolition & Deplant | fiona.pearse@magnoxsites.com | FTS Comp Proc with Negotiation | £50m to £100m | 2022-12-06 | 2023-10-08 | (a) | 2025-07-09 | (f) | Not yet confirmed | 09. Tenders being assessed
DEC 0708 | Decommissioning | Dungeness | Dismantle A Frame Crane & Remove Skip Mast | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | FTS Open | <£100K | n/a | 2025-04-10 | (f) | 2025-08-08 | (f) | Not yet confirmed
DEC 0720 | Decommissioning | Trawsfynydd | Ponds Complex Demolition - Execution | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | FTS Comp Proc with Negotiation | £5m to £10m | n/a | 2025-05-10 | (f) | 2026-09-12 | (f) | Not yet confirmed
DEC 0785 | Decommissioning | Dungeness | DNA Boilers - Waste Clearance Facility - fit-out | Construction | david.m.sanderson@magnoxsites.com | Other - No Competition | <£100K | n/a | 2025-05-10 | (f) | 2025-07-09 | (f) | Not yet confirmed | 01. On the horizon
DEC 0807 | Decommissioning | Trawsfynydd | Traws Reactor Retrievals - Scheme Design 5 - Building Modifications | Design services/support | claire.scott@magnoxsites.com | DPS Call-Off | £1m to £5m | n/a | 2024-09-02 | (a) | 2025-02-09 | (f) | Tend: More than 10 | 08. ITT issued
FRM 0171 | Decommissioning | Dungeness | Package 1: Demolition & Boiler and ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@magnoxsites.com | FTS Comp Proc with Negotiation | £50m to £100m | 2023-02-07 | 2023-06-10 | (a) | 2026-07-14 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C10070 | Ops & Enablers | Enablers/Not Location Specific | Occupational Health (inc DNA Testing) 26+ | Support Services | Amy.Vale@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2025-01-10 | (f) | 2025-08-08 | (f) | Not yet confirmed | 01. On the horizon
C13038 | Ops & Enablers | Enablers/Not Location Specific | Drawing Management System - 2026 | IT hardware/software | jayne.chalmers@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2025-09-07 | (f) | 2026-03-06 | (f) | Not yet confirmed
C13774 | Ops & Enablers | Enablers/Not Location Specific | Vehicle Lease and Fleet Management Aug 2025-29 | Support Services | holly.griffith@magnoxsites.com | CCS F/W Call off | £5m to £10m | n/a | 2024-10-02 | (f) | 2025-05-10 | (f) | Not yet confirmed | 02. Strategy being developed
C16731 | Ops & Enablers | Enablers/Not Location Specific | Consolidated Testing Services - 2025 | IT hardware/software | jayne.chalmers@magnoxsites.com | G-Cloud F/W Call off | £1m to £5m | n/a | 2025-01-10 | (f) | 2025-04-10 | (f) | Not yet confirmed | 01. On the horizon
C16929 | Ops & Enablers | Enablers/Not Location Specific | HR Permanent Recruitment | Support Services | alwena.owen@magnoxsites.com | FTS Open | £1m to £5m | 2024-07-08 | 2024-09-02 | (a) | 2025-02-09 | (f) | Not yet confirmed | 08. ITT issued
C17087 | Ops & Enablers | Enablers/Not Location Specific | Supply of new Metrology Instruments (Installed and Portable) | Engineering | caroline.j.milner@magnoxsites.com | DPS Set up | £5m to £10m | n/a | 2024-10-02 | (f) | 2025-03-11 | (f) | Not yet confirmed | 07. ITT in preparation
C17366 | Ops & Enablers | Enablers/Not Location Specific | Office Supplies 2025 onwards | Support Services | Amy.Vale@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2024-06-04 | (a) | 2025-04-10 | (f) | Tend: Lyreco UK Limited,WildHearts Office Ltd,Banner Group Limited,Bates Office Services,ACS Group,OT GROUP LIMITED | 10. Identification of preferred bidder
C17387 | Ops & Enablers | Bradwell; Dungeness; Sizewell | Civils Support DPS - South East Region | Construction | adrian.h.williams@magnoxsites.com | DPS Set up | £5m to £10m | n/a | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') now open for supplier registration and pre-qualification
C17506 | Ops & Enablers | Chapelcross | Chapelcross New Potable Water Main - Supply & install | Utilities | andrew.dobson@magnoxsites.com | Non-FTS Competition | £500k to £1m | n/a | 2024-02-05 | (a) | 2024-07-04 | (a) | Story Contracting Ltd | 12. Contract in place
C17872 | Ops & Enablers | Hinkley | Hinkley - Cladding and Louvres Replacement | Construction | adrian.h.williams@magnoxsites.com | Non-FTS Competition | £1m to £5m | n/a | 2024-06-04 | (a) | 2024-08-03 | (a) | Central Roofing and Building Services Ltd | 12. Contract in place
C18640 | Ops & Enablers | Enablers/Not Location Specific | Thermo Support 2024 | IT hardware/software | debbie.collin@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2024-07-04 | (a) | 2024-07-04 | (a) | Thermo FIsher Scientific Messtechnik GmbH | 12. Contract in place
C18837 | Ops & Enablers | Enablers/Not Location Specific | BATS 069 200224 ES AW | Design services/support | anna.h.walker@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2024-06-04 | (a) | 2024-08-03 | (a) | AtkinsRealis | 12. Contract in place
C19724 | Ops & Enablers | Enablers/Not Location Specific | Asbestos Analytical Services 2025 | Design services/support | matt.p.eeley@magnoxsites.com | DPS Call-Off | £25m to £50m | n/a | 2024-10-02 | (f) | 2025-05-10 | (f) | Not yet confirmed | 02. Strategy being developed
C19775 | Ops & Enablers | Winfrith | Winfrith Site - Main Gate Reconfiguration - Design | Maintenance | sukyee.hermon@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2024-06-04 | (a) | 2024-10-02 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C19793 | Ops & Enablers | Chapelcross; Hunterston | Civils Support DPS (Scottish Region) - Pre-Qualification | Construction | adrian.h.williams@magnoxsites.com | DPS Set up | £5m to £10m | n/a | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') being prepared for supplier registration and pre-qualification
C20096 | Ops & Enablers | Enablers/Not Location Specific | ERP Payroll 2024 | IT hardware/software | jayne.chalmers@magnoxsites.com | G-Cloud F/W Call off | £1m to £5m | n/a | 2024-05-05 | (a) | 2024-07-04 | (a) | Phase 3 Consulting Limited | 12. Contract in place
C20156 | Ops & Enablers | Hunterston | Hunterston Welfare Improvements | Construction | adrian.h.williams@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-06-04 | (a) | 2024-10-02 | (f) | Tend: McLaughlin Construciton,Thomas Johnstone Ltd.,J&S Builders and Joiners | 10. Identification of preferred bidder
C20172 | Ops & Enablers | Enablers/Not Location Specific | Car Share RM6265 Lot 5 EOI | Support Services | holly.griffith@magnoxsites.com | Market Engagement | £500k to £1m | 2024-11-01 | n/a | (f) | n/a | (f) | Not Applicable | Market Engagement
C20430 | Ops & Enablers | Hinkley | Hinkley - Roof Refurbishments | Construction | adrian.h.williams@magnoxsites.com | Non-FTS Competition | £500k to £1m | n/a | 2024-06-04 | (a) | 2024-08-03 | (a) | Central Roofing and Building Services Ltd | 12. Contract in place
C20508 | Ops & Enablers | Berkeley; Hinkley; Oldbury | Civils Support DPS (South West Region) - Pre-Qualification | Construction | adrian.h.williams@magnoxsites.com | DPS Set up | £5m to £10m | n/a | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') being prepared for supplier registration and pre-qualification
C20825 | Ops & Enablers | Enablers/Not Location Specific | BATS 071 190624 AO CH (Project Rutherford) | Design services/support | alwena.owen@magnoxsites.com | DPS Call-Off | <£100K | n/a | 2024-07-04 | (a) | 2024-11-01 | (f) | Tend: More than 10 | 10. Identification of preferred bidder
C20831 | Ops & Enablers | Maentwrog; Trawsfynydd; Wylfa | Civils Support DPS (Welsh Region) - Pre-Qualification | Construction | adrian.h.williams@magnoxsites.com | DPS Set up | £5m to £10m | n/a | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') being prepared for supplier registration and pre-qualification
C21710 | Ops & Enablers | Enablers/Not Location Specific | Access & Insulation Services 2025-2029 | Construction | alex.macdonald@magnoxsites.com | FTS Restricted | £50m to £100m | 2024-10-14 | 2024-11-01 | (f) | 2025-10-07 | (f) | Not yet confirmed
C21711 | Ops & Enablers | Enablers/Not Location Specific | Passport 2026 | IT hardware/software | isla.fray@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2025-08-08 | (f) | 2025-12-06 | (f) | Not yet confirmed
C21822 | Ops & Enablers | Harwell; Winfrith | Civils Support DPS - South Region - Pre-Qualification | Construction | adrian.h.williams@magnoxsites.com | DPS Set up | £5m to £10m | n/a | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') being prepared for supplier registration and pre-qualification
C22056 | Ops & Enablers | Dungeness | Dungeness Contractors Accomodation and Construction Office Upgrade | Construction | adrian.h.williams@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2024-09-02 | (a) | 2024-11-01 | (f) | Tend: More than 10 | 08. ITT issued
C22073 | Ops & Enablers | Enablers/Not Location Specific | IT Javelin Bridging contract Direct Award (2025-2028) | IT hardware/software | james.hiller@magnoxsites.com | Direct Award F/W | £25m to £50m | n/a | 2024-10-02 | (f) | 2025-01-10 | (f) | Not yet confirmed | 02. Strategy being developed
C16954 | Waste | Chapelcross | Lease of 7.5T Drop side for Chapelcross | Support Services | julie.a.jones@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-11-07 | (a) | 2024-07-04 | (a) | Riverside Truck Rental LTD (Trading as NRG Riverside) | 12. Contract in place
C17610 | Waste | Hinkley | Hinkley - Design, supply and installation of 415V Switchboard | Consumables | karen.maguire@magnoxsites.com | Non-FTS Competition | £500k to £1m | n/a | 2024-12-01 | (f) | 2025-05-10 | (f) | Not yet confirmed | 02. Strategy being developed
C18847 | Waste | Hunterston | Provision of 3m3 Drums for Hunterston | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2024-04-05 | (a) | 2024-08-03 | (a) | Stainless Metalcraft (Chatteris) Ltd. | 12. Contract in place
C20416 | Waste | Enablers/Not Location Specific | Characterisation Services | Design services/support | Liz.Gilbert@magnoxsites.com | New Framework set up | £10m to £25m | n/a | 2024-11-01 | (f) | 2025-07-09 | (f) | Not yet confirmed | 02. Strategy being developed
C20805 | Waste | Winfrith | Winfrith Segmented Gamma Scanner – Update of Nucleonics and PC | IT hardware/software | julie.a.jones@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2024-07-04 | (a) | 2024-07-04 | (a) | Mirion Technologies (Canberra UK) Ltd | 12. Contract in place
C21538 | Waste | Oldbury | Oldbury - Detailed Design & Construction of AVDS Building | Construction | danielle.staples@magnoxsites.com | Non-FTS Competition | £1m to £5m | n/a | 2024-10-02 | (f) | 2025-04-10 | (f) | Not yet confirmed | 07. ITT in preparation
C21868 | Waste | Enablers/Not Location Specific | PIN - Supply of Powders & Aggregates in Bulk Bags & IBCs | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Market Engagement | £1m to £5m | 2024-09-13 | n/a | (f) | n/a | (f) | Not Applicable | Market Engagement
WAS 0028 | Waste | Berkeley | Gravel, Amalgam & R2 POCO - Equipment | Waste management, disposal & storage | karen.maguire@magnoxsites.com | FTS Restricted | £100k to £500k | n/a | 2025-03-11 | (f) | 2025-08-08 | (f) | Not yet confirmed | 01. On the horizon
WAS 0126 | Waste | Hinkley | Package 03 - SPF9f Waste Characterisation | Waste management, disposal & storage | danielle.staples@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2025-12-06 | (f) | 2026-04-05 | (f) | Not yet confirmed