## Procurement_Plan
		Nuclear Restoration Services Limited (Dounreay) - Procurement pipeline April 2024
For further information contact Dounreay at commercial.services@dounreay.com
☆ Record Ref	Business Unit	Sourcing to Contract: Record Name	☆ Published Description	Procurement Route (If Known)	Contract Type	Commercial Strategy	Desired Contract Start Date	Desired Contract End Date	Value Range	Contract Owner	Ops Project Manager	Previous Contract Ref
C9905	Operations - Waste	Mechanical Design Services	Mechanical Design Services	To be added	Services		01/06/2024	31/03/2028	≥ £1m to <£5m	Sonja Sinclair	Michael Gray
C9903	Operations - Waste	Electrical Control and Instrumentation Services	Electrical Control and Instrumentation Services	To be added	Services		01/06/2024	31/03/2028	≥ £500k to <£1m	Sonja Sinclair	Michael Gray
C18173	Strategic Programme	Shaft & Silo - Prototype model for the dismantling of Existing Shaft Headworks	A mock up is required to ensure that the best practical means is applied in dismantling the shaft slab to minimise any additional materials falling into the existing shaft. The mock up must replicate the working environment and to scale.	Below Threshold - Competitive Tender	Works		05/06/2024	06/09/2024	≥ £100k to <£500k	John Johnstone	Gordon Sutherland
C18747	Operations - Maintenance & Engineering Support	Provision of C&I / Software Engineer	Provision of C&I / Software Engineer for 6 months	Framework - Further Competition	Services	Not known	01/06/2024	30/11/2024	≥ £100k to <£500k	Hannah Budge	Matthew Hitchin
C17690	Strategic Programme	Ongoing Support to SPOT Robot	Ongoing Support Contract for SPOT Robot System	Direct Award - Below Threshold	Services		30/04/2024	31/03/2025	< £100k	Robert McDonald	Heather Fairweather
C15173	Operations - Waste	Reserved Procurement - Air Handling Unit Design	Reserved Procurement - Air Handling Unit Design	Below Threshold - Competitive Tender	Services		20/05/2024	30/08/2024	< £100k	Donna Stewart	Michael Bailey
C1177	Operations - FCA Decommissioning	Design for Active Filter Change Replacement Robot Implementation	Design for Active Filter Change Replacement Robot Implementation	Framework - Further Competition	Services		01/10/2024	02/11/2025	< £100k	Alex Wood	Graham Carle
C1151	Strategic Programme	Low Level Waste Pits - Review and development of the Environmental Safety Case	Low Level Waste Pits - Review and development of the Environmental Safety Case	Framework - Further Competition	Services	Not known	01/04/2025	31/03/2026	< £100k	Kelsey Bain	Adreain Gill
C1149	Strategic Programme	Site Closure and Environmental Restoration - Peer Review	Site Closure and Environmental Restoration - Peer Review	Framework - Further Competition	Services	Not known	01/04/2025	31/12/2025	< £100k	Kelsey Bain	Adreain Gill
C1073	Operations - Fuel	Thorium Nitrate Drums Final Letter of Compliance	Thorium Nitrate Drums Final Letter of Compliance	Framework - Further Competition	Services		01/08/2025	01/05/2026	< £100k	Dawn Sewell	Robert McKiddie
C18746	Operations - Maintenance & Engineering Support	Provision of C&I Draughtsperson	Provision of C&I Draughtsperson for 6 months	Framework - Further Competition	Services	Not known	01/06/2024	30/11/2024	≥ £100k to <£500k	Hannah Budge	Matthew Hitchin
C15129	Assurance	Supply of Electronic Personal Dosimeters	Supply of Electronic Personal Dosimeters	Direct Award - PCR Single Source (Reg 32)	Supplies	Not known	24/04/2024	31/03/2026	≥ £500k to <£1m	Emma Gordon	Anthony Ridgley
C12769	Operations - Fuel	Irradiated Fuel Replacement Grabs Design	Irradiated Fuel Replacement Grabs Design	Framework - Further Competition	Services		27/09/2024	28/03/2025	< £100k	Jade Plowman	Vicki Edmunds
C12888	Operations - Waste	Manufacturing and Delivery of the D1215 Red Extract System Fans	Manufacturing and Delivery of the D1215 Red Extract System Fans	Below Threshold - Competitive Tender	Supplies		03/06/2024	09/09/2024	≥ £100k to <£500k	Hannah Budge	Michael Bailey
C1222	Operations - Maintenance & Engineering Support	Prototype Fast Reactor Transformers	Prototype Fast Reactor Transformers	Below Threshold - Competitive Tender	Supplies	Not known	02/09/2024	31/12/2024	≥ £100k to <£500k	Fraser Bruce	Laurence Campbell
C14956	Operations - Waste	Reserved Procurement - Provision of Ad-hoc Haulage Services	Provision of ad-hoc haulage services	Below Threshold - Competitive Tender	Services		01/05/2024	31/03/2025	< £100k	Sarah McCaughey	Stephen Mackie
C1143	Operations - FCA Decommissioning	Raffinate Room Concept Design and Safety and Environmental Overview Report	Raffinate Room Concept Design and Safety and Environmental Overview Report	Framework - Further Competition	Services		30/04/2024	06/05/2025	< £100k	Dawn Sewell	Andrew Hamilton
C16984	Assurance	Replacement of Wound Monitor and Supporting Equipment	This procurement is to supply a replacement Wound Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Below Threshold - Competitive Tender	Supplies	Not known	03/06/2024	31/12/2024	< £100k	Fraser Bruce	Avril Fell	N/A
C15305	Operations - Waste	Low Level Waste Pits - Resurfacing	Low Level Waste Pits - Resurfacing	Below Threshold - Competitive Tender	Works		05/07/2024	31/10/2024	≥ £100k to <£500k	Janet Rosie	Suzanne Griffiths
C1142	Operations - Waste	Manufacture and Design Ammonium Dirurante Floc Transport Stillage Lifting Beam	Manufacture and Design of Ammonium Dirurante Floc Transport Stillage Lifting Beam	Below Threshold - Competitive Tender	Services		18/07/2025	07/01/2026	≥ £100k to <£500k	Sonja Sinclair	Michael Gray
C1249	Operations - Waste	D1310 Auto-Analyser Spectrophotometers - Gallery - 2 off	D1310 Auto-Analyser Spectrophotometers - Gallery - 2 off	Direct Award - Below Threshold	Supplies		23/10/2024	31/03/2025	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C9875	Operations - Waste	Area 600 - Internal Cement Powders Line and Caustic Line installation	Area 600 - Internal Cement Powders Line installation, internal and external Caustic Line installation and Phase 1 internal ventilation installalation	Direct Award - Below Threshold	Works		01/07/2024	12/09/2024	≥ £100k to <£500k	Sonja Sinclair	Michael Gray
C17121	Operations - Waste	Dampers Manufacturing and Delivery	Dampers Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		31/08/2024	31/01/2025	< £100k	Lesley-Ann Crombie	Michael Bailey
C17833	Security and Resilience	Power Fence Repair	Power Fence Repair	Below Threshold - Competitive Tender	Works		17/06/2024	13/09/2024	≥ £100k to <£500k	Lauren J Mackay	Richard Berry
C1150	Strategic Programme	Development of Individual Component Environmental Safety Cases	Development of Individual Component Environmental Safety Cases	Framework - Further Competition	Services	Not known	01/04/2025	31/12/2025	< £100k	Kelsey Bain	Adreain Gill
C18808	Operations - Waste	Supply of Gamma Detector for D2176	Supply of Gamma Detector for D2176	Direct Award - Below Threshold	Supplies		31/05/2024	02/09/2024	< £100k	Hannah Budge	Jeremy Andrew
C18787	Operations - Waste	Gamma Spectroscopy Detector	Gamma Spectroscopy Detector	Direct Award - Below Threshold	Supplies		31/05/2024	02/09/2024	≥ £100k to <£500k	Hannah Budge	Jeremy Andrew
C9096	Operations - Waste	Waste Framework Agreement – Provision of Waste Skips to Support Waste Generation	Waste Framework Agreement – Provision of Waste Skips to Support Waste Generation	Framework Agreement – Set up of a new Framework	Services		06/05/2024	05/05/2028	≥ £500k to <£1m	Janet Rosie	Douglas McGeachin
C14046	Operations - Waste	D1208 Peer Review	D1208 Peer Review	Framework - Further Competition	Services		01/06/2024	25/05/2026	< £100k	Hannah Budge	Andrew Cormack
C12555	Security and Resilience	Purchase of Ambulance	Purchase of Ambulance	Below Threshold - Competitive Tender	Supplies		01/04/2026	31/03/2027	≥ £100k to <£500k	Debbie Weir	Rob Bly
C1254	Operations - Waste	D2176 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	D2176 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	Direct Award - Below Threshold	Supplies		11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C1211	Operations - Waste	D1310 - Gas Chromatography - Mass Spectrometer	D1310 - Gas Chromatography - Mass Spectrometer	Below Threshold - Competitive Tender	Supplies		11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C13986	Operations - Waste	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Below Threshold - Competitive Tender	Services		03/06/2024	29/11/2024	≥ £100k to <£500k	Donna Stewart	Morris Macleod
C1172	Strategic Programme	Repair of Steelwork	Repair of Steelwork	Below Threshold - Competitive Tender	Works		30/11/2024	30/11/2025	≥ £100k to <£500k	Heidi Warner	Jason Park
C12887	Operations - Waste	D1215 Glove box Manufacturing and Delivery	D1215 Glove box Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		20/05/2024	29/11/2024	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C16547	Operations - Waste	Low Level Waste Pits - Provision of Cover Building	Low Level Waste Pits - Provision of Cover Building	Below Threshold - Competitive Tender	Supplies		07/06/2024	31/10/2024	< £100k	Janet Rosie	Suzanne Griffiths
C1093	Operations - Waste	Supply of Fume Cupboards for D1310 Labs	15 Fume Cupboards - D1310 and D1215 Upgrade Projects	Below Threshold - Competitive Tender	Supplies	Not known	29/04/2024	28/10/2024	≥ £100k to <£500k	Hannah Budge	Michael Bailey
C18814	Operations - Waste	Supply of Easycount System for D2176	Supply of Easycount System for D2176	Direct Award - Below Threshold	Supplies		01/06/2024	01/10/2024	≥ £100k to <£500k	Hannah Budge	Jeremy Andrew
C12385	Operations - Waste	Dounreay Cementation Plant Peer Review	Dounreay Cementation Plant Peer Review	Framework - Further Competition	Services		05/07/2024	28/10/2025	< £100k	Lesley-Ann Crombie	Frank Simmons
C6605	Operations - Maintenance & Engineering Support	Prototype Fast Reactor Steam Generator Building West Wall Facade Replacement	Construction of the Prototype Fast Reactor Steam Generator Building West Wall Face Replacement.	Below Threshold - Competitive Tender	Works	Not known	27/05/2024	30/08/2024	≥ £1m to <£5m	Jade Plowman	James Robertson
C1121	Operations - Reactor	Reserved Procurement - Prototype Fast Reactor Effluent Treatment Plant Upgrades	Prototype Fast Reactor Effluent Treatment Plant Pipework Replacement and Performance Upgrades	Below Threshold - Competitive Tender	Works		31/05/2024	28/03/2025	≥ £1m to <£5m	Jade Plowman	James Campbell
C1200	Operations - Reactor	Prototype Fast Reactor Manufacture Prototype Containment and Cutting Tool	Prototype Fast Reactor Manufacture Prototype Containment and Cutting Tool for Argon Gas Blanket	Below Threshold - Competitive Tender	Services		17/08/2024	31/10/2024	≥ £100k to <£500k	Robert McDonald	James Robertson
C17834	Organisational Excellence	Provision of Opticians Services	Provision of Opticians Services	Below Threshold - Competitive Tender	Services		01/05/2025	30/04/2030	< £100k	Lauren J Mackay	Kirsty McIntosh
C9887	Operations - Waste	Area 400 Internal Ventilation	To be coordinated with the installation of Area 300 and Area 400 Fan and Filter Rooms	Direct Award - Below Threshold	Works		02/10/2025	10/12/2025	< £100k	Sonja Sinclair	Michael Gray
C1128	Operations - FCA Decommissioning	D1217 - Cell Floor Block Lifting Bags	D1217 - Cell Floor Block Lifting Bags	Below Threshold - Competitive Tender	Supplies		01/07/2024	31/12/2024	< £100k	Alex Wood	Leslie D M Mackay
C9673	Operations - Waste	Telehandler	Telehandler	Below Threshold - Competitive Tender	Supplies		01/10/2024	31/01/2025	< £100k	Donna Stewart	Stephen Mackie
C17940	Operations - Waste	D1208 In-cell Inspections	D1208 In-cell Inspections	Framework - Further Competition	Services	Re-procurement (same scope)	01/09/2024	01/09/2025	< £100k	Hannah Budge	Chris Sinclair	3300021440
C1136	Operations - Reactor	Prototype Fast Reactor Delivery and Design of the Cold Trap Loop	Prototype Fast Reactor Delivery and Design Phase for the Prototype Fast Reactor Secondary Cold Trap Loop 1 and 2	Framework - Further Competition	Services		02/10/2025	12/12/2025	< £100k	Robert McDonald	James Campbell
C12890	Operations - Waste	D1215 Ductwork Manufacturing and Delivery	D1215 Ductwork Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		09/09/2024	31/01/2025	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C17227	Finance	Internet Resilience Project	Wide Area Network connectivity/ Internet Feeding requirement	Framework - Direct Award	Services		07/05/2024	20/01/2025	≥ £100k to <£500k	Ilona Unger-Russell	Rob Bohee
C9919	Operations - Waste	Stillage Transfer System - Changing Room	Stillage Transfer System - Changing Room	Below Threshold - Competitive Tender	Works		06/01/2026	06/04/2026	< £100k	Sonja Sinclair	Michael Gray
C12889	Operations - Waste	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Open Procedure	Services		03/06/2024	31/01/2025	≥ £100k to <£500k	Janet Rosie	Michael Bailey
C1173	Strategic Programme	Design of Steelwork Repair	Design of Steelwork Repair	Framework - Further Competition	Services		30/11/2024	14/03/2025	≥ £100k to <£500k	Heidi Warner	Jason Park
C18815	Operations - Waste	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Direct Award - PCR Single Source (Reg 32)	Supplies		01/04/2026	01/08/2026	≥ £100k to <£500k	Hannah Budge	Jeremy Andrew
C18809	Operations - Waste	Supply of Cryocooler for D1310	Supply of Cryocooler for D1310	Direct Award - Below Threshold	Supplies		31/05/2024	02/09/2024	< £100k	Hannah Budge	Jeremy Andrew
C1248	Operations - Waste	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Direct Award - PCR Single Source (Reg 32)	Supplies		11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C1122	Operations - Waste	D3000 Switchboard	D3000 Switchboard	Open Procedure	Supplies		06/05/2024	31/01/2025	≥ £100k to <£500k	Donna Stewart	Morris Macleod
C12893	Operations - Waste	Fit-out and Commissioning of Glovebox and Extract Systems	Electrical, Control and Instrumentation Fit-out and Commissioning of Glovebox and Extract Systems	Open Procedure	Services		05/06/2024	06/06/2025	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C1114	Operations - Waste	Low Level Waste Metals Diversion Projects	Low Level Waste Metals Diversion Projects	Framework - Further Competition	Services		02/09/2024	31/03/2025	≥ £100k to <£500k	Carly Erridge	Douglas McGeachin
C1168	Strategic Programme	Waste Optimisation - Waste Optimisation Improvements	Waste Optimisation - Waste Optimisation Improvements	Framework - Further Competition	Services		01/07/2024	31/05/2025	< £100k	Janet Rosie	Alan Mowat
C1129	Operations - FCA Decommissioning	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility for Testing	Below Threshold - Competitive Tender	Works		19/09/2024	30/03/2025	≥ £100k to <£500k	Alex Wood	Leslie D M Mackay
C12897	Operations - Waste	Mechanical Fit-out and Commissioning of Glovebox and extract systems	Mechanical Fit-out and Commissioning of Glovebox and extract systems	Open Procedure	Services		03/07/2024	04/07/2025	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C18653	Operations - FCA Decommissioning	D1206 Breathing Air Containerised System	D1206 Breathing Air Containerised System	Open Procedure	Services		07/05/2024	07/01/2025	≥ £100k to <£500k	Erica Innes	Iona Fraser	NA
C14411	Operations - FCA Decommissioning	D1206 Breathing Air Containerised System	D1206 Breathing Air Containerised System	Open Procedure	Services		07/05/2024	07/01/2025	≥ £100k to <£500k	Erica Innes	Iona Fraser	NA
C1246	Operations - Maintenance & Engineering Support	The supply of Cameras, Camera Encoders & Server Upgrade & supporting maintenance	- The supply and delivery of Cameras, Camera Encoders and Server Upgrade. / - Maintenance of Titan Vision Control Equipment.	Direct Award - PCR Single Source (Reg 32)	Supplies	Not known	01/07/2024	30/06/2028	≥ £1m to <£5m	Kelsey Bain	Douglas Mackenzie	N/A
C19393	Operations - Reactor	Rental and Ad-Hoc Support to the Breeder Fuel Trials Rig	Rental and Ad-Hoc Support to the Breeder Fuel Trials Rig	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	01/07/2024	29/12/2028	≥ £500k to <£1m	Robert McDonald	Magnus O'Brien	3300019316
C16884	Operations - Reactor	Refit of IPM9 Monitor	Supply, Installation, Commissioning and Site Acceptance Testing of an IPM Rebuild Kit	Direct Award - Below Threshold	Works		02/09/2024	30/09/2024	< £100k	Jade Plowman	Chris Wratten
C17177	Operations - Maintenance & Engineering Support	Legionella Risk Assessment	Legionella Risk Assessment	Direct Award - Below Threshold	Works	Not known	01/07/2024	30/11/2024	< £100k	Kelsey Bain	Matthew Hitchin
C12623	Security and Resilience	Firefighter and Officer Related Training	Firefighter and Officer Related Training	Open Procedure	Services		01/07/2024	30/06/2029	≥ £500k to <£1m	Lauren J Mackay	Rob Bly
C12892	Operations - Waste	Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Below Threshold - Competitive Tender	Services		09/09/2024	28/03/2025	< £100k	Donna Stewart	Michael Bailey
C1155	Operations - Waste	Supply of Heavy Weight Towing Vehicle	Supply of Heavy Weight Towing Vehicle	Open Procedure	Supplies	Re-procurement (same scope)	01/05/2025	01/04/2026	≥ £100k to <£500k	Carly Erridge	Stephen Mackie	3300028934
C18806	Operations - Waste	Gallery photometric analyser	Gallery photometric analyser	Direct Award - Below Threshold	Supplies		31/05/2024	02/09/2024	< £100k	Hannah Budge	Jeremy Andrew
C16095	Strategic Programme	Advanced Transition Works - Trials for Removal of Shaft Slab Cover	Shaft & Silo - Dismantle Existing Shaft Headworks. Dismantling the existing supplementary concrete Cover Slab below and then the original concrete Capping Slab. The capping slab is recorded as being constructed in two lifts.	Below Threshold - Competitive Tender	Works		05/07/2024	25/06/2025	≥ £500k to <£1m	John Johnstone	Willie Ross
C15664	Operations - Maintenance & Engineering Support	Replacement of Cooling Fins on Prototype Fast Reactor Transformers	Replacement of Cooling Fins on Prototype Fast Reactor Transformers	Direct Award - PCR Single Source (Reg 32)	Works	Not known	15/05/2024	15/11/2024	≥ £100k to <£500k	Fraser Bruce	Graham Parker
C9897	Operations - Waste	Stillage Transfer System - Control System Modifications	Control system Modifications design and implementation	Below Threshold - Competitive Tender	Works		15/01/2026	18/03/2026	< £100k	Sonja Sinclair	Michael Gray
C1109	Operations - Fuel	Reserved Procurement - D1203 Ventilation System	The Manufacture and Installation and Site Acceptance of the D1203 Ventilation System	Below Threshold - Competitive Tender	Works		31/07/2024	30/06/2025	≥ £1m to <£5m	Alex Wood	Hugh J Tunn
C13963	Security and Resilience	Razor Wire Fence Maintenance	Razor Wire Fence Maintenance	Below Threshold - Competitive Tender	Works		10/06/2024	09/08/2024	≥ £100k to <£500k	Debbie Weir	Richard Berry
C13987	Operations - Waste	D3000 Generator	D3000 Generator	Below Threshold - Competitive Tender	Supplies		06/05/2024	01/11/2024	< £100k	Donna Stewart	Morris Macleod
C19167	Operations - Waste	D1208 Fire Escape Scaffold	Temporary scaffolding for the fire escape from D1208 East Elevation	Framework - Further Competition	Services		06/05/2024	01/11/2024	< £100k	Heidi Warner	Michael Gray
C9890	Operations - Waste	Stillage Transfer System- Gantry Crane & Frame	Works on the Stillage Transfer System- the Gantry Crane and Frame only	Below Threshold - Competitive Tender	Works		05/09/2025	16/03/2026	≥ £100k to <£500k	Sonja Sinclair	Michael Gray
C9877	Operations - Waste	Area 300 Main Immobilisation Line installation	Area 300 Main Immobilisation Line installation	Below Threshold - Competitive Tender	Works		18/11/2024	09/06/2026	≥ £100k to <£500k	Sonja Sinclair	Michael Gray
C16843	Operations - Waste	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Framework - Further Competition	Services		06/05/2024	28/06/2024	< £100k	Donna Stewart	Morris Macleod
C16823	Operations - FCA Decommissioning	Procurement of a Non-Destructive Assay System	Procurement of a Non-Destructive Assay System	Open Procedure	Supplies	Not known	01/05/2024	30/06/2025	≥ £100k to <£500k	Robert McDonald	Derek Manson	N/A
C1247	Operations - Waste	Alpha Spectrometry Analyst Controller Units	Alpha Spectrometry Analyst Controller Units (1 and 6 Dual Packs Alpha Spectrometer)	Direct Award - Below Threshold	Supplies		11/05/2024	17/11/2024	< £100k	Donna Stewart	Jeremy Andrew
C1157	Operations - Maintenance & Engineering Support	Maintenance of Air Compressors	Maintenance of Air Compressors	Open Procedure	Services	Re-procurement (same scope)	01/05/2024	30/04/2027	≥ £100k to <£500k	Fraser Bruce	Laurence Campbell	3300024069
C13988	Operations - Waste	Gravity Receipt Tank Ladder Replacement	Gravity Receipt Tank Ladder Replacement	Below Threshold - Competitive Tender	Works		08/07/2025	08/01/2026	< £100k	Donna Stewart	Morris Macleod
C1102	Operations - Fuel	Irradiated Fuels Multi-functional Rig and Fixtures Scheme	Irradiated Fuels Multi-functional Rig and Fixtures Scheme and Detailed Design	Framework - Further Competition	Services		30/09/2024	30/10/2025	≥ £500k to <£1m	Robert McDonald	Vicki Edmunds
C8637	Operations - Waste	Dounreay Cementation Plant Engineering Substantiation	Dounreay Cementation Plant Engineering Substantiation	Framework - Further Competition	Services		06/05/2024	27/06/2025	≥ £100k to <£500k	Donna Stewart	Frank Simmons
C1096	Strategic Programme	Non Active Drain Water Treatment Plant Works	Non Active Drain Water Treatment Plant Works	Below Threshold - Competitive Tender	Works		31/10/2024	24/06/2025	≥ £1m to <£5m	Dawn Sewell	Adreain Gill
C19606	Operations - Fuel	Provision of Non Destructive Assey 34	Provision of Non Destructive Assey 34 as detailed in specification.	Open Procedure	Supplies		01/07/2024	30/06/2027	≥ £100k to <£500k	Erica Innes	Derek Manson
C10632	Assurance	Replacement of the Whole Body Monitor and Supporting Equipment	This procurement is to supply a replacement Whole Body Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Open Procedure	Supplies	Not known	03/06/2024	31/12/2024	≥ £100k to <£500k	Fraser Bruce	Avril Fell	N/A
C1113	Operations - Waste	Voidage and Container Assessments	Voidage and Container Assessments	Framework - Further Competition	Services		02/09/2024	31/08/2025	≥ £100k to <£500k	Donna Stewart	Stephen Mackie
C10405	Operations - Waste	48 tonne Forklift Replacement	48 tonne Forklift Replacement	Open Procedure	Supplies		01/05/2024	30/04/2025	≥ £100k to <£500k	Janet Rosie	Stephen Mackie
C19455	Operations - Maintenance & Engineering Support	Annual Grounds Maintenance	Annual Grounds Maintenance	Open Procedure	Services	Re-procurement (same scope)	01/12/2024	30/11/2034	≥ £1m to <£5m	Kelsey Bain	Peter Swanson	3300008447
C15329	Strategic Programme	Shaft & Silo Waste Retrieval System	Procurement of a Silo Retrieval System for the Shaft & Silo programme - Detail Design, Manufacture, Installation & Commissioning,.	Restricted Procedure	Works		15/01/2025	15/01/2031	≥ £10m to <£25m	Lee Parnell	Grant Coghill
C1124	Strategic Programme	Waste Treatment Plant - Scheme Design & Safety Assessment	Waste Treatment Plant - Scheme Design & Safety Assessment	Framework - Further Competition	Services		01/09/2025	30/09/2026	≥ £100k to <£500k	Heidi Warner	Gary Armstrong
C18791	Operations - Waste	NDA40 equipment and Software	NDA40 equipment and Software	Direct Award - Below Threshold	Supplies		31/05/2024	02/09/2024	< £100k	Hannah Budge	Jeremy Andrew
C1165	Strategic Programme	Remote Handled Intermediate Level Waste Letter of Compliance (Ion Exchange)	Remote Handled Intermediate Level Waste Letter of Compliance (Ion Exchange)	Framework - Direct Award	Services		03/07/2024	31/07/2025	< £100k	Robert McDonald	Duncan Gray	N/A
C18812	Operations - Waste	Portable X-Ray Radiography System	Portable X-Ray Radiography System	Below Threshold - Competitive Tender	Supplies		30/04/2025	01/08/2025	< £100k	Hannah Budge	Jeremy Andrew
C8624	Operations - Waste	Low Level Waste Effluent Treatment Plant Ventilation System Upgrade	Low Level Waste Effluent Treatment Plan Ventilation System Upgrade	Below Threshold - Competitive Tender	Works		01/05/2024	30/09/2024	< £100k	Donna Stewart	Morris Macleod
C16201	Operations - Maintenance & Engineering Support	Purchase of 2 x new Tipper / Gritter Lorries	Purchase of 2 x new Tipper / Gritter Lorries	Open Procedure	Supplies	Not known	01/05/2024	30/04/2025	≥ £100k to <£500k	Fraser Bruce	Ian Mackay
C18813	Operations - Waste	Dionex Ion Chromatography System (Effluent Lab)	Dionex Ion Chromatography System (Effluent Lab)	Direct Award - Below Threshold	Supplies		01/05/2025	01/09/2025	< £100k	Hannah Budge	Jeremy Andrew
C15131	Operations - Maintenance & Engineering Support	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/05/2025	30/04/2029	≥ £1m to <£5m	Carly Erridge	Mick Moore	CFA/21/0002-0010
C18928	Operations - Maintenance & Engineering Support	Provision of Lifting Services	Provision of Lifting Services	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/05/2025	30/04/2029	≥ £500k to <£1m	Janet Rosie	Laurence Campbell	CFA/21/0011
C13989	Operations - Waste	Break Tank Improvements	Break Tank Improvements	Below Threshold - Competitive Tender	Works		02/09/2025	02/03/2026	< £100k	Hannah Budge	Morris Macleod
C1167	Strategic Programme	Fuel Cycle Area North Concept Decommissioning Planning	Fuel Cycle Area North Concept Decommissioning Planning	Framework - Further Competition	Services		01/05/2025	30/05/2026	≥ £1m to <£5m	Robert McDonald	Duncan Gray
C1072	Strategic Programme	Shaft and Silo Process Cell and Waste Transfer System	Shaft and Silo Process Cell and Waste Transfer System	Framework - Further Competition	Services		01/05/2025	29/09/2030	≥ £10m to <£25m	Kirstin Polson	Iain Lyall
C11262	Finance	U4BW Software as a Service	Unit4 Business World (U4BW) Software as a Service (SaaS).	Framework - Direct Award	Services	Re-procurement (same scope)	01/07/2025	30/06/2028	≥ £500k to <£1m	Lynsey Will	Amanda Petrie	3300026361
C1120	Strategic Programme	Supply of Half Height ISO Low Level Waste Containers Framework Agreement	Framework Agreement for the Supply of Half Height ISO Low Level Waste Containers	Framework Agreement – Set up of a new Framework	Supplies	Re-procurement (same scope)	01/07/2025	30/06/2029	≥ £10m to <£25m	Janet Rosie	Alistair Ross	CFA/12/0048 - CFA/12/0049
C14394	Assurance	Provision of Criticality Software MONK & Visual Workshop	Provision of Criticality Software MONK & Visual Workshop	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	01/04/2025	31/03/2030	≥ £100k to <£500k	Kelsey Bain	Mike Potts	3300031908
C1108	Operations - Fuel	Thorium Nitrate Manufacture, Integrated Works Testing, Installation	Thorium Nitrate Manufacture, Integrated Works Testing, Installation and Commissioning	Framework - Further Competition	Works		01/08/2025	31/05/2026	≥ £500k to <£1m	Dawn Sewell	Derek Manson
C1252	Finance	Programme Controls Support	Programme Controls Support	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	11/08/2025	11/08/2028	≥ £500k to <£1m	Ilona Unger-Russell	Neil Cook	3300027789
C1100	Operations - Fuel	D2001 Irradiated Fuels Containers Manufacture	D2001 Irradiated Fuels Containers Manufacture	Open Procedure	Services		01/09/2025	30/01/2028	≥ £1m to <£5m	Erica Innes	Andrew Hamilton
C1099	Operations - Fuel	D2001 Irradiated Fuels Detailed Design and Build	D2001 Irradiated Fuels Detailed Design and Build	Framework - Further Competition	Works		01/09/2025	31/07/2028	≥ £25m to <£50m	Adam Scott	Derek Manson
C1097	Operations - Reactor	Prototype Fast Reactor Intermediate Level Waste Size Reduction Facility	Prototype Fast Reactor Intermediate Level Waste Size Reduction Facility Scheme, Detail Design and Build	Framework - Further Competition	Works		01/09/2025	23/04/2029	≥ £10m to <£25m	Adam Scott	Vicki Edmunds
C1098	Strategic Programme	Waste Treatment Plant - Detail Design and Build	Waste Treatment Plant - Detail Design and Build	Framework - Further Competition	Works		01/09/2025	01/07/2028	≥ £5m to <£10m	Heidi Warner	Gary Armstrong
C1110	Operations - Fuel	Irradiated Fuels Consolidated Furniture Scheme and Detail	Irradiated Fuels Consolidated Furniture Scheme and Detailed Design	Framework - Further Competition	Services		29/11/2024	27/06/2025	≥ £100k to <£500k	Robert McDonald	Vicki Edmunds
C17717	Operations - Fuel	Supply of Stainless Steel Boxes	Supply of Stainless Steel Boxes	Below Threshold - 3 Quotes	Supplies		30/04/2024	15/05/2024	< £100k	Erica Innes	Derek Manson
C18811	Operations - Waste	D1310 Total Organic Carbon backup	D1310 Total Organic Carbon backup	Below Threshold - 3 Quotes	Supplies		31/05/2024	02/09/2024	< £100k	Hannah Budge	Jeremy Andrew
C1144	Operations - Reactor	Treatment and Disposal of Sodium and Sodium Contaminated Waste	Prototype Fast Reactor Treatment and Disposal of Sodium and Sodium Contaminated Waste	Innovation Partnership (IP)	Services		07/10/2025	07/10/2030	≥ £5m to <£10m	Robert McDonald	Andrew MacInnes
C18805	Operations - Waste	Shielded Collimator	Shielded Collimator	Direct Award - Below Threshold	Supplies		31/05/2024	01/09/2024	< £100k	Hannah Budge	Jeremy Andrew
C18788	Operations - Waste	SPIRE ACE Inspector System	SPIRE ACE Inspector System	Direct Award - Below Threshold	Supplies		31/05/2024	01/09/2024	< £100k	Hannah Budge	Jeremy Andrew
C19577	Operations - Fuel	Safety Case Consultant to provide safety case support to D1203 and D2001	a Safety Case Consultant to provide safety case support to D1203 and D2001 decommissioning, and provide inventory support to the Irradiated Fuels Programme.	Framework - Further Competition	Services		01/05/2024	30/04/2026	≥ £100k to <£500k	Alex Wood	Derek Manson	3300032871
C19142	Assurance	Provision of Internal and Criticality Accident Dosimetry Service	Provision of Internal and Criticality Accident Dosimetry Service	Open Procedure	Services	Re-procurement (different scope)	01/04/2026	31/03/2030	≥ £1m to <£5m	Fraser Bruce	Anthony Ridgley	3300008206
C19644	Operations - FCA Decommissioning	Provision of Decommissioning Operatives	Provision of Decommissioning Operatives	Restricted Procedure	Services	Not known	01/04/2026	31/03/2031	≥ £25m to <£50m	Robert McDonald	Graeme Dunnett	3300031138
C18828	Strategic Programme	Advanced Transition Works (ATW) - facility hire for prototype model testing	Hire of a facility for the prototype testing for the Existing Shaft Headworks. A facility is required for a to-scale mock up which is required to ensure the most effective means is applied in dismantling the shaft slab.	Open Procedure	Works		05/06/2024	06/09/2024	≥ £100k to <£500k	Samantha Davidson	Jared Fraser
C12886	Operations - Waste	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	Below Threshold - Competitive Tender	Services		02/09/2024	28/03/2025	< £100k	Donna Stewart	Michael Bailey