## Procurement_Plan
		Nuclear Restoration Services Limited (Dounreay) - Procurement Plan June 2025
For further information contact Dounreay at commercial.services@dounreay.com
☆ Record Ref	Business Unit	Sourcing to Contract: Record Name	☆ Published Description	Procurement Route ( If known )	Contract Type	Desired Contract Start Date	Desired Contract End Date	Value Range	Previous Contract Ref	Contract Owner
C1239	Balance of Site	65 tonne Bogie Modifications Package	65 tonne Bogie Modifications Package	Below Threshold - Competitive Tender	Works	26/03/2027	29/07/2027	≥ £100k to <£500k		Sonja Sinclair
C9877	Balance of Site	Area 300 Main Immobilisation Line installation	Area 300 Main Immobilisation Line installation	Below Threshold - Competitive Tender	Works	24/10/2026	18/12/2027	≥ £100k to <£500k		Sonja Sinclair
C9887	Balance of Site	Area 400 Internal Ventilation	To be coordinated with the installation of Area 300 and Area 400 Fan and Filter Rooms	Direct Award - Below Threshold	Works	18/06/2026	30/03/2026	< £100k		Sonja Sinclair
C9900	Balance of Site	Area 500 Electrical Equipment Procurement	Area 500 Electrical Equipment Procurement	Below Threshold - 3 Quotes	Works	25/01/2027	20/07/2027	< £100k		Sonja Sinclair
C9875	Balance of Site	Area 600 - Internal Cement Powders Line and Caustic Line installation	Area 600 - Internal Cement Powders Line installation, internal and external Caustic Line installation and Phase 1 internal ventilation installation	Below Threshold - Competitive Tender	Works	01/04/2026	18/07/2026	≥ £100k to <£500k		Sonja Sinclair
C9871	Balance of Site	Area 600 Caustic Line	Area 600 Caustic Line	Direct Award - Below Threshold	Works	06/06/2026	07/07/2026	< £100k		Sonja Sinclair
C26046	Balance of Site	Asset Management of Plant and Equipment for Shaft & Silo	Asset management of plant and equipment incorporating storage and limited maintenance.	Open (PA23)	Services	01/10/2026	30/09/2031	≥ £1m to <£5m		Kelsey Bain
C13989	Balance of Site	Break Tank Improvements	Break Tank Improvements	Below Threshold - Competitive Tender	Works	02/09/2025	02/03/2026	< £100k		Lee Parnell
C25157	Balance of Site	Civil and Structural Engineering Support	Civil & Structural Engineering Support for LLW Disposal Facilities	Below Threshold - Competitive Tender	Services	01/09/2025	31/08/2029	≥ £100k to <£500k	3300017689	Kelsey Bain
C23323	Balance of Site	Construction of Intermediate Floor Slab on top of half-height ISO containers	Construction of Intermediate Floor Slab on top of half-height ISO containers	Direct Award - Below Threshold	Works	14/07/2025	31/10/2025	≥ £100k to <£500k		Kelsey Bain
C25459	Balance of Site	Consultancy Advice on Site Electrical System	A consultant is required to provide advice on the existing electrical infrastructure and support development of a utilities upgrade strategy	Direct Award - Below Threshold	Services	14/07/2025	09/07/2027	≥ £100k to <£500k		Samantha Davidson
C22296	Balance of Site	Costal erosion study and peer review	Costal erosion study and peer review	Framework - Further Competition	Services	01/07/2026	27/07/2027	< £100k		Erica Innes
C26552	Balance of Site	ADU FLoc Opportunity	Survey area, produce and options report, develop chosen option to a scheme design for a new active transfer line	Competitive Flexible	Services	08/09/2025	27/02/2026	< £100k		Sonja Sinclair
C23315	Balance of Site	Electrical Rationalisation	Electrical Rationalisation	Below Threshold - Competitive Tender	Works	01/04/2026	10/04/2029	≥ £500k to <£1m		Sonja Sinclair
C23313	Balance of Site	external Design, build, installation of a new containerised Switch room	external Design, build, installation of a new containerised Switch room	Below Threshold - Competitive Tender	Works	28/07/2026	23/04/2028	≥ £100k to <£500k		Sonja Sinclair
C23310	Balance of Site	North Side Asbestos removal	North Side Asbestos Removal	Framework - Further Competition	Works	01/10/2025	22/06/2026	≥ £1m to <£5m		Sonja Sinclair
C23314	Balance of Site	Reyrolle enabling	Reyrolle enabling	Direct Award - Below Threshold	Works	26/01/2026	11/06/2026	≥ £100k to <£500k		Sonja Sinclair
C23312	Balance of Site	South Side Asbestos Removal	South Side Asbestos Removal	Below Threshold - Competitive Tender	Works	10/03/2026	23/08/2027	≥ £1m to <£5m		Sonja Sinclair
C25688	Balance of Site	Laboratories Upgrades	NRS Dounreay is undertaking a series of services upgrades and refurbishment work within the Laboratories. A Contractor is required to undertake mechanical, electrical and architectural design, refurbishment and commissioning activities.	Below Threshold - Competitive Tender	Works	01/09/2025	31/08/2028	≥ £1m to <£5m		Erica Innes
C26383	Balance of Site	CCTV Camera System Upgrade	Nuclear Restoration Services (NRS) Limited (Dounreay) requires the design, supply and commissioning of new CCTV camera to upgrade the current obsolete camera system within a facility on the Dounreay site.	Below Threshold - 3 Quotes	Supplies	01/09/2025	30/01/2026	< £100k		Janet Brooke
C13987	Balance of Site	Generator	Generator	Below Threshold - Competitive Tender	Supplies	31/08/2025	30/11/2025	< £100k		Lee Parnell
C1122	Balance of Site	Switchboard	Switchboard	Open Procedure	Supplies	30/07/2025	30/12/2025	≥ £100k to <£500k		Lee Parnell
C24247	Balance of Site	Roller Door Design and Installation	Roller Door Design and Installation	Below Threshold - 3 Quotes	Supplies	01/09/2025	01/03/2026	< £100k		Kate Murray
C25689	Balance of Site	Design and Build of Shaft & Silo Waste Transfer Corridor	Shaft & Silo have a requirement for a Contractor to undertake Design and Build of a Waste Transfer Corridor in relation to the main build.	Competitive Flexible	Works	01/02/2026	20/12/2030	≥ £10m to <£25m		Kirstin Polson
C12385	Balance of Site	Dounreay Cementation Plant Licence Condition Peer Review	Dounreay Cementation Plant Licence Condition Peer Review	Framework - Further Competition	Services	21/07/2025	31/08/2026	≥ £100k to <£500k		Erica Innes
C9903	Balance of Site	Electrical Control and Instrumentation Services	Electrical Control and Instrumentation Services	Open Procedure	Services	01/09/2026	31/03/2029	≥ £500k to <£1m		Sonja Sinclair
C22302	Balance of Site	Geochemical And Near Field Evolution	Geochemical And Near Field Evolution	Framework - Further Competition	Services	01/10/2026	31/07/2027	< £100k		Erica Innes
C13988	Balance of Site	Gravity Receipt Tank Ladder Replacement	Gravity Receipt Tank Ladder Replacement	Below Threshold - Competitive Tender	Works	08/07/2025	08/01/2026	< £100k		Lee Parnell
C26585	Balance of Site	Hire of Rubber Duck, Hydraulic Breaker Attachment & Operator	Hire of Rubber Duck, Hydraulic Breaker Attachment & Operator	Direct Award - Below Threshold	Works	07/07/2025	19/09/2025	< £100k		Kelsey Bain
C25230	Balance of Site	IEF North Load Bay Door Replacement	Manufacture, installation and project management of fitting IEF North Load Bay door.	Below Threshold - Competitive Tender	Works	01/09/2025	31/10/2025	≥ £100k to <£500k		Janet Brooke
C26744	Balance of Site	Independent Peer Review Licence Condition 15 Periodic Review - Low Active Drain	The Client has a requirement for a Consultant to undertake an Independent Peer Review of the Licence Condition 15 Period Review of the extant safety case for the Low Active	Framework - Further Competition	Services	01/09/2025	31/08/2026	≥ £100k to <£500k		Erica Innes
C26743	Balance of Site	Independent Peer Review of Licence Condition 15 Periodic Review - Laboratories	The Client has a requirement for a Consultant to undertake an Independent Peer Review of the Licence Condition 15 Period Review of the extant facility safety cases	Framework - Further Competition	Services	01/12/2026	01/09/2028	≥ £100k to <£500k		Erica Innes
C26695	Balance of Site	Independent Peer Review of Licence Condition 15 Periodic Review	The Client requires a Consultant to undertake an Independent Peer Review of the Licence Condition 15 Period Review of the extant facility safety cases.	Framework - Further Competition	Services	01/12/2025	30/04/2028	≥ £100k to <£500k		Lauren J Mackay
C22303	Balance of Site	Infield Investigation Planning	Infield Investigation Planning	Framework - Further Competition	Services	01/07/2026	12/02/2027	< £100k		Erica Innes
C22295	Balance of Site	Legal compliance position statements	Legal compliance position statements	Below Threshold - 3 Quotes	Services	01/08/2026	31/01/2027	< £100k		Erica Innes
C26742	Balance of Site	Licence Condition 15 Periodic Review	The Client has a requirement for a Consultant to undertake a Licence Condition 15 Period Review of the extant facility safety cases.	Framework - Further Competition	Services	01/09/2026	01/09/2028	≥ £500k to <£1m		Erica Innes
C26694	Balance of Site	Licence Condition 15 Periodic Review.	The Client requires a Consultant to undertake a Licence Condition 15 Period Review of the extant facility safety case.	Framework - Further Competition	Services	01/10/2025	30/04/2028	≥ £500k to <£1m		Lauren J Mackay
C1238	Balance of Site	Lid Lifting Frame and Bedplate Frame Package	Lid Lifting Frame and Bedplate Frame Package	Below Threshold - Competitive Tender	Works	27/04/2027	15/07/2027	< £100k		Sonja Sinclair
C13986	Balance of Site	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Below Threshold - Competitive Tender	Services	30/11/2025	30/06/2026	≥ £100k to <£500k		Lee Parnell
C16843	Balance of Site	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Framework - Further Competition	Services	30/07/2025	30/09/2025	< £100k		Lee Parnell
C8624	Balance of Site	Low Level Waste Effluent Treatment Plant Ventilation System Upgrade	Low Level Waste Effluent Treatment Plan Ventilation System Upgrade	Below Threshold - Competitive Tender	Works	14/09/2025	30/11/2025	< £100k		Lee Parnell
C16547	Balance of Site	Low Level Waste Pits - Provision of Cover Building	Low Level Waste Pits - Provision of Cover Building	Below Threshold - Competitive Tender	Supplies	03/09/2025	27/12/2025	< £100k		Lee Parnell
C15305	Balance of Site	Low Level Waste Pits - Resurfacing	Low Level Waste Pits - Resurfacing	Below Threshold - Competitive Tender	Works	03/09/2025	31/03/2026	≥ £100k to <£500k		Lee Parnell
C1142	Balance of Site	Manufacture and Design Ammonium Diuranate Floc Transport Stillage Lifting Beam	Manufacture and Design of Ammonium Diuranate Floc Transport Stillage Lifting Beam	Below Threshold - Competitive Tender	Services	24/06/2026	20/12/2027	≥ £100k to <£500k		Sonja Sinclair
24472	Balance of Site	Mechanical Design Services	Mechanical Design Services	Open Procedure	Services	01/09/2026	31/03/2029	≥ £1m to <£5m		Sonja Sinclair
C22297	Balance of Site	Performance Assessment Initial Report	Performance Assessment Initial Report	Framework - Further Competition	Services	15/01/2027	15/06/2028	< £100k		Erica Innes
C23640	Balance of Site	Programme and Technical Integration Support Services for Shaft & Silo	The Balance of Site Programme has a requirement for experienced and highly skilled Programme and Technical Integration Support Services for the Shaft and Silo Programme.	Framework - Further Competition	Services	28/07/2025	27/07/2027	≥ £500k to <£1m	3300017188	Kirstin Polson
C26617	Balance of Site	Provision of Environmental Services to Balance of Site	Provision of Environmental Services to Balance of Site	Framework - Direct Award	Services	21/07/2025	27/02/2027	< £100k		Lauren J Mackay
C23473	Balance of Site	Provision of Environmental Support	The purpose of this Contract is to provide embedded Environmental Support to NRS Dounreay.	Framework - Further Competition	Services	20/10/2025	16/10/2027	≥ £100k to <£500k	3300042672	Lauren J Mackay
C22594	Balance of Site	Provision of Long Term Storage complete with Overhead Crane Facility	NRS looks to engage a contractor to provide the provision of Long Term Storage complete with Overhead Crane Facility	Restricted Procedure	Services	01/10/2025	30/09/2026	≥ £100k to <£500k		Kelsey Bain
C16984	Balance of Site	Replacement of Wound Monitor and Supporting Equipment	This procurement is to supply a replacement Wound Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Below Threshold - Competitive Tender	Supplies	01/09/2025	28/02/2026	< £100k	N/A	Erica Innes
C22663	Balance of Site	Reserved Procure Immob Line - System 331 Double Door & System 330 Mixing Station	ADU Floc Immobilisation Line - System 331 Double Door & System 330 Mixing Station Assembly, Mixing head & Hydraulic pac including EC&I	Below Threshold - Competitive Tender	Works	07/10/2025	23/02/2026	≥ £100k to <£500k		Sonja Sinclair
C24473	Balance of Site	Reserved Procurement Immobilisation Line - Mechanical Rectifications	Ammonium Di-Uranate Flocculant (ADU Floc) Immobilisation Line - Mechanical Rectification	Below Threshold - Competitive Tender	Works	24/10/2026	18/12/2026	< £100k		Sonja Sinclair
C24472	Balance of Site	Reserved Procurement Immobilisation Line - System 330 - SCADA Programming	Ammonium Di-Uranate Flocculant (ADU Floc) Immobilisation Line - System 330 - SCADA Programming	Below Threshold - Competitive Tender	Works	24/10/2026	18/12/2026	< £100k		Sonja Sinclair
C24470	Balance of Site	Reserved Procurement Immobilisation Line - System 360 DF Improvements	Ammonium Di-Uranate Flocculant (ADU Floc) Immobilisation Line - System 360 - DF Improvements and penetrations inc EC&I	Below Threshold - Competitive Tender	Works	21/10/2026	06/11/2026	≥ £100k to <£500k		Sonja Sinclair
C22661	Balance of Site	Reserved Procurement Immobilisation Line - System 361 Drum Lid Transfer Station	Ammonium Di-Uranate Flocculant (ADU Floc) Immobilisation Line - System 361 Drum Lid Transfer Station	Below Threshold - Competitive Tender	Works	23/09/2025	12/01/2026	< £100k		Sonja Sinclair
C22670	Balance of Site	Reserved procurement Immobilisation Line-Interface works - Area 400	ADU Floc Immobilisation Line - Interface works - fire damper panel mods and installing connection for SCADA	Below Threshold - Competitive Tender	Works	21/10/2025	06/11/2025	< £100k		Sonja Sinclair
C25401	Balance of Site	Retrieval Option - Review of Options and Data Development	Retrieval Option - Review of Options and Data Development	Framework - Further Competition	Services	15/01/2027	15/07/2029	< £100k		Erica Innes
C26389	Balance of Site	Services of Electrical Engineers to support DCP Stores Extension	Services of experiences electrical engineers to support DCP Stores Extension Project		Services	31/03/2026			C26388	Sonja Sinclair
C22521	Balance of Site	Shaft Head Removal - Concrete Cutting of the shaft headworks	NRS looks to engage a contractor to provide concrete cutting of the shaft headworks , which includes both the cutting of a Mock Up Trials Rig and the actual works.	Below Threshold - Competitive Tender	Works	01/09/2025	31/07/2026	≥ £500k to <£1m		Kelsey Bain
C20555	Balance of Site	Shaft Head Removal - Facility Hire & Construction of Mock Up Trials Rig	NRS looks to engage a contractor to provide the hire of a local facility, and the construction of a trials rig for the Shaft Head Removal Trials	Below Threshold - Competitive Tender	Works	01/09/2025	28/02/2026	≥ £100k to <£500k		Kelsey Bain
C26782	Balance of Site	Silo Licence Condition 15 Engineering Substantiation	Silo Licence Condition 15 Engineering Substantiation	Direct Award - Below Threshold	Services	01/09/2025	31/12/2027	< £100k		Lauren J Mackay
C26047	Balance of Site	Silo Transition Works	Upgrade and removal of redundant services demolition works to facilitate future construction, Demobilise site and handover for main construction	Open (PA23)	Works	01/04/2026	31/03/2028	≥ £1m to <£5m		Kelsey Bain
C25886	Balance of Site	Steam Upgrade - Hire of Steam Package Units	There are nine facilities identified for steam heating to be reinstated. Two steam rental units will be required.	Open (PA23)	Services	29/08/2025	28/08/2026	≥ £100k to <£500k		Dawn Sewell
C25893	Balance of Site	Steam Upgrade - Lifting Support	There are nine facilities for steam heating to be reinstated. Two facilities will require lifting support.	Framework - Direct Award	Works	29/08/2025	28/08/2026	< £100k		Dawn Sewell
C25891	Balance of Site	Steam Upgrade - Scaffolding Support	There are nine facilities identified for steam heating to be reinstated. Four of these facilities will require scaffolding support	Framework - Direct Award	Services	29/08/2025	28/08/2026	≥ £100k to <£500k		Dawn Sewell
C25885	Balance of Site	Steam Upgrade Asbestos Removal	There are nine facilities identified for steam heating to be reinstated. Asbestos surveys and licensed asbestos removal will be required.	Direct Award - Below Threshold	Works	29/08/2025	28/08/2026	< £100k		Dawn Sewell
C25881	Balance of Site	Steam Upgrade Design	There are nine facilities identified for steam heating to be reinstated. Five facilities will require design drawing packs.	Framework - Further Competition	Services	29/08/2025	28/08/2026	≥ £100k to <£500k		Dawn Sewell
C25884	Balance of Site	Steam Upgrade Mechanical Fabrication	There are nine facilities identified for steam heating to be reinstated. Three fabrication and installation packages will be required.	Below Threshold - Competitive Tender	Works	29/08/2025	28/08/2026	≥ £100k to <£500k		Dawn Sewell
C26712	Balance of Site	Steamline Contingency - Fabrication	The procurement, fabrication and commissioning of temporary steam piping, feedwater piping and drainage	Direct Award - Below Threshold	Works	14/07/2025	30/01/2026	≥ £100k to <£500k		Dawn Sewell
C9919	Balance of Site	Stillage Transfer System - Changing Room	Stillage Transfer System - Changing Room	Below Threshold - Competitive Tender	Works	18/11/2026	12/03/2027	< £100k		Sonja Sinclair
C9897	Balance of Site	Stillage Transfer System - Control System Modifications	Control system Modifications design and implementation	Below Threshold - Competitive Tender	Works	14/12/2026	23/02/2027	< £100k		Sonja Sinclair
C9890	Balance of Site	Stillage Transfer System- Gantry Crane & Frame	Works on the Stillage Transfer System- the Gantry Crane and Frame only	Below Threshold - Competitive Tender	Works	04/03/2026	19/02/2027	≥ £100k to <£500k		Sonja Sinclair
C26680	Balance of Site	Supply and Delivery of a Portacabin	Supply and Delivery of a Portacabin	Below Threshold - 3 Quotes	Supplies	28/07/2025	29/08/2025	< £100k		Lauren J Mackay
C24962	Balance of Site	Supply of a Whole Body Monitor	This procurement is to supply a replacement Whole Body Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Direct Award - Above Threshold - Competition Dispensed With	Supplies	28/07/2025	31/03/2026	≥ £500k to <£1m		Erica Innes
C1246	Balance of Site	The supply of Cameras, Camera Encoders & Server Upgrade & supporting maintenance	- The supply and delivery of Cameras, Camera Encoders and Server Upgrade. / - Maintenance of Titan Vision Control Equipment.	Direct Award - PCR Single Source (Reg 32)	Supplies	28/05/2026	29/05/2030	≥ £1m to <£5m	N/A	Fraser Bruce
C22505	Capability	Automated Access Control System Replacement	Supply, Commissioning, Installation and Maintenance of an Automated Access Control System (AACS) on the Dounreay Site.	PCR Exemption - Other	Works	30/07/2025	31/10/2026	≥ £500k to <£1m		Louise Gunn
C26000	Capability	GovPass Service Implementation and Support Serivces	GovPass service implementation for the NRS Dounreay Site Automated Access Control System	Framework - Direct Award	Works	01/08/2025	30/09/2030	≥ £100k to <£500k		Louise Gunn
C10546	Capability	LINC with Dounreay Registration	Registration for LINC with Dounreay DPS	Dynamic Purchasing System (DPS)	Other	08/12/2025	13/12/2028	≥ £1m to <£5m		Hannah Budge
C20891	Capability	Maintenance and Development of the Dounreay Data Management System	Maintenance and Development of the Dounreay Data Management System	Open (PA23)	Services	01/10/2025	30/09/2029	≥ £1m to <£5m	3300015868	Ilona Unger-Russell
C26487	Capability	NRS Limited Dounreay Make verses Buy Assessment	NRS Limited Dounreay Make verses Buy Assessment	Framework - Further Competition	Services	06/10/2025	31/01/2026	< £100k		Corrinda Pearson
C26561	Capability	Safety Case Support and Peer Review Services Framework (2027-2031)	Safety Case Support and Peer Review Services Framework (2027-2031)	Framework Agreement – Set up of a new Framework	Services	01/02/2027	31/01/2031	≥ £10m to <£25m	CFA/23/0001 - CFA/23/0007	Janet Brooke
C26562	Capability	Technical and Professional Services Support Framework (2027-2031)	Technical and Professional Services Support Framework (2027-2031)	Framework Agreement – Set up of a new Framework	Services	01/06/2027	31/05/2031	≥ £10m to <£25m	CFA/23/0015 - CFA/23/0020	Janet Brooke
C20641	EHSSQ	Call-off contract for ambulance training and Learning in Practice days	Call-off contract for ambulance training and Learning in Practice days	Direct Award - Below Threshold	Services	01/09/2025	31/03/2026	< £100k		Debbie Weir
C26042	EHSSQ	Civil Nuclear Constabulary Budget 2026-27	Civil Nuclear Constabulary Budget 2026-27	Non Procurement	Other	01/04/2026	31/03/2027	≥ £10m to <£25m	3300046763	Corrinda Pearson
C12623	EHSSQ	Firefighter and Officer Related Training	Firefighter and Officer Related Training	Direct Award - Below Threshold	Services	01/10/2025	31/03/2026	< £100k		Debbie Weir
C25966	EHSSQ	Provision of Canine Support Services - Explosive Search Capability	Provision of Canine Support Services - Explosive Search Capability	Competitive Flexible	Services	20/09/2026	19/09/2028	≥ £100k to <£500k	3300034425	Corrinda Pearson
C26037	EHSSQ	Provision of Emergency Communication System	Provision of Emergency Communication System	Below Threshold - Competitive Tender	Services	01/10/2025	29/09/2027	< £100k		Lynsey Will
C19142	EHSSQ	Provision of Internal and Criticality Accident Dosimetry Service	Provision of Internal and Criticality Accident Dosimetry Service	Open Procedure	Services	01/04/2026	31/03/2030	≥ £1m to <£5m	3300008206	Fraser Bruce
C12555	EHSSQ	Purchase of Ambulance	Purchase of Ambulance	Below Threshold - Competitive Tender	Supplies	01/04/2027	31/03/2028	≥ £100k to <£500k		Debbie Weir
C1182	EHSSQ	Purchase of Anti-Pedestrian Gates	Purchase of Anti-Pedestrian Gates	Below Threshold - Competitive Tender	Supplies	03/06/2027	06/12/2027	≥ £100k to <£500k		Lee Parnell
C1164	EHSSQ	Purchase of Fence	Purchase of Fence	Below Threshold - Competitive Tender	Supplies	03/06/2027	06/12/2027	≥ £100k to <£500k		Lee Parnell
C1183	EHSSQ	Purchase of Pedestrian Gates	Purchase of Pedestrian Gates	Below Threshold - Competitive Tender	Supplies	03/06/2027	06/12/2027	< £100k		Lee Parnell
C1184	EHSSQ	Purchase of Vehicle Access Gates	Purchase of Vehicle Access Gates	Below Threshold - Competitive Tender	Supplies	03/06/2027	06/12/2027	< £100k		Lee Parnell
C26036	EHSSQ	Supply of Fire Appliance	Supply of Fire Appliance	Open (PA23)	Supplies	01/04/2026	30/03/2027	≥ £100k to <£500k		Corrinda Pearson
C25707	FCA	Carbon Bed Filter Borehole Project	Drilling of boreholes associated with Carbon Bed Filter investigation work.	Below Threshold - 3 Quotes	Works	03/11/2025	06/07/2026	≥ £100k to <£500k		Kerrie Mackay
C22243	FCA	Crane Control System Upgrade	Crane Control System Upgrade	Below Threshold - Competitive Tender	Services	10/09/2025	02/06/2026	< £100k		Alex Wood
C26183	FCA	Safety Case Support	Safety Case Support 2026-28	Framework - Further Competition	Services	01/02/2026	31/03/2028	≥ £100k to <£500k		Kerrie Mackay
C25112	FCA	Waste Crates	Waste Crates	Below Threshold - Competitive Tender	Services	01/01/2026	01/12/2027	< £100k		Kerrie Mackay
C25127	FCA	Air Handling Unit Duct Replacement	Air Handling Unit Duct Replacement	Below Threshold - 3 Quotes	Works	06/10/2025	05/10/2026	≥ £100k to <£500k		Kate Thomson
C25122	FCA	Fall Restraint Installation	Fall Restraint Installation	Below Threshold - 3 Quotes	Services	01/01/2026	01/01/2027	≥ £100k to <£500k		Kate Thomson
C25110	FCA	Window Replacement Design Services	Window Replacement Design Services for the Fuel Cycle Area	Below Threshold - Competitive Tender	Services	01/06/2026	01/06/2027	≥ £100k to <£500k		Kate Thomson
C25106	FCA	Window Replacement Safety Case Consultancy	Window Replacement Safety Case Consultancy for Fuel Cycle Area	Framework - Further Competition	Services	01/12/2026	01/12/2028	≥ £100k to <£500k		Kate Thomson
C25137	FCA	Demolition	Demolition	Below Threshold - 3 Quotes	Works	02/09/2025	01/06/2026	< £100k		Kerrie Mackay
C1128	FCA	Cell Floor Block Lifting Bags	Cell Floor Block Lifting Bags	Direct Award - Below Threshold	Supplies	30/09/2025	30/11/2025	< £100k		Alex Wood
C25190	FCA	Concrete Coring of the Facility Floor	Concrete Coring of the Facility Floor	Below Threshold - Competitive Tender	Works	15/08/2025	28/02/2026	≥ £100k to <£500k		Robert McDonald
C25115	FCA	Floor Removal Equipment Design and Build	Floor Removal Equipment Design and Build	Open (PA23)	Works	15/09/2025	15/05/2026	≥ £500k to <£1m		Kate Thomson
C25251	FCA	Licence Condition 15 review of Authority to Operate 19 Facility Safety Cas	Licence Condition 15 review of Authority to Operate 19 Facility Safety Case Review	Framework - Further Competition	Services	30/07/2025	30/11/2027	≥ £100k to <£500k		Sarah McCaughey
C25133	FCA	Engineering Subtantiation	Engineering Subtantiation Services	Framework - Further Competition	Services	06/10/2025	05/10/2026	≥ £100k to <£500k		Kate Thomson
C23509	FCA	Electrical Design Support	Project require electrical design support.	Framework - Further Competition	Services	31/12/2025	31/12/2026	< £100k		Alex Wood
C25135	FCA	Fuel Cycle Area Ventilation Condition Assessment	Fuel Cycle Area Ventilation Condition Assessment	Below Threshold - 3 Quotes	Services	30/04/2026	26/04/2027	≥ £100k to <£500k		Kate Thomson
C25128	FCA	Non-Destructive Testing of Pond Concrete Structure	Non-Destructive Testing of Pond Concrete Structure	Open (PA23)	Services	08/09/2025	01/04/2026	< £100k		Kerrie Mackay
C25766	FCA	Provision of Environmental advisory support	Provision of Environmental advisory support	Framework - Further Competition	Services	17/11/2025	17/11/2027	≥ £500k to <£1m	3300043316	Sarah McCaughey
C1177	FCA	Reserved Procurement - Active Filter Change Robot Mechanical Modifications	Reserved Procurement - Active Filter Change Robot Mechanical Modifications	Below Threshold - Competitive Tender	Services	29/08/2025	28/11/2025	≥ £100k to <£500k		Alex Wood
C22691	FCA	Supply of Stainless Steel Boxes	Supply of Stainless Steel Boxes	Below Threshold - 3 Quotes	Supplies	02/09/2025	31/03/2026	≥ £100k to <£500k		Kerrie Mackay
C23973	FCA	Waste Characterisation Support for the Fuel Cycle Area on the Dounreay site.	The provision of Waste Characterisation Support to assist with the review of radionuclide fingerprints used at Dounreay for the purpose of waste characterisation, sentencing and disposal.	Framework - Further Competition	Services	24/11/2025	23/11/2027	≥ £500k to <£1m	3300042953; 3300036106; 3300036104	Louise Gunn
C26560	People	Framework Agreement for Contingent Resource (2027-2031)	Framework Agreement for Contingent Resource	Framework Agreement – Set up of a new Framework	Services	01/06/2027	31/05/2031	≥ £10m to <£25m	CFA/23/0012 - CFA/23/0015	Janet Brooke
C26041	People	LINC Opportunity 32 - Provision of Various Electrical Training	LINC Opportunity 32 - Provision of Various Electrical Training	Below Threshold - Competitive Tender	Services	01/11/2025	31/10/2028	≥ £100k to <£500k		Corrinda Pearson
C26040	People	LINC Opportunity 33 - Provision of NEBOSH Training	LINC Opportunity 33 - Provision of NEBOSH Training	Below Threshold - Competitive Tender	Services	01/11/2025	31/10/2028	≥ £100k to <£500k		Corrinda Pearson
C23541	Portfolio & Support	LINC Opportunity 30 - Legionella Risk Assessments	Legionella Risk Assessments	Below Threshold - Competitive Tender	Services	01/09/2025	31/01/2026	< £100k		Fraser Bruce
C14394	Portfolio & Support	Provision of Criticality Software MONK & Visual Workshop	Provision of Criticality Software MONK & Visual Workshop	Direct Award - Below Threshold	Services	01/04/2026	31/03/2030	< £100k	3300031908	Ilona Unger-Russell
C1168	Portfolio & Support	Waste Optimisation - Waste Optimisation Improvements	Waste Optimisation - Waste Optimisation Improvements	Framework - Further Competition	Services	01/09/2025	29/05/2026	< £100k		Janet Brooke
C25539	Reactors	Breeder Fuel Removal Flask Furniture Manufacture Sets 10 to 13	Breeder Fuel Removal Flask Furniture Manufacture Sets 10 to 13	Direct Award - Above Threshold - PA23 Section 41 (Special cases)	Services	31/10/2025	30/03/2026	≥ £500k to <£1m		Robert McDonald
C26435	Reactors	Roof Repairs	Roof Repairs	Below Threshold - 3 Quotes	Works	20/03/2027	13/08/2028	≥ £100k to <£500k		Kate Thomson
C26427	Reactors	Determine Method of Melting of Sodium from KnK Drums	Determine Method of Melting of Sodium from KnK Drums	Below Threshold - Competitive Tender	Services	31/05/2027	24/11/2027	≥ £1m to <£5m		Kate Thomson
C25549	Reactors	Demolition	Demolition	Below Threshold - 3 Quotes	Works	12/09/2025	30/01/2026	≥ £100k to <£500k		Kate Thomson
C25560	Reactors	Roof Repairs	Roof Repairs	Below Threshold - 3 Quotes	Works	02/04/2026	05/06/2028	≥ £100k to <£500k		Kate Thomson
C26438	Reactors	Building - Recladding	Building - Recladding	Below Threshold - 3 Quotes	Works	08/03/2027	10/09/2028	≥ £500k to <£1m		Kate Thomson
C25557	Reactors	Heating upgrade	Heating upgrade	Below Threshold - 3 Quotes	Works	15/02/2026	04/03/2028	≥ £100k to <£500k		Kate Thomson
C26437	Reactors	Pond Building - Reclad	Pond Building - Reclad	Below Threshold - 3 Quotes	Works	03/05/2026	08/08/2028	≥ £500k to <£1m		Kate Thomson
C26524	Reactors	Effluent Treatment Plant SCADA Software Upgrades	Supervisory Control and Data Acquisition (SCADA) software upgrades for Effluent Treatment Plant	Direct Award - Below Threshold	Works	14/07/2025	16/01/2026	< £100k		Jade Plowman
C26424	Reactors	Electrical Anne, Tank Farm and Buffer Store Repairs	Prototype Fast Reactor re-cladding of the Electrical Anne, re-cladding of the Tank Farm and re-roofing or repairs to PFR Buffer store roof	Below Threshold - Competitive Tender	Services	01/04/2027	29/03/2028	≥ £500k to <£1m		Kate Thomson
C21304	Reactors	Erection and Outfitting	Erection and Outfitting including Services Racking & Access Platforms	Below Threshold - Competitive Tender	Works	17/03/2026	30/09/2026	≥ £1m to <£5m		Jade Plowman
C25545	Reactors	Off-site Storage of PFR Ventilation Upgrades Equipment and Materials	Off-site Storage of PFR Ventilation Upgrades Equipment and Materials	Direct Award - Below Threshold	Works	01/08/2025	31/12/2026	< £100k		Adam Scott
C26436	Reactors	Painting Lower Area of Dounreay Fast Reactor Sphere	Painting Lower Area of Dounreay Fast Reactor Sphere	Below Threshold - 3 Quotes	Works	03/03/2027	25/08/2028	≥ £500k to <£1m		Kate Thomson
C25718	Reactors	Power Provision & Functional Testing of Residual NaK Removal Control System	Power Provision & Functional Testing of Residual NaK Removal (RNR) Control System	Direct Award - Below Threshold	Works	04/12/2025	25/12/2025	< £100k		Kerrie Mackay
C25559	Reactors	Concrete Panel Repair/Overcladding	Concrete Panel Repair/Overcladding	Below Threshold - 3 Quotes	Works	01/04/2026	29/03/2027	≥ £1m to <£5m		Kate Thomson
C25554	Reactors	Concrete Panels Methodology	Concrete Panels Methodology	Framework - Further Competition	Services	01/01/2026	31/03/2026	≥ £100k to <£500k		Kate Thomson
C25541	Reactors	North Wall Turbine Hall Recladding	North Wall Turbine Hall Recladding	Direct Award - Below Threshold	Works	04/08/2025	14/11/2025	≥ £500k to <£1m		Kate Thomson
C25536	Reactors	Structural Verification	Structural Verification	Framework - Further Competition	Services	28/07/2025	17/03/2026	≥ £100k to <£500k		Adam Scott
C26426	Reactors	Ventilation Upgrades	Procurement, Manufacture, Installation and Commissioning for Prototype Fast Reactor Ventilation Upgrades	Open (PA23)	Services	01/01/2027	31/12/2029	≥ £5m to <£10m		Kate Thomson
C25542	Reactors	Wall Recladding	Steam Generator Building North and West Wall Recladding, including De-Aerator Tower West	Direct Award - Below Threshold	Works	04/08/2025	14/11/2025	≥ £1m to <£5m		Kate Thomson
C25584	Reactors	Provision of Scaffolding Services for Dounreay Fast Reactor	Provision of Scaffolding Services for Dounreay Fast Reactor	Framework - Direct Award	Works	02/04/2026	02/04/2027	≥ £100k to <£500k		Kerrie Mackay
C25585	Reactors	Provision of Scaffolding Services for Prototype Fast Reactor	Provision of Scaffolding Services for Prototype Fast Reactor	Framework - Direct Award	Works	02/04/2026	02/04/2027	≥ £100k to <£500k		Kerrie Mackay
C25548	Reactors	Reactors Admin Roof Covering and Windows Replacement	Prototype Fast Reactor and Dounreay Fast Reactor Admin Block Replace Windows and Prototype Fast Reactor Roof Covering Replacement	Below Threshold - 3 Quotes	Works	05/08/2025	26/09/2026	≥ £100k to <£500k		Kate Thomson
C25558	Reactors	Replacement of Pond Vent Extract - Supply Only	Replacement of Pond Vent Extract - Supply Only	Below Threshold - 3 Quotes	Supplies	10/03/2026	09/05/2026	< £100k		Kate Thomson
C24486	Reactors	Reserved Procurement - Element Storage Building Exit to Sphere Walkway Repairs	5th floor element storage building exit walkway to sphere walkway repairs and replacements to steelwork.	Competitive Flexible	Works	14/07/2025	01/08/2025	≥ £100k to <£500k		Jade Plowman
C25552	Reactors	Residual NaK Removal Deterministic Fire Risk Assessment Author	Dounreay Fast Reactor - Residual NaK Treatment - Procurement of Deterministic Fire Risk Assessment Author	Framework - Further Competition	Services	02/10/2025	11/03/2026	< £100k		Kate Thomson
C25553	Reactors	Residual NaK Removal Safety Case Substantiation Support	Dounreay Fast Reactor - Residual NaK Treatment - Procurement of Safety Case Substantiation Support	Framework - Further Competition	Services	01/12/2025	20/08/2026	≥ £100k to <£500k		Kate Thomson
C25527	Reactors	Transport Bogeys for Small Water Leak Rig Tank 1 & 2 Vessels	Transport Bogeys for Small Water Leak Rig Tank 1 & 2 Vessels	Below Threshold - 3 Quotes	Works	14/07/2025	31/10/2025	< £100k		Jade Plowman
C21122	Reactors	Water Vapour Nitrogen Delivery System	Dounreay Fast Reactor - Removal of NaK Residues - Procurement of Water Vapour Nitrogen Delivery System	Below Threshold - 3 Quotes	Services	15/02/2027	29/02/2028	≥ £100k to <£500k		Jade Plowman
C25543	Reactors	Water Vapour Nitrogen Rigs Drawings Update	Water Vapour Nitrogen Rigs Drawings Update	Framework - Further Competition	Services	04/08/2025	31/03/2026	≥ £100k to <£500k		Kerrie Mackay
C26833	Site Services	4no. Portacabins for Site	4no. Portacabins for Site	Below Threshold - 3 Quotes	Supplies	01/09/2025	31/12/2026	< £100k		Fraser Bruce
C25181	Site Services	Annual ArcGIS Software Maintenance	Annual ArcGIS Software Maintenance 01/04/26 to 31/03/27	Below Threshold - 3 Quotes	Services	01/04/2026	31/03/2027	< £100k	3300046555	Fraser Bruce
C26634	Site Services	Calibration, Service and Repair of Aerosol Photometer and Aerosol Generators	Calibration, Service and Repair of Aerosol Photometer and Aerosol Generators	Direct Award - Below Threshold	Services	25/07/2025	24/07/2028	≥ £100k to <£500k		Immi Smith
C26319	Site Services	Ducting Project	Ducting Project	Below Threshold - 3 Quotes	Supplies	01/09/2025	31/12/2025	< £100k		Fraser Bruce
C1254	Site Services	Inductively Coupled Plasma - Mass Spectrometer	Inductively Coupled Plasma - Mass Spectrometer	Direct Award - Below Threshold	Supplies	06/10/2025	02/02/2026	≥ £100k to <£500k		Hannah Budge
C1211	Site Services	Gas Chromatography - Mass Spectrometer	Gas Chromatography - Mass Spectrometer	Below Threshold - Competitive Tender	Supplies	30/09/2025	17/02/2026	≥ £100k to <£500k		Hannah Budge
C26826	Site Services	Supply Ventilation (Design & Install)	Supply Ventilation (Design & Install)	Open (PA23)	Services	01/10/2025	31/01/2026	≥ £100k to <£500k		Fraser Bruce
C24497	Site Services	Decothane, Sika and Primer Liquid Plastic Paint	Decothane, Sika and Primer Liquid Plastic Paint	Below Threshold - 3 Quotes	Supplies	15/01/2026	06/03/2026	< £100k		Fraser Bruce
C1150	Site Services	Development of Individual Component Environmental Safety Cases	Development of Individual Component Environmental Safety Cases	Framework - Further Competition	Services	01/09/2025	28/05/2026	< £100k		Immi Smith
C18813	Site Services	Dionex Ion Chromatography System (Effluent Lab)	Dionex Ion Chromatography System (Effluent Lab)	Direct Award - Below Threshold	Supplies	30/09/2025	01/12/2025	< £100k		Hannah Budge
C26578	Site Services	Electronic Personal Dosemeter (EPD) calibrator	Electronic Personal Dosemeter (EPD) calibrator	Direct Award - Above Threshold - Competition Dispensed With	Supplies	05/08/2025	25/06/2025	≥ £100k to <£500k		Fraser Bruce
C26822	Site Services	Emergency Roofing Structural Assessment	Emergency Roofing Structural Assessment	Direct Award - Below Threshold	Services	21/07/2025	20/07/2026	< £100k		Fraser Bruce
C25999	Site Services	Floor Covering Dounreay Site	To supply/Fit and Repair various floor coverings on a ad-hoc basis on the NRS Dounreay Site.	Direct Award - Below Threshold	Works	10/07/2025	09/07/2027	≥ £100k to <£500k		Heidi Warner
C22433	Site Services	Ground nesting bird management services	Bird Hazzard Management Services & Vermin Management Services	Open Procedure	Services	01/01/2026	01/06/2031	≥ £500k to <£1m	3300024313	Heidi Warner
C24965	Site Services	Haulage of Salt	Haulage of Salt from Wick or / Scrabster Harbour to Dounreay Site (Offsite Hangar)	Below Threshold - 3 Quotes	Works	31/07/2025	30/07/2029	< £100k	3300032464	Immi Smith
C26572	Site Services	HP Instruments	HP Instruments	Open (PA23)	Supplies	01/09/2025	31/12/2025	≥ £100k to <£500k		Fraser Bruce
C14940	Site Services	Inspection of Dounreay Outfall 10 Diffuser	Inspection of Dounreay Outfall 10 Diffuser	Below Threshold - Competitive Tender	Services	01/04/2027	30/09/2030	≥ £100k to <£500k	C14929	Sarah McCaughey
C26269	Site Services	Lease of Refuse Wagon	Lease of Refuse Wagon	Below Threshold - Competitive Tender	Supplies	15/12/2026	14/12/2029	≥ £100k to <£500k	3300035293	Corrinda Pearson
C26270	Site Services	Lease of Skip Loader	Lease of Skip Loader	Below Threshold - Competitive Tender	Supplies	01/04/2027	31/03/2030	< £100k	3300035294	Corrinda Pearson
C23723	Site Services	Licence Condition 28 Inspections	This requirement is for inspections in accordance with Licence Condition 28.	Open Procedure	Services	01/08/2025	30/06/2028	≥ £500k to <£1m		Heidi Warner
C23351	Site Services	LINC Opportunity 29 - Flow Meter Calibration	This procurement is for the calibration of flow meters within the Non-Active Drain network and associated ad hoc support.	Below Threshold - Competitive Tender	Services	01/06/2026	01/06/2029	< £100k		Fraser Bruce
C1151	Site Services	Low Level Waste Pits - Review and development of the Environmental Safety Case	Low Level Waste Pits - Review and development of the Environmental Safety Case	Framework - Further Competition	Services	01/09/2025	31/08/2026	< £100k		Immi Smith
C21725	Site Services	Maintenance, Support & Development - Environment Sample Management System	Annual Maintenance, Support & Development of the Dounreay Environment Sample Management System	Open Procedure	Services	01/09/2025	31/08/2028	≥ £100k to <£500k	3300022841	Lynsey Will
C24578	Site Services	Manufacture of 1560 500 litre stainless steel drums	Manufacture and supply of approximately 1560 500 litre drums for the encapsulation of intermediate level waste. The drums to be delivered to Site on a just in time basis.	Open (PA23)	Supplies	19/04/2026	30/04/2030	≥ £1m to <£5m		Sonja Sinclair
C18812	Site Services	Portable X-Ray Radiography System	Portable X-Ray Radiography System	Below Threshold - Competitive Tender	Supplies	30/09/2025	30/11/2025	< £100k		Hannah Budge
C25016	Site Services	Provision of Chemical Collection Services	Provision of Chemical Collection Services	Below Threshold - Competitive Tender	Services	31/07/2025	31/07/2028	< £100k		Hannah Budge
C26038	Site Services	Provision of Electricity for Dounreay Main Site, Car Park - 2026/27	Provision of Electricity for Dounreay Main Site, Car Park - 2026/27	Framework - Further Competition	Services	01/04/2026	31/03/2027	≥ £5m to <£10m	3300046539	Corrinda Pearson
C26203	Site Services	Purchase of X-Ray Scanner	Purchase of X-Ray Scanner	Direct Award - Below Threshold	Supplies	14/07/2025	31/10/2025	< £100k		Corrinda Pearson
C25936	Site Services	Radiometric Non-Destructive Assay	The scope of this service includes the provision of measurement services using mobile NDA equipment directly in facilities at Dounreay, to quantify radionuclide contents and report the activity assessment of waste items, to enable their consignment.	Framework - Direct Award	Works	01/09/2025	31/12/2025	< £100k		Janet Brooke
C26320	Site Services	Replacement Gamma Bag Monitors for Non-Destructive Assay (NDA) Systems 36 and 45	Design, Manufacture, Installation and Commission of Replacement Gamma Bag Monitors for Non-Destructive Assay (NDA) Systems 36 and 45.	Below Threshold - Competitive Tender	Works	01/09/2025	31/03/2026	≥ £100k to <£500k		Janet Brooke
C25687	Site Services	Replacement of Two Stationary Automatic Water Samplers	Nuclear Restoration Services (NRS) Limited (Dounreay) required the design, supply, install and commission of two stationary automatic water samplers to replace the current obsolete samplers within Low Level Liquid Effluent Treatment Plant.	Direct Award - Below Threshold	Works	26/08/2025	28/11/2025	< £100k	C13981	Janet Brooke
C22054	Site Services	Reserved Procurement - Mild Steel Waste Cans	Under PPN 005 this procurement is being Reserved to the county of Caithness. This procurement is for the manufacture and supply of mild steel waste cans.	Below Threshold - Competitive Tender	Supplies	21/07/2025	17/11/2025	< £100k		Immi Smith
C23610	Site Services	Reserved Procurement - Provision of an Onsite Minibus Service	Reserved Procurement - Provision of an Onsite Minibus Service	Below Threshold - Competitive Tender	Services	01/04/2026	31/03/2028	≥ £100k to <£500k	3300031691	Corrinda Pearson
C24456	Site Services	Reserved Procurement - Stainless Steel Drums with Gaitor Attachment	This procurement is for the manufacture, inspection, testing and delivery of 200 litre stainless steel waste drums with a gaitor attachment. Under PPN 005 this procurement is being Reserved to the county of Caithness.	Below Threshold - Competitive Tender	Supplies	01/08/2025	28/11/2025	≥ £100k to <£500k		Immi Smith
C25241	Site Services	Reserved Procurement - Supply and Delivery of Assorted Quarry Materials	In accordance with PPN005, this procurement is being reserved to the county of Caithness. The procurement is for the supply and delivery to the Dounreay Site of a range of quarry materials including, aggregate, sand, concrete and concrete blocks.	Below Threshold - Competitive Tender	Supplies	14/08/2025	12/08/2027	≥ £100k to <£500k	3300031879	Heidi Warner
C23545	Site Services	Routine servicing/maintenance of Laboratory Equipment	Routine servicing/maintenance of Laboratory Equipment	Below Threshold - 3 Quotes	Services	01/02/2026	31/01/2030	≥ £100k to <£500k	3300033178	Immi Smith
C26830	Site Services	Safety Case Engineer - Engineer Substantiation Report	C26830 - Safety Case Engineer - Engineer Substantiation Report	Direct Award - Below Threshold	Services	18/08/2025	07/12/2026	< £100k		Fraser Bruce
C26831	Site Services	Saws & Extraction System	Saws & Extraction System	Direct Award - Below Threshold	Supplies	01/09/2025	31/12/2026	< £100k		Fraser Bruce
C23104	Site Services	Scaffolding Services Framework (inc Asbestos Licensed Works) 2026/30	Scaffolding Services Framework (including Asbestos Licensed works) 2026/30	Framework Agreement – Set up of a new Framework	Services	02/03/2026	28/02/2030	≥ £1m to <£5m	CFA/22/0004	Janet Brooke
C1157	Site Services	Servicing and Maintenance of Air Compressor Equipment at NRS Limited (Dounreay)	Servicing and Maintenance of Air Compressor Equipment at Nuclear Restoration Services Limited (Dounreay)	Open Procedure	Services	31/07/2025	28/07/2028	≥ £100k to <£500k	3300040385, 3300032756	Immi Smith
C1149	Site Services	Site Closure and Environmental Restoration - Peer Review	Site Closure and Environmental Restoration - Peer Review	Framework - Further Competition	Services	01/09/2025	04/05/2026	< £100k		Immi Smith
C26317	Site Services	Supply and Delivery of a new 8-tonne capacity Forklift Truck	Nuclear Restoration Services (NRS) Limited (Dounreay) have a requirement for the supply of delivery of a new 8-tonne capacity Forklift Truck.	Below Threshold - 3 Quotes	Supplies	21/07/2025	29/08/2025	< £100k		Janet Brooke
C18809	Site Services	Supply of Cryocooler	Supply of Cryocooler	Direct Award - Below Threshold	Supplies	06/10/2025	02/03/2026	< £100k		Hannah Budge
C18814	Site Services	Supply of Easycount System	Supply of Easycount System	Direct Award - Below Threshold	Supplies	30/09/2025	31/01/2026	≥ £100k to <£500k		Hannah Budge
C21802	Site Services	Supply of Flask Trailer	Supply of Flask Trailer	Below Threshold - Competitive Tender	Services	01/09/2025	27/02/2026	≥ £100k to <£500k		Janet Brooke
C23612	Site Services	Supply of Medium Fuel Oil, Gas Oil, Kerosene and Road Diesel for Dounreay Site	Supply of Medium Fuel Oil, Gas Oil, Kerosene and Road Diesel for Dounreay Site	Framework - Further Competition	Supplies	01/04/2026	31/03/2029	≥ £5m to <£10m	3300039529	Corrinda Pearson
C21856	Site Services	Supply of Road Salt 2025-2029	Supply of Road Salt	Direct Award - PCR Single Source (Reg 32)	Supplies	31/07/2025	30/07/2029	≥ £100k to <£500k	3300041524	Fraser Bruce
C22782	Site Services	UPS Service & Repair and Battery Replacements	UPS Service & Repair and Battery Replacements	Open Procedure	Services	01/09/2025	31/08/2028	≥ £100k to <£500k	3300017815	Corrinda Pearson
C1113	Site Services	Voidage and Container Assessments	Voidage and Container Assessments	Framework - Further Competition	Services	01/12/2025	30/09/2026	≥ £100k to <£500k		Janet Brooke