## External Plan Format
NRS Procurement Plan as at end of November 2025
1
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PIN or PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded | REMOVE
C10070 | Ops & Enablers | Enablers/Not Location Specific | Occupational Health Services 25 onwards | Support Services | Amy.Vale@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-05-10 | (a) | 2025-10-07 | (a) | Optima Health Group
C10684 | Ops & Enablers | Enablers/Not Location Specific | Calibration and Maintenance of Radiological Instruments - Installed | Engineering | caroline.j.milner@nrservices.uk | PA23 Open | £5m to £10m | n/a | 2026-07-14 | (f) | 2027-03-11 | (f) | Not yet confirmed
C13780 | Ops & Enablers | Enablers/Not Location Specific | Provision of a Managed Learning Service 26+ | Support Services | holly.griffith@nrservices.uk | PA23 Open | £5m to £10m | n/a | 2026-02-04 | (f) | 2026-10-12 | (f) | Not yet confirmed
C14315 | Ops & Enablers | Enablers/Not Location Specific | Project Controls & Commercial Services (2026+) | Design services/support | michelle.a.edwards@nrservices.uk | Mini Competition F/W | £50m to £100m | n/a | 2026-07-14 | (f) | 2027-07-09 | (f) | Not yet confirmed
C14462 | Ops & Enablers | Enablers/Not Location Specific | Videoconferencing Support - 2026 | IT hardware/software | jayne.chalmers@nrservices.uk | Direct Award F/W | £1m to £5m | n/a | 2025-11-06 | (a) | 2026-02-04 | (f) | Not yet confirmed
C17087 | Ops & Enablers | Enablers/Not Location Specific | Supply of Metrology Instruments (Installed and Portable) | Engineering | caroline.j.milner@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | Dynamic Purchasing System ('DPS') now open for supplier registration and pre-qualification
C17387 | Ops & Enablers | Bradwell; Dungeness; Sizewell | Civils Support DPS - South East Region | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C17421 | Ops & Enablers | Dounreay; Enablers/Not Location Specific | Workplace Services 2027 | Maintenance | steven.j.lock@nrservices.uk | CCS F/W Call off | £250m plus | n/a | 2025-04-10 | (a) | 2025-11-06 | (a) | Tend: EQUANS Services Limited,CBRE Managed Services Limited,EMCOR Group (UK) PLC,Amey Consulting,MITIE FM LIMITED,OCS Group UK Limited,G4S FACILITIES MANAGEMENT (UK) LIMITED,ISS Mediclean Limited
C17423 | Ops & Enablers | Enablers/Not Location Specific | Enterprise Asset Management (EAM) - System | IT hardware/software | james.hiller@nrservices.uk | PA23 Competitive Flexible | £10m to £25m | n/a | 2025-07-09 | (a) | 2026-07-14 | (f) | Not yet confirmed
C17426 | Ops & Enablers | Enablers/Not Location Specific | Enterprise Asset Management (EAM) - Data Management | Manpower | james.hiller@nrservices.uk | Mini Competition F/W | £25m to £50m | n/a | 2026-08-13 | (f) | 2027-04-10 | (f) | Not yet confirmed
C19489 | Ops & Enablers | Enablers/Not Location Specific | PM&BA and TDA 2026 (Procurement) | IT hardware/software | jonathan.harris@nrservices.uk | CCS F/W Call off | £10m to £25m | n/a | 2026-05-05 | (f) | 2027-01-10 | (f) | Not yet confirmed
C19614 | Ops & Enablers | Enablers/Not Location Specific | Calibration and Maintenance of Radiological Instruments - Portable | Engineering | caroline.j.milner@nrservices.uk | PA23 Open | £5m to £10m | n/a | 2026-07-14 | (f) | 2027-03-11 | (f) | Not yet confirmed
C19724 | Ops & Enablers | Enablers/Not Location Specific | Asbestos Analytical Services 2025 | Design services/support | Shelley.Lawrence@nrservices.uk | DPS Call-Off | £50m to £100m | n/a | 2026-02-04 | (f) | 2026-08-13 | (f) | Not yet confirmed
C19793 | Ops & Enablers | Chapelcross; Hunterston | Civils Support DPS (Scottish Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C20416 | Waste | Enablers/Not Location Specific | Characterisation Services | Design services/support | Liz.Gilbert@nrservices.uk | New Framework set up | £10m to £25m | 2025-02-22 | 2025-12-06 | (f) | 2026-03-06 | (f) | Not yet confirmed
C20508 | Ops & Enablers | Berkeley; Hinkley; Oldbury | Civils Support DPS (South West Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C20831 | Ops & Enablers | Maentwrog; Trawsfynydd; Wylfa | Civils Support DPS (Welsh Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C21428 | Ops & Enablers | Enablers/Not Location Specific | Supply of Air Filter & Ancilary Equipement 2026-2030 | Consumables | sion.apglyn@nrservices.uk | New Framework set up | £1m to £5m | n/a | 2025-10-07 | (a) | 2026-05-05 | (f) | Not yet confirmed
C21822 | Ops & Enablers | Harwell; Winfrith | Civils Support DPS - South Region - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £1m to £5m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C21842 | Ops & Enablers | Enablers/Not Location Specific | Project Controls & Commercial Services Bridging Contract | Design services/support | michelle.a.edwards@nrservices.uk | Direct Award F/W | £10m to £25m | n/a | 2025-07-09 | (a) | 2025-12-06 | (f) | Not yet confirmed
C24019 | Ops & Enablers | Oldbury | Radios - Oldbury | Maintenance | Kwadwo.Awuku@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-08-08 | (a) | 2025-11-06 | (a) | Tend: Thales UK Limited,Radiocoms Systems Limited,Trellisware Technologies, Inc.,Steatite Limited,L3Harris Communications Systems UK Limited,General Dynamics United Kingdom Limited,Elbit Systems UK Limited,Domo Tactical Communications (DTC) Limited,C3iA Solutions Limited,Blacktree Technologies Limited,BAE Systems (Operations) Limited
C24146 | Waste | Berkeley | 2 Forklifts 5 year hire for Berkeley site | Support Services | louise.waldron@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-08-08 | (a) | 2025-10-07 | (a) | Aprolis UK Ltd (trading as Impact Handling)
C24227 | Ops & Enablers | Enablers/Not Location Specific | Pension Trustee Services | Manpower | gissela.m.hughes@nrservices.uk | PA23 Competitive Flexible | £500k to £1m | n/a | 2026-01-05 | (f) | 2026-08-13 | (f) | Not yet confirmed
C24235 | Ops & Enablers | Berkeley; Bradwell; Chapelcross; Dungeness; Harwell; Hinkley; Hunterston; Oldbury; Sizewell; Trawsfynydd; Winfrith; Wylfa | Category 2 - Health Physics Monitoring Resource | Design services/support | emma.gordon@nrservices.uk | DPS Call-Off | £25m to £50m | n/a | 2026-02-04 | (f) | 2026-10-12 | (f) | Not yet confirmed
C24237 | Ops & Enablers | Berkeley; Bradwell; Carlisle; Chapelcross; Crewe; Dounreay; Dungeness; Harwell; Hinkley; Hunterston; Oldbury; Preston; Sizewell; Trawsfynydd; Winfrith; Wylfa | Security Personnel Services 2027 | Support Services | steven.j.lock@nrservices.uk | CCS F/W Call off | £50m to £100m | n/a | 2026-06-04 | (f) | 2027-03-11 | (f) | Not yet confirmed
C24391 | Waste | Chapelcross | Special Waste Management – Provisions of Containers, Carriage and Disposal of No | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2025-12-06 | (f) | 2026-05-05 | (f) | Not yet confirmed
C24971 | Decommissioning | Berkeley | Berkeley Blower Houses Interim Safe State | Engineering | david.m.sanderson@nrservices.uk | Direct Award F/W | £1m to £5m | n/a | 2025-08-08 | (a) | 2026-03-06 | (f) | Tend: Altrad Support Services Limited
C25013 | Ops & Enablers | Enablers/Not Location Specific | Legal Advice Services July 25 - Nov 27 | Support Services | gissela.m.hughes@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-05-10 | (a) | 2025-11-06 | (a) | Addleshaw Goddard LLP, Burges Salmon LLP, DWF Law LLP, DAC Beachcroft LLP, Gowling WLG (UK) LLP, TLT LLP
C25144 | Decommissioning | Trawsfynydd | Sampling & Analysis Characterisation | Construction | Shelley.Lawrence@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2026-03-06 | (f) | 2026-11-11 | (f) | Not yet confirmed
C25464 | Ops & Enablers | Hinkley | HPA RCA Welfare Facility | Construction | louise.x.brown@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2025-10-07 | (a) | 2026-01-05 | (f) | Tend: More than 10
C25602 | Decommissioning | Enablers/Not Location Specific | Ground Water Monitoring Services 2025-2028 | Support Services | lindsay.gibson@nrservices.uk | Mini Competition F/W | £1m to £5m | n/a | 2025-06-09 | (a) | 2025-09-07 | (a) | Arcadis Consulting (UK) Limited
C25638 | Decommissioning | Harwell | BEPO Characterisation DQO / Sampling Plan | Design services/support | Shelley.Lawrence@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2026-02-04 | (f) | 2026-07-14 | (f) | Not yet confirmed
C25644 | Decommissioning | Harwell | BEPO Welfare Facilities | Plant & Equipment & Materials | Shelley.Lawrence@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2027-02-09 | (f) | 2027-05-10 | (f) | Not yet confirmed
C25654 | Decommissioning | Maentwrog | Maentwrog Estate Management 2025 - 2029 | Support Services | lindsay.gibson@nrservices.uk | PA23 Open | £100k to £500k | n/a | 2025-09-07 | (a) | 2025-11-06 | (a) | Tend: Savills (UK) Ltd,O B R Construction,D&C Jones Co Ltd,John Roberts (ffestiniog) Ltd,Avison Young (UK) Limited,Montagu Evans LLP,T.D. Plant Hire and Haulage Ltd,NATIONAL INFRASTRUCTURE SOLUTIONS LTD,Cartwright Associates,NURTURE LANDSCAPES LIMITED
C25655 | Decommissioning | Maentwrog | Maentwrog Outage Welding Support 2026-2030 | Construction | lindsay.gibson@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2026-03-06 | (f) | 2026-06-04 | (f) | Not yet confirmed
C25807 | Ops & Enablers | Berkeley | Berkeley Site Services Building | Construction | ben.bilton@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-06-09 | (a) | 2025-11-06 | (a) | Premierseal Ltd
C26111 | Ops & Enablers | Hunterston | BATS 074 Inspection of Stack and Ducts | Design services/support | Kwadwo.Awuku@nrservices.uk | PA23 Open | £100k to £500k | n/a | 2025-06-09 | (a) | 2025-12-06 | (f) | Not yet confirmed
C26368 | Decommissioning | Dungeness | Dungeness A: Replace Surface Drains Pumps 1&3 | Construction | danyal.nawaz@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-11-06 | (a) | 2026-01-05 | (f) | Tend: More than 10
C26579 | Waste | Hunterston | DESIGN, MANUFACTURE & OVERSIGHT THE INSTALLATION OF TWO LARGE ITEM BAG MONITORS | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-07-09 | (a) | 2025-10-07 | (a) | Mirion Technologies (Canberra UK) Ltd
C26596 | Waste | Berkeley; Oldbury | Low Level Waste Assay System at Berkeley & Oldbury Site | Engineering | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2025-07-09 | (a) | 2025-10-07 | (a) | Mirion Technologies (Canberra UK) Ltd
C26824 | Ops & Enablers | Sizewell | Sizewell A Reactor Building Structural Investigations | Construction | adrian.h.williams@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-08-08 | (a) | 2025-10-07 | (a) | Central Roofing and Building Services Ltd
C27067 | Ops & Enablers | Hinkley | HPA Clean Waste Building Roof Refurbishment | Construction | louise.x.brown@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2025-09-07 | (a) | 2025-11-06 | (a) | Tend: More than 10
C27212 | Decommissioning | Chapelcross | Chapelcross Electrical Overlay 5MVA Transformer No.2 Replacement | Engineering | mark.taylor2@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2025-12-06 | (f) | 2026-01-05 | (f) | Tend: Brush Transformers Ltd,Slaters Electricals Ltd,Rosh Engineering Ltd
C27308 | Decommissioning | Chapelcross | Chapelcross Sub-station Overbuild | Design services/support | mark.taylor2@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-09-07 | (a) | 2026-01-05 | (f) | Tend: More than 10
C27309 | Ops & Enablers | Chapelcross | Chapelcross Roof Repairs | Construction | mark.taylor2@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2025-12-06 | (f) | 2026-01-05 | (f) | Not yet confirmed
C27319 | Ops & Enablers | Enablers/Not Location Specific | Managed services provision for contingent labour | Manpower | alwena.owen@nrservices.uk | Mini Competition F/W | £1m to £5m | n/a | 2025-09-07 | (a) | 2025-11-06 | (a) | Tend: Morson Human Resources Limited t/a Morson Talent
C27337 | Decommissioning | Winfrith | CCTV Modifications, Dragon | Maintenance | janet.smith@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-06-09 | (a) | 2025-09-07 | (a) | Evolution (Electronic Security Systems) Ltd
C27411 | Ops & Enablers | Oldbury | Oldbury - Design & Build of Auto-SAS Facility | Construction | claire.scott@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2025-09-07 | (a) | 2025-12-06 | (f) | Tend: More than 10
C27447 | Decommissioning | Sizewell | Commissioning support Two men X 6 weeks | Design services/support | julie.a.jones@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-09-07 | (a) | 2025-09-07 | (a) | STP Fabrication LTD
C27528 | Decommissioning | Harwell | Specialist Waste Removal (B418) | Engineering | Shelley.Lawrence@nrservices.uk | Mini Competition F/W | £1m to £5m | n/a | 2025-12-06 | (f) | 2026-03-06 | (f) | Not yet confirmed
C27583 | Waste | Oldbury | Gamma Clearance Monitors at Oldbury Nuclear Power Station | Engineering | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-09-07 | (a) | 2025-11-06 | (a) | Tend: Mirion Technologies (Canberra UK) Ltd,Nuvia Limited,Southern Scientific Ltd,Thermo FIsher Scientific Messtechnik GmbH,Ludlum Systems Ltd,High Technology Sources Limited,Advanced Measurement Technology (Ametek)
C5672 | Decommissioning | Sizewell | Install Modify Vent - Splitter Vane Store (SVS) | Construction | sarah.j.deeble@nrservices.uk | Non-FTS Competition | <£100K | 2026-02-01 | 2026-04-05 | (f) | 2026-06-04 | (f) | Not yet confirmed
C5678 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@nrservices.uk | PA23 Competitive Flexible | £1m to £5m | n/a | 2026-08-13 | (f) | 2027-02-09 | (f) | Not yet confirmed
C5690 | Decommissioning | Trawsfynydd | Reactor Buildings Height Reduction (EXECUTION phase) | Decommissioning, Demolition & Deplant | fiona.pearse@nrservices.uk | FTS Comp Proc with Negotiation | £50m to £100m | 2022-12-06 | 2023-10-08 | (a) | 2025-10-07 | (a) | Costain Limited
C5693 | Decommissioning | Dungeness | Dismantle A Frame Crane & Remove Skip Mast | Decommissioning, Demolition & Deplant | david.m.sanderson@nrservices.uk | PA23 Open | <£100K | n/a | 2026-04-05 | (f) | 2026-08-13 | (f) | Not yet confirmed
C5824 | Ops & Enablers | Enablers/Not Location Specific | Statutory Examination Services 2026+ | Design services/support | caroline.j.milner@nrservices.uk | PA23 Open | £10m to £25m | n/a | 2025-12-06 | (f) | 2026-08-13 | (f) | Not yet confirmed
C8950 | Decommissioning | Dungeness | Package 1 Demolition, Boiler & ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@nrservices.uk | FTS Comp Proc with Negotiation | £50m to £100m | 2023-02-07 | 2023-06-10 | (a) | 2026-10-12 | (f) | Not yet confirmed
C9092 | Decommissioning | Oldbury | Oldbury Site Turbine Hall & Non RCA (South Clearance) | Decommissioning, Demolition & Deplant | danielle.staples@nrservices.uk | Mini Competition F/W | £25m to £50m | n/a | 2025-11-06 | (a) | 2026-11-11 | (f) | Not yet confirmed
C9924 | Decommissioning | Harwell | LETP Land Re-instatement & SUDS system (Package 8b) | Construction | paul.phillips@nrservices.uk | PA23 Open | £1m to £5m | n/a | 2025-06-09 | (a) | 2025-09-07 | (a) | Jones Bros Ruthin (Civ Eng) Co.Ltd
C24504 | Decommissioning | Dungeness | Dungeness Boilers Principal Designer | Design services/support | nicola.j.smith-lee@nrservices.uk | PA23 Open | £500k to £1m | n/a | 2025-12-06 | (f) | 2026-05-05 | (f) | Not yet confirmed
C24805 | Waste | Hinkley | Supply of 3m Boxes and connections for Hinkley | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2025-10-07 | (a) | 2026-02-04 | (f) | Tend: More than 10
C27684 | Waste | Hinkley | Teletruck and MEWP 5 year hire for HPA | Support Services | paul.phillips@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-10-07 | (a) | 2026-01-05 | (f) | Not yet confirmed
C27718 | Decommissioning | Winfrith | ALES - Sea Tanks Design and Fabrication of 2 No. Staircases | Construction | janet.smith@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-10-07 | (a) | 2025-10-07 | (a) | Mortec Welding LTD
C27830 | Waste | Chapelcross | LC28 Repairs to include Road & Pathway Improvements | Construction | mark.taylor2@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2025-11-01 | (a) | 2026-02-04 | (f) | Not yet confirmed
C27832 | Decommissioning | Winfrith | Mini MILWEP - Concrete Floor Slab Rectification | Construction | rachael.sheriff@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-10-07 | (a) | 2025-12-06 | (f) | Not yet confirmed
C27867 | Decommissioning | Winfrith | Design Engineering Support - EC&I Control Systems | Design services/support | chris.dorain@nrservices.uk | Other - No Competition | £500k to £1m | n/a | 2025-10-07 | (a) | 2026-01-05 | (f) | Not yet confirmed
C27873 | Decommissioning | Winfrith | SGHWR Design Engineering Support - Mechnical Engineer | Design services/support | chris.dorain@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2025-11-06 | (a) | 2026-02-04 | (f) | Not yet confirmed
C27906 | Waste | Sizewell | Sizewell A Electrical installation for Southern Welfare Cabins | Construction | danyal.nawaz@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-11-06 | (a) | 2026-02-04 | (f) | Tend: More than 10
C27913 | Ops & Enablers | Enablers/Not Location Specific | Asbestos Analytical Services 2025 - PIN | Design services/support | Shelley.Lawrence@nrservices.uk | Market Engagement | £50m to £100m | 2025-10-30 | n/a |  | n/a |  | n/a
C28015 | Waste | Berkeley | Roof Repairs at Berkeley Site | Construction | liv.kelly@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2026-01-05 | (f) | 2026-04-05 | (f) | Not yet confirmed
C28050 | Decommissioning | Winfrith | SGHWR - CS&A Support | Design services/support | chris.dorain@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2026-01-05 | (f) | 2026-07-14 | (f) | Not yet confirmed
C28051 | Decommissioning | Winfrith | SGHWR Safety Case Support | Design services/support | chris.dorain@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2026-01-05 | (f) | 2026-07-14 | (f) | Not yet confirmed
C28079 | Ops & Enablers | Enablers/Not Location Specific | PIN Statutory Examination Services 2026+ | Design services/support | caroline.j.milner@nrservices.uk | PA23 Open | £10m to £25m | 2025-10-23 | n/a | (a) | n/a | (a) | n/a
C28086 | Waste | Chapelcross; Hinkley | MILWEP Maintenance and Breakdown Support | Design services/support | pauline.z.mackemsley@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2025-10-07 | (a) | 2025-12-06 | (f) | Not yet confirmed
C28149 | Waste | Winfrith | Supply Practicon C-Pak+ Concrete Batching System. | Design services/support | rachael.sheriff@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-11-06 | (a) | 2026-09-12 | (f) | Not yet confirmed
C28252 | Waste | Oldbury | Oldbury Weir Chamber Remediation | Design services/support | ben.bilton@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2025-11-06 | (a) | 2026-04-05 | (f) | Not yet confirmed
C28255 | Waste | Enablers/Not Location Specific | Pension secretarial services | Support Services | alwena.owen@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2026-08-13 | (f) | 2027-05-10 | (f) | Not yet confirmed
C28256 | Waste | Enablers/Not Location Specific | Pension administration - ESPS | Support Services | alwena.owen@nrservices.uk | Other - No Competition | £1m to £5m | n/a | 2026-09-12 | (f) | 2027-06-09 | (f) | Not yet confirmed
C28332 | Waste | Winfrith | Crane - Electrical Upgrade - Market Engagement | Engineering | chris.dorain@nrservices.uk | Market Engagement | £500k to £1m | 2025-11-13 | n/a |  | n/a |  | n/a
C28469 | Waste | Berkeley | RMS Modifications - Berkeley | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | Direct Award - Below Threshold | £100k to £500k | n/a | 2025-11-06 | (a) | 2025-12-06 | (f) | Not yet confirmed
zz | zz | zz | zz | zz | zz | zz | zz | zz | zz | zz | zz | zz | zz