## EXTERNAL ISSUE
PPP Reqmnt | X | X | X | X | X | X | X | X | X | X | X | X
Annex Reqmnt |  |  | X | X | X | X |  |  |  | X | X
PLEASE NOTE THIS PROCUREMENT PLAN IS TAKEN AS A SNAPSHOT IN TIME AND THEREFORE IS SUBJECT TO CHANGE
| MPP Reference (If Applicable) | Project | Procuring Partner | Project Scope / Trade Packs Description | Basis of competition | Quality / Technical Risk | Contract Type | Outline Business Case Estimated Value £ | EPMS Advert Date | ITT Release Date | Contract Award Date | Successful Contractor
| n/a | SCP | Doosan Babcock | Bulk Excavation / Earth works - (-1m to level) Phase 3 | OSW | Low | NEC -C | 2700000 | Complete | complete | complete | OSW
| N/A - placed | SCP | Doosan Babcock | Main Civils FRC | Competitive Tender | Medium | NEC -C | 20300000 | Complete | complete | 2020-09-14 | Careys Civil Engineering
| N/A - placed | SCP | Doosan Babcock | Primary Steelwork | Competitive Tender | Medium | NEC- A&C | 13000000 | Complete | complete | TBC (fc Jan 21) | Harry Peers
| GSA 5 | SCP | Doosan Babcock | Contractors Village | Competitive Tender | Low | NEC-A | 900000 | 2021-03-01 | 2021-06-01 | 2021-09-01 | TBC
| GSA 4 | SCP | Doosan Babcock | Building Lifts | MPP | Medium | NEC-A | 700000 | Complete | 2022-06-01 | 2022-10-01 | TBC
| N/A - placed | SCP | Doosan Babcock | Construction Cranes Erection | Competitive Tender | Medium | NEC-A | 2400000 | Complete | complete | 2020-06-03 | Liebherr
| N/A - placed | SCP | Doosan Babcock | Construction Cranes Operation | Competitive Tender | Low | NEC-A | 1400000 | Complete | complete | 2020-12-02 | Mammeot
| KDP 9 / KDP 6 | SCP | Doosan Babcock | Civils Finishing | MPP | Low | NEC-A | 4400000 | 2021-06-01 | 2021-08-01 | TBC | TBC
| N/A - placed | SCP | Doosan Babcock | Construction Crane Piling | Competitive Tender | Low | NEC - A |  | Complete | complete | 2020-09-16 | Volker Ground Engineering
| TBC | SCP | Doosan Babcock | Alimaks x2 |  | Low | TBC |  | TBC | TBC | 2022-03-01 | TBC
| N/A - placed | SCP | Doosan Babcock | E&I Enabling and Temporary Power Supplies | Competitive Tender | Low | NEC-A |  | Complete | complete | 2020-08-10 | PPS Electrical Ltd
| KDP 4 | SCP | Doosan Babcock | Electrical Installation | MPP | Low | TBC | 22200000 | 2021-06-01 | 2021-08-01 | 2022-02-01 | TBC
| KDP 4 | SCP | Doosan Babcock | Electrical Equipment | MPP | Low | TBC | as above | 2021-06-01 | 2021-08-01 | 2022-02-01 | TBC
| KDP 4 | SCP | Doosan Babcock | Instrumentation | MPP | Low | TBC | as above | 2021-06-01 | 2021-08-01 | 2022-02-01 | TBC
| N/A - placed | SCP | Doosan Babcock | Encast Items (Wall & Floor Boxes, Liners, Sumps, Plugs) -4m | Competitive Tender | Medium | NEC - SUPPLY | 800000 | Complete | complete | 2020-02-07 | West Cumberland Engineering Ltd
| N/A - placed | SCP | Doosan Babcock | Encast Items (Wall & Floor Boxes, Liners, Sumps, Plugs) +8m | Competitive Tender | Medium | NEC - SUPPLY | 3400000 | Complete | complete | 2020-12-02 | West Cumberland Engineering Ltd
| GSA 1 | SCP | Doosan Babcock | Encast Items (Plugs) | MPP | Medium | NEC - SUPPLY | 200000 | 2022-12-01 | 2023-02-01 | 2023-06-01 | TBC
| N/A - placed | SCP | Doosan Babcock | T1 Alternative Valves (Design, PROTOTYPE manufacture & Test) AZ ARMATUREN | Competitive Tender | Medium | NEC - SUPPLY | 1700000 | Complete | complete | 2019-12-11 | AZ Armaturen
| N/A - placed | SCP | Doosan Babcock | T1 Alternative Valves (Design, PROTOTYPE manufacture & Test) HAYWARD TYLER | Competitive Tender | Medium | NEC - SUPPLY | 1700000 | Complete | complete | 2020-06-29 | Hayward Tyler Fluid Handling Ltd
| GSA 1 | SCP | Doosan Babcock | Material Handling Equipment (FLT,PPT,PT) | MPP | Medium | NEC - SUPPLY | 100000 | 2021-03-01 | 2021-06-01 | 2021-11-01 | TBC
| GSA 1 | SCP | Doosan Babcock | Process Cabinets(incl Pressure Transducer Cabinets) | MPP | Medium | NEC - SUPPLY | 3200000 | 2021-03-01 | 2021-06-01 | 2021-11-01 | TBC
| N/A - SSJ | SCP | Doosan Babcock | Pumps (Hayward Tyler) |  | Medium | NEC - SUPPLY | 2100000 | Complete | complete | TBC (fc Mar 21) | Hayward Tyler Fluid Handling Ltd
| N/A - Cat Man | SCP | Doosan Babcock | Control Systems (inc SIXEP Control System) | Category Management | Low | SL BESPOKE | 3600000 | 2021-04-01 | 2021-05-01 | 2021-10-01 | JACOBS
| KDP 5 | SCP | Doosan Babcock | Interconnecting Pipework and pipe bridge sumps (East &West Pipe bridge) | MPP | Medium | NEC - SUPPLY | 7200000 | 2021-01-01 | 2022-03-01 | 2022-09-01 | TBC
| Specialist | SCP | Doosan Babcock | Steam & Air Ejectors | Competitive Tender | Medium | NEC - SUPPLY | 300000 | 2021-08-01 | 2021-10-01 | 2022-03-03 | TBC
| KDP 5 | SCP | Doosan Babcock | Pipework (Fabrication only) | MPP | Medium | NEC - SUPPLY | inc | 2022-01-01 | 2022-03-01 | 2022-09-14 | TBC
| Remove | SCP | Doosan Babcock | Misc. Balance of Plant (Mech | Competitive Tender | Medium | NEC - SUPPLY | 7600000 | 2020-12-01 | 2021-02-01 | 2021-07-01 | TBC
| KDP 5 | SCP | Doosan Babcock | SIXEP Tie in's | MPP | Medium | NEC - SUPPLY | 2700000 | 2021-07-01 | 2021-09-01 | 2022-03-04 | TBC
| GSA 1 | SCP | Doosan Babcock | Pump & Valve Modules | MPP | Medium | NEC - SUPPLY | 4800000 | 2021-03-01 | 2021-06-01 | 2021-11-01 | TBC
| GSA 1 | SCP | Doosan Babcock | Flask Transfer Bogie & existing Plant items | MPP | Medium | NEC - SUPPLY | 400000 | 2021-10-01 | 2021-12-01 | 2022-06-14 | TBC
| GSA 1 | SCP | Doosan Babcock | Flask Transfer Rails | MPP | Low | TBC | as above | 2021-03-01 | 2021-06-01 | 2021-11-01 | TBC
| N/A - Cat Man | SCP | Doosan Babcock | LoF / UoF Crane (Category Management) | Category Management | Medium | SL BESPOKE | 5300000 | Complete | complete | 2020-03-10 | Taim Weser
| N/A - placed | SCP | Doosan Babcock | Tanks & Vessels - Free issue Primary Steelwork (CAT MAN - Langfields) | Category Management | Medium | SL BESPOKE | 1000000 | Complete | complete | 2020-10-28 | Langfields
| N/A - placed | SCP | Doosan Babcock | Tanks & Vessels - UV Vessels (x7) (CAT MAN - Bendalls) | Category Management | Medium | SL BESPOKE | 2000000 | Complete | complete | 2020-09-10 | Bendalls Engineering
| N/A - placed | SCP | Doosan Babcock | Tanks & Vessels x4 - On Site Build (CAT MAN - Langfields) | Category Management | Medium | SL BESPOKE | 2400000 | Complete | complete | 2020-10-01 | Langfields
| N/A - placed | SCP | Doosan Babcock | Tanks & Vessels x16 Remaining Phase 1 (CAT MAN - WCEL) | Category Management | Medium | SL BESPOKE | 500000 | Complete | complete | 2020-09-17 | West Cumberland Engineering Ltd
| N/A - Cat Man | SCP | Doosan Babcock | Tanks & Vessels x28 - Phase 2 (CAT MAN) | Category Management | Medium | SL BESPOKE | 400000 | Complete | complete | 2021-04-29 | Langfields / Bendalls / WCEL
| KDP 12 | SCP | Doosan Babcock | Mech Plant Installation Subcontract | MPP | Medium | NEC - C | 1500000 | 2021-08-01 | 2021-10-01 | 2022-05-05 | TBC
| N/A - current competitive tender | SCP | Doosan Babcock | BST’s on site build (install F9.3 scope) | Category Management | Medium | SL BESPOKE | 800000 | 2021-01-01 | 2021-03-01 | 2021-08-01 | TBC
| KDP5 | SCP | Doosan Babcock | Pipework & Supports Install Subcontract | MPP | Medium | NEC- A / C | 12700000 | 2022-03-01 | 2022-05-01 | 2022-09-14 | TBC
| KDP 3 | SCP | Doosan Babcock | Ventilation / HVAC (Mechanical) | MPP | Medium | NEC-C | 7800000 | Complete | 2021-04-08 | 2021-10-28 | TBC
| 0 | SCP | Sellafield | Site Investigation Works | SL - Call Offs | Low | SL FRAMEWORK - MDSW | tbc | complete | complete | 2016-05-01 | MDSW
| 0 | SCP | Sellafield | Refurbishment of CO947 | SL - Call Offs | Low | SL FRAMEWORK - OneFM | tbc | complete | complete | 2019-11-01 | OneFM
| 0 | SCP | Sellafield | Site Preperation - Substation | SL - Call Offs | Low | SL FRAMEWORK - ISA | tbc | complete | complete | 2017-07-01 | Morgan Sindall
| 0 | SCP | Sellafield | Preliminary to Design for Manufacture | SL - Call Offs | Low | DSA / NEC PSC | tbc | complete | complete | 2015-05-01 | AXIOM
| KDP 7 | SCP | Doosan Babcock | Scaffolding, Insualtion & Painting | MPP | Low | NEC-A | 5600000 | 2021-04-01 | 2021-06-01 | 2021-11-01 | TBC
| N/A - site procuremetnt | SCP | Doosan Babcock | Site Access Controls and Fencing | Competitive Tender | Low | NEC -C | 2400000 | TBC | TBC | TBC | TBC
| KDP 12 | SCP | Doosan Babcock | Specialist Contract Lifting | MPP | Low | NEC-A | 300000 | TBC | TBC | TBC | TBC
| N/A | RAP | Jacobs | Ongoing design support for detailled design | Complete | tbc | Framework Contract | 5300000 | complete | complete | 2020-09-30 | Mott Macdonald
| N/A | RAP | Jacobs | Ongoing design support for detailled design | Complete | tbc | Framework Contract | 3300000 | complete | complete | 2020-09-30 | Assystem
| N/A | Multiple | Jacobs | Mechanical Engineering Services (inc. Finite Element Analysis & Glovebox design, alpha skills) | Competitive Tender | tbc | NEC PSC | tbc |  | 2021-06-01 | 2021-09-01
| N/A | Multiple | Jacobs | EC&I Engineering Services (inc. HV Electrical, Smart instruments, PLC/SCADA, Radiometrics/Nucleonic, Loss of Grid/Resilience & Earthing) | Competitive Tender | tbc | NEC PSC | tbc |  | 2021-06-01 | 2021-09-01
| N/A | Multiple | Jacobs | Structural Integrity Services (inc.Topographical Survey, Seismic Analysis & Substantiation) | Competitive Tender | tbc | NEC PSC | tbc |  | 2021-06-01 | 2021-09-01
| N/A | Multiple | Jacobs | Technical Safety Services (inc. Hazard Analysis, Equipment Qualification & Thermal hydraulics) | Competitive Tender | tbc | NEC PSC | tbc |  | 2021-06-01 | 2021-09-01
| N/A | Multiple | Jacobs | Waste & Environmental Consultancy Services | - | tbc | NEC PSC | tbc |  | - |  | Assume to be delivered by Jacobs
| N/A | Multiple | Jacobs | Process Engineering Services (inc. CFD & Process Substantiation) | Competitive Tender | tbc | NEC PSC | tbc |  | 2021-06-01 | 2021-09-01
| N/A | Multiple | Jacobs | General Engineering Services (inc. Systems engineering, BIM & Certification eg UKCA/CE) | Competitive Tender | tbc | NEC PSC | tbc |  | 2021-06-01 | 2021-09-01
| N/A | Multiple | Jacobs | Safety Case Services (inc. HF & COMAH) | Competitive Tender | tbc | NEC PSC | tbc |  | 2021-06-01 | 2021-09-01
| N/A | Multiple | 0 | Environmental Site Surveys | Competitive Tender | tbc | Bespoke | 500000 |  | - | 2020-11-01 | Wood E&IS Ltd
| N/A | SRP | Morgan Sindall | Watertight Process Building (FRC and Roof Trusses) | Complete | tbc | NEC | 68700000 | complete | complete | Complete | KIER INFRASTRUCTURE AND OVERSEAS LIMITED
| N/A | SRP | Morgan Sindall | Consultant | Complete | tbc | NEC PSC | tbc | complete | complete | Complete | Connor Commercial Services Limited
| N/A | SRP | Morgan Sindall | Consultant | Complete | tbc | NEC PSC | tbc | complete | complete | Complete | FRAZER-NASH CONSULTANCY LIMITED
| N/A | SRP | Morgan Sindall | Catering | Complete | tbc | NEC PSC | tbc | complete | complete | Complete | PKL GROUP (UK) LIMITED
| N/A | SRP | Morgan Sindall | Catering | Complete | tbc | NEC PSC | tbc | complete | complete | Complete | MIRE SERVICES LIMITED
| N/A | SRP | Morgan Sindall | Design - Glovebox | Complete | tbc | NEC PSC | tbc | complete | complete | Complete | CAVENDISH NUCLEAR LIMITED
| N/A | SRP | Morgan Sindall | Induction video | Complete | tbc | NEC | tbc | complete | complete | Complete | PIXELMILL LTD
| N/A | SRP | Morgan Sindall | Training - machinary directive | Complete | tbc | NEC PSC | tbc | complete | complete | Complete | SAFETY, TECHNOLOGY & LEGISLATION LIMITED
| N/A | SRP | Morgan Sindall | Minor Civils (External) - Proof Trenching | Complete | tbc | framework | 1100000 | Complete | Complete | Complete | DSD Construction Ltd
| N/A | SRP | Morgan Sindall | Turnstiles - Supply Only | Complete | tbc | Material Order | tbc | Complete | Complete | Complete | TENSOR TIME AND ENERGY LLP
| N/A | SRP | Morgan Sindall | Temporary Electrics | Complete | tbc | Option B | tbc | Complete | Complete | Complete | PPS Electrical
| N/A | SRP | Morgan Sindall | Tower Cranes (4nr) | Complete | tbc | Option A / B | 8700000 | complete | complete | complete | Mammoet (UK) Limited
| 0 | SRP | Morgan Sindall | Miscellaneous Sundry Purchases - Office Consumables, small tools & equipment. | Competitive Tender | tbc | Material Order | 1500000 | N/A | N/A | N/A | TBC
| 0 | SRP | Morgan Sindall | Facilities Management - Temp Bldg's | Framework | tbc | Open Competition | included | N/A | TBC | Complete | TBC
| 0 | SRP | Morgan Sindall | Facilities Management - Canteen Catering | Framework | tbc | Open Competition | included | N/A | TBC |  | TBC
| 0 | SRP | Morgan Sindall | Facilities Management - Deep Clean for Rtn to Work & Ongoing Cleaning Services during COVID-19 | Competitive Tender | tbc | Option B | included | complete | complete | 2020-05-15 | TBC
| 0 | SRP | Morgan Sindall | Preliminaries | Competitive Tender | tbc | Open Competition | 23600000 | N/A | 2021-01-15 | 2021-02-26 | TBC
| 0 | SRP | Morgan Sindall | Scaffolding | MPP | tbc | Option C/B | 15400000 | N/A | 2021-10-13 | 2021-12-22 | TBC
| 0 | SRP | Morgan Sindall | Access Equipment - incl'g Alimak Temp Lift | Competitive Tender | tbc | Option B | 6600000 | N/A | 2021-12-01 | 2022-04-26 | TBC
| 0 | SRP | Morgan Sindall | Warehousing and Storage | Competitive Tender | tbc | Lease | 5100000 | N/A | 2021-07-13 | 2021-11-25 | TBC
| 0 | SRP | Morgan Sindall | Warehousing and Storage - Specialist (GBS) | Competitive Tender | tbc | Lease | 400000 | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Logistics (incl. Personnel Transfers) | Framework | tbc | Framework | 11200000 | N/A | 2020-10-27 | 2022-12-22 | TBC
| 0 | SRP | Morgan Sindall | Waste Management | Competitive Tender | tbc | TBC | 600000 | N/A | 2021-03-18 | 2021-05-18 | TBC
| 0 | SRP | Morgan Sindall | Traffic Management | Competitive Tender | tbc | TBC | included | N/A | TBC | 2021-02-22 | TBC
| 0 | SRP | Morgan Sindall | Communication Systems and Remote line of sight | Competitive Tender | tbc | TBC | included | N/A | 2022-01-31 | 2022-06-17 | TBC
| 0 | SRP | Morgan Sindall | Site Temporary Accommodation - Elliotts | Competitive Tender | tbc | NEC option a | 1000000 | Complete | Complete | complete | TBC
| 0 | SRP | Morgan Sindall | Site Temporary Accommodation - PKL Canteen | Competitive Tender | tbc | NEC option a | 1000000 | Complete | Complete | complete | TBC
| 0 | SRP | Morgan Sindall | Site Temporary Accommodation - Demoltion | Competitive Tender | tbc | Option A / C | included | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Refurbishment and fit out of existing B1668 Bld'g | Competitive Tender | tbc | Option A/ C | 2000000 | complete | complete | Complete | TBC
| 0 | SRP | Morgan Sindall | Refurbishment and fit out of existing B1808 Bld'g | Competitive Tender | tbc | Option A / C | 300000 | N/A | 2020-07-31 | 2020-08-28 | TBC
| 0 | SRP | Morgan Sindall | Design Completion of Detailed Design - DSA / Lot2 Transition post Jul20 to Nov20 [Detailed Design PWS, GBS & S&RM + Construction Support] | Competitive Tender | tbc | Option E | included | complete | complete | complete | TBC
| 0 | SRP | Morgan Sindall | Design & S&RM Support post Nov20 - Civil Construction, GBS, MEICA & Commissioning | Competitive Tender | tbc | Option E | included | complete | complete | complete | TBC
| 0 | SRP | Morgan Sindall | SPRS Modifications | Competitive Tender | tbc | Option C | 12300000 | N/A | 2021-06-08 | 2021-08-09 | TBC
| 0 | SRP | Morgan Sindall | RC Slab & Bulk Excavation (OSW - see comment2) | Competitive Tender | tbc | Option C | 6500000 | Complete | Complete | Complete | TBC
| 0 | SRP | Morgan Sindall | Steelwork & Cladding - Internal Process Hall Steelwork, External Steelwork & Cladding | MPP | tbc | Option A off site option C onsite | 13500000 | complete | complete | 2021-04-29 | TBC
| 0 | SRP | Morgan Sindall | Architectural - CLADDING | MPP | tbc | Option A off site option C onsite | 3300000 | complete | complete | 2021-04-29 | TBC
| 0 | SRP | Morgan Sindall | Architectural - BUILDING WORKS | MPP | tbc | option C | 30100000 | N/A | 2021-12-23 | 2022-05-19 | TBC
| 0 | SRP | Morgan Sindall | GBS PSC Professional Services Contract [incl'g Manufacture Support] | Competitive Tender | tbc | PSC Option E with fee moderator linked to KPIs | 500000 | N/A | 2022-03-24 | 2022-09-15 | TBC
| 0 | SRP | Morgan Sindall | Glovebox Design | Competitive Tender | tbc | see above | 5100000 | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | GBS Manufacture Batch Furnace CAT MAN | Competitive Tender | tbc | Option A | 10700000 | complete | complete | Complete | TBC
| 0 | SRP | Morgan Sindall | GBS Manufacture CAT MAN | TBC | tbc | TBC | included | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Acrylic window material - Lexan | Competitive Tender | tbc | incl with packages 127 - 131 | included | complete | complete | 2022-04-05 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Glove ports | Competitive Tender | tbc | Purchase Order | 2000000 | complete | complete | 2021-11-19 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Window Shielding - Lead lined Acrylic (Premac) | Competitive Tender | tbc | Option A | 3300000 | complete | complete | 2021-10-22 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Shielding - Densified Beechwood (Jabroc) | Competitive Tender | tbc | Option A | included | complete | complete | 2021-05-19 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Glove port covers | Competitive Tender | tbc | Option A | included | complete | complete | 2021-09-10 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Lasers | Competitive Tender | tbc | Option A | 2500000 | complete | complete | 2020-12-17 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Swabbing robots | Competitive Tender | tbc | incl with 128 | included | complete | complete | 2021-10-01 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Outer Can TiG welders | Competitive Tender | tbc | Option A | 2300000 | complete | complete | 2021-05-26 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Lighting | Competitive Tender | tbc | incl with packages 127 - 131 | included | complete | complete | 2021-03-16 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Lifting Equipment | Competitive Tender | tbc | Option A | included | complete | complete | 2021-11-26 | TBC
| 0 | SRP | Morgan Sindall | Commodity Supply F.O.C. to Manufacturers - Miscellaneous: Access platforms, Maintenance equipment, Spares, Consumables, operational tools | Competitive Tender | tbc | TBC | included | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Glovebox Ancillary Services Panels | Competitive Tender | tbc | Option C part of PWS Procurement | 2100000 | N/A | 2021-03-12 | 2021-09-21 | TBC
| 0 | SRP | Morgan Sindall | Manufacture IWT, Test & Deliver - Front & Back end systems 300/400/410/500/308/408/418/518 | Competitive Tender | tbc | Option A | 5200000 | complete | complete | 2021-01-15 | TBC
| 0 | SRP | Morgan Sindall | Manufacture IWT, Test & Deliver - Group 400 (Repacking Line) & 06/07 systems (Intermediate Can cut and weld systems) 401/411/406/407/416/417/306/307/506/507 | Competitive Tender | tbc | Option A | 12800000 | complete | complete | 2021-03-29 | TBC
| 0 | SRP | Morgan Sindall | Manufacture IWT, Test & Deliver Group 300 (Powder Retreatment line) 301/302/303/304/305 | Competitive Tender | tbc | Option A | 8400000 | complete | complete | 2021-04-20 | TBC
| 0 | SRP | Morgan Sindall | Manufacture IWT, Test & Deliver - Group 500 (Residues Retreatment line) 501/502/503/505 | Competitive Tender | tbc | Option A | 8200000 | Complete | Complete | 2021-03-19 | TBC
| 0 | SRP | Morgan Sindall | Manufacture IWT, Test & Deliver - Simple Glove Boxes 520 / 699 | Competitive Tender | tbc | Option A | 1200000 | Complete | Complete | 2021-04-30 | TBC
| 0 | SRP | Morgan Sindall | Integrated Works Testing - GBS Series 300 | Competitive Tender | tbc | incl within package 129 | included | N/A | inc above | inc above | TBC
| 0 | SRP | Morgan Sindall | Integrated Works Testing - GBS Series 400 | Competitive Tender | tbc | incl within package 128 | included | N/A | inc above | inc above | TBC
| 0 | SRP | Morgan Sindall | Integrated Works Testing - GBS Series 500 | Competitive Tender | tbc | incl within package 130 | included | N/A | inc above | inc above | TBC
| 0 | SRP | Morgan Sindall | GBX Installation Only - Mechanical | MPP | tbc | Option C | 4800000 | N/A | 2022-03-03 | 2022-09-08 | TBC
| 0 | SRP | Morgan Sindall | GBX Installation Only - EC&I Field | MPP | tbc | Option C | 13800000 | N/A | 2023-05-25 | 2023-11-27 | TBC
| 0 | SRP | Morgan Sindall | Fit Out - Process Building, IT and Specialist Equipment | MPP | tbc | Option A/C | 600000 | N/A | 2023-08-07 | 2023-12-19 | TBC
| KDP 3 | SRP | Morgan Sindall | HVAC - Supply & Install | MPP | tbc | Option A/C | 32200000 | Complete | 2021-04-28 | 2021-10-15 | TBC
| KDP 4 | SRP | Morgan Sindall | EC&I - LV Power Distribution (Cabling, Installation) | MPP | tbc | Option A/C | 29000000 | 2021-04-01 | 2021-07-01 | 2022-04-05 | TBC
| KDP 4 | SRP | Morgan Sindall | EC&I - Lighting | MPP | tbc | Option A/C | 9300000 | TBC | 2021-04-01 | 2022-01-21 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Specialist Supply & Install; Fire System | MPP | tbc | Option A/C | 6300000 | N/A | 2022-07-13 | 2023-03-20 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Specialist Supply & Install; Process CCTV | MPP | tbc | Option A/C | 4400000 | N/A | 2021-02-17 | 2022-02-16 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Specilaist Supply & Install; Internal Emergency Radio System | MPP | tbc | Option A/C | 1000000 | N/A | 2023-01-24 | 2023-09-26 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Specialist Supply & Install; Data Telecomms | MPP | tbc | Option A/C | 2900000 | N/A | 2022-11-04 | 2023-09-26 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Specialist Supply & Install; Security Systems | MPP | tbc | Option A/C | 5800000 | N/A | 2022-11-04 | 2023-09-26 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Specialist Supply & Install; Radiological Protection/Monitoring | MPP | tbc | Option A/C | 5600000 | N/A | 2022-03-21 | 2022-09-12 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Supply Only - Control Panels Instrumentation (Tier 4) incl'g GBS | Competitive Tender | tbc | Option A | 3500000 | N/A | 2021-07-15 | 2022-03-16 | TBC
| GSA 1 | SRP | Morgan Sindall | Package Management MECH - Supply Only - Machine Shop - FULL MACHINE | Competitive Tender | tbc | Option A | 9400000 | 2021-03-01 | TBC | 2022-03-18 | TBC
| 0 | SRP | Morgan Sindall | Mech Installation Package Transfer Installation (incl's 000/100/200 IWT & SAT support) | MPP | tbc | Option A | 20800000 | N/A | 2021-06-11 | 2022-06-13 | TBC
| tbc | SRP | Morgan Sindall | Mechanical Fabrication (incl's 000/100/200 IWT & SAT support) | Competitive Tender | tbc | Option A | 2700000 | N/A | 2022-07-19 | 2022-11-30 | TBC
| 0 | SRP | Morgan Sindall | Cranes & Hoists | MPP | tbc | Option A | 100000 | N/A | 2022-10-12 | 2023-01-27 | TBC
| 0 | SRP | Morgan Sindall | Monorail (incl's 000/100/200 IWT & SAT support) | Competitive Tender | tbc | Option A | 4700000 | N/A | 2021-06-16 | 2022-04-13 | TBC
| 0 | SRP | Morgan Sindall | Shield Doors | Competitive Tender | tbc | option A | 3000000 | N/A | 2021-05-27 | 2021-12-02 | TBC
| 0 | SRP | Morgan Sindall | Lifts | MPP | tbc | Option A | 600000 | N/A | 2023-02-20 | 2023-07-07 | TBC
| 0 | SRP | Morgan Sindall | Control Systems PLC & Scada | Competitive Tender | tbc | Option A | 9600000 | N/A | 2021-02-02 | 2021-06-10 | TBC
| 0 | SRP | Morgan Sindall | EC&I - Control Systems Network Wiring | MPP | tbc | option A/C | 500000 | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Piped ServicesI PiPEWORK - Fabrication, COTs, Installation & Test | MPP | tbc | option A/C | 13600000 | N/A | 2021-03-15 | 2021-12-09 | TBC
| 0 | SRP | Morgan Sindall | Tank Farm (Vessels) | Competitive Tender | tbc | Option A | 200000 | N/A | 2021-10-20 | 2022-03-11 | TBC
| 0 | SRP | Morgan Sindall | Statutory Inspections | Competitive Tender | tbc | Option E | 200000 | N/A | 2021-04-21 | 2021-11-08 | TBC
| 0 | SRP | Morgan Sindall | CE marking (main systems) | Competitive Tender | tbc | Option E | 900000 | complete | complete | complete | TBC
| 0 | SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | MPP | tbc | Option C | 500000 | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | ECI - Machine Directive Training | Competitive Tender | tbc | Fixed Price | included | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Fork Lift Truck (FLT) | Competitive Tender | tbc | Fixed Price | included | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Testing Packages | Competitive Tender | tbc | Fixed Price | Included in glovebox values | N/A | N/A | N/A | TBC
| 0 | SRP | Morgan Sindall | Maintenance Equipment e.g. Pallet Trucks, MEWP's | Competitive Tender | tbc | Fixed Price | included | N/A | 2024-01-31 | 2024-06-18 | TBC
| 0 | SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Competitive Tender | tbc | TBC | 1900000 | N/A | 2024-10-30 | 2025-03-24 | TBC
| 0 | SRP | Morgan Sindall | Steam Supply from THORP | Framework | tbc | TBC | 3200000 | N/A | 2021-12-10 | 2022-02-21 | TBC
| 0 | SRP | Morgan Sindall | Services Building (prev. ref. Welfare) - Civils & Bld'g works | MPP | tbc | Option A/C | 12600000 | N/A | 2021-11-16 | 2022-04-07 | TBC
| 0 | SRP | Morgan Sindall | Services Building (prev. ref. Welfare) - MEICA works | MPP | tbc | Option A/C | included | N/A | 2023-04-24 | 2023-09-07 | TBC
| 0 | SRP | Morgan Sindall | Fit Out - Services Building | MPP | tbc | Option A/C | 100000 | N/A | 2023-01-05 | 2023-07-12 | TBC
| 0 | SRP | Morgan Sindall | Service / Welfare Building Facilities Management | MPP | tbc | Reimbursable | 700000 | N/A | 2024-04-24 | 2024-09-09 | TBC
| 0 | SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Security | MPP | tbc | Reimbursable | included | N/A | 2024-04-24 | 2024-09-09 | TBC
| 0 | SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Cleaning | MPP | tbc | Reimbursable | included | N/A | 2024-04-24 | 2024-09-09 | TBC
| 0 | SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Consumable re-stocking | MPP | tbc | Reimbursable | included | N/A | 2024-04-24 | 2024-09-09 | TBC
| 0 | SRP | Morgan Sindall | Minor Civils (External) - Underground / Buried Services Rq'd [Buried Services incl'g BT Data ducts, Piped Services ducts, Pumped Water, 11Kv ducts, Surface & Foul Water] - Incl's Security Resource | Competitive Tender | tbc | Option A/C /E | 6300000 | N/A | 2021-01-21 | 2021-03-04 | TBC
| 0 | SRP | Morgan Sindall | Minor Civils (External) - Balance of Civils Works ALAP | Competitive Tender | tbc | Option A/C | 4300000 | N/A | 2022-04-07 | 2022-06-22 | TBC
| 0 | SRP | Morgan Sindall | Security Fence | MPP | tbc | Option C | 8300000 | N/A | 2023-07-05 | 2023-10-25 | TBC
| 0 | SRP | Morgan Sindall | Site security infrastructure | TBC | tbc | TBC | 6200000 | N/A | 2020-07-24 | 2021-02-10 | TBC
| 0 | SRP | Morgan Sindall | Active Commissioning Support | Competitive Tender | tbc | TBC | 20300000 | N/A | TBC | TBC | TBC
| 0 | SRP | Morgan Sindall | Training (Operation & Maintenance) | TBC | tbc | TBC | included | N/A | 2023-10-09 | 2024-02-28 | TBC
| 0 | SRP | Morgan Sindall | O&M Equipment | TBC | tbc | TBC | 300000 | N/A | 2026-04-16 | 2026-09-01 | TBC
| N/A | BEPPS2 | Morgan Sindall | Temporary Construction Services & Permit Office | Competitive Tender | tbc | NEC-A | TBC | TBC | 2022-09-15 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Fence & Access Control | Competitive Tender | tbc | NEC-A | TBC | TBC | 2022-02-01 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Construction Surveys | Competitive Tender | tbc | NEC-A | TBC | TBC | 2022-06-12 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Construction Surveys - 3D Laserscans | Competitive Tender | Low | Short Form/Fixed Price | TBC | N/A | 2020-07-01 | 2020-09-01 | WYG Engineering Ltd
| N/A | BEPPS2 | Morgan Sindall | SHEF Services | MPP | tbc | PSC | TBC | TBC | 2021-12-21 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Welfare & Maintenance Services | Competitive Tender | tbc | Services Agreement | TBC | TBC | 2023-06-16 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Scaffold | Competitive Tender | tbc | NEC-A | TBC | TBC | 2022-11-10 | TBC | TBC
| GSA 5 | BEPPS2 | Morgan Sindall | Site Accommodation Block | MPP | tbc | GSA 5 | TBC | 2021-03-01 | TBC | TBC | TBC
| KDP 1 | BEPPS2 | Morgan Sindall | Early Ground Works | MPP | tbc | KDP 1 | TBC | TBC | 2022-06-15 | TBC | TBC
| KDP 1 | BEPPS2 | Morgan Sindall | Ground Works & Excavation | MPP | tbc | KDP 1 | TBC | TBC | 2022-09-12 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Concrete Supply | Supply Order | tbc | NEC/SUPPLY | TBC | TBC | 2022-12-10 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Site Emergency phone line (Copper) | Competitive Tender | tbc | NEC-A | TBC | TBC | 2023-05-15 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Goods Hub Fit out | Competitive Tender | tbc | NEC-A | TBC | TBC | 2023-06-16 | TBC | TBC
| GSA 7 | BEPPS2 | Morgan Sindall | Digital Construction (Software/Hardware) | MPP | tbc | GSA 7 | TBC | TBC | 2023-04-21 | TBC | TBC
| SA 3 | BEPPS2 | Morgan Sindall | Crane Schemes (main build/equipment hire/Shield door lift) | MPP | tbc | TBC | TBC | TBC | 2021-01-26 | TBC | TBC
| KDP 7 | BEPPS2 | Morgan Sindall | Scaffold | MPP | tbc | KDP 7 | TBC | TBC | 2024-08-20 | TBC | TBC
| KDP 4 | BEPPS2 | Morgan Sindall | Temporary Lighting/Power | MPP | tbc | KDP 4 | TBC | TBC | 2025-03-22 | TBC | TBC
| TBC | BEPPS2 | Morgan Sindall | Permanent Services/water/fire hydrants/elec/drains/networks/phones | Competitive Tender | tbc | NEC-A / C | TBC | TBC | 2026-06-22 | TBC | TBC
| KDP 11 | BEPPS2 | Morgan Sindall | Temp/perm fire protection/doors/stopping | MPP | tbc | KDP 11 | TBC | TBC | 2026-04-21 | TBC | TBC
| KDP 1 | BEPPS2 | Morgan Sindall | Permanent Roads & Paths/External Handrails and Crash Barriers | MPP | tbc | KDP 1 | TBC | TBC | 2026-07-20 | TBC | TBC
| KDP 8 | BEPPS2 | Morgan Sindall | Concrete structures (walls/slabs/floors/vault roof) | MPP | tbc | KDP 8 | TBC | TBC | 2023-12-21 | TBC | TBC
| KDP 8 | BEPPS2 | Morgan Sindall | Encast items liners/tunnel/vault/plant room floor/east annexe | MPP | tbc | KDP1 | TBC | TBC | 2022-09-19 | TBC | TBC
| KDP 6 & KDP 2 | BEPPS2 | Morgan Sindall | Structured Steelwork & Cladding | MPP | tbc | KDP6 & KDP 2 | TBC | TBC | 2025-07-14 | TBC | TBC
| KDP 9 | BEPPS2 | Morgan Sindall | Finishes - protection/floors/ironmongeryl/locking systems | MPP | tbc | KDP 9 | TBC | 2021-02-01 | 2021-06-01 | 2022-01-01 | TBC
| N/A | BEPPS2 | Morgan Sindall | Specialist Permanent Doors | Competitive Tender | tbc | Competition-NEC-A | TBC | TBC | 2025-11-25 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Goods Hub operations | Competitive Tender | tbc | Competition-NEC-A | TBC | TBC | 2023-07-27 | TBC | TBC
| GSA 4 | BEPPS2 | Morgan Sindall | Goods Lift | MPP | tbc | GSA 4 | TBC | TBC |  | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Vault Cranes supplied with local control panels and locally mounted CM&I equipment (2 off) | Category Management | tbc | Category Management | TBC | TBC | 2023-01-26 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Shield Door, drives, guides and local control panel | Category Management | tbc | Category Management | TBC | TBC | 2022-12-22 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Sliding Vent Covers & local control panels (2 off) | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2024-04-08 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Peronsal Access Doors | Category Management | tbc | Category Management | TBC | TBC | 2025-09-15 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Cranes (out-cell) with local control panels (5 off) | Category Management | tbc | Category Management | TBC | TBC | 2024-02-17 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Integrated Control System - SCADA & PLC | Category Management | tbc | Category Management | TBC | TBC | 2026-10-18 | TBC | TBC
| KDP 3 | BEPPS2 | Morgan Sindall | HVAC Design, supply, install, commission | MPP | tbc | KDP 3 | TBC | 2021-03-01 | 2024-04-29 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Condition, Moniltoring and Inspection instrumentation | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2025-08-04 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Crane & Shield Door - rails/guides fabrications | Category Management | tbc | Category Management | TBC | TBC | 2025-06-23 | TBC | TBC
| KDP 4 | BEPPS2 | Morgan Sindall | Power Distribution (main level 2/3 switchboards) | MPP | tbc | KDP 4 | TBC | TBC | 2025-05-19 | TBC | TBC
| KDP 4 | BEPPS2 | Morgan Sindall | UPS and batteries for guaranteed power | MPP | tbc | KDP 4 | TBC | TBC | 2026-01-05 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Intruder detection systems expansion (BEPPS1) | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2026-08-08 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Fire Detection system expansion (BEPPS1) | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2026-08-08 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Communications system expansion | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2026-08-08 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Public address system expansion | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2027-06-06 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Wireless IT Expansion | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2027-02-13 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | CCTV system expansion | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2027-06-06 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Radiometrics system expansion | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2027-06-06 | TBC | TBC
| N/A | BEPPS2 | Morgan Sindall | Process Equipment | Competitive Tender | tbc | Competition - NEC-A | TBC | TBC | 2026-02-08 | TBC | TBC
| KDP 3 | BEPPS2 | Morgan Sindall | Electrical Installation | MPP | tbc | KDP 3 | TBC | 2021-03-01 | 2026-04-13 | TBC | TBC
| KDP 5 | BEPPS2 | Morgan Sindall | Mechanical Installation | MPP | tbc | KDP 5 | TBC | TBC | 2026-04-13 | TBC | TBC
| KDP 5 | BEPPS2 | Morgan Sindall | Pipework - design/supply/install/commission | MPP | tbc | KDP 5 | TBC | TBC | 2026-04-13 | TBC | TBC
| GSA 5 | LSS1 | Morgan Sindall | Site Accommodation Block | MPP | tbc | GSA 5 | TBC | 2021-03-01 | 2021-10-01 | TBC | TBC
| KDP 6 | LSS1 | Morgan Sindall | Roofing and Cladding | MPP | tbc | KDP 6 | TBC | TBC | 2023-12-01 | TBC | TBC
| KDP 11 | LSS1 | Morgan Sindall | Fire Protection | MPP | tbc | KDP 11 | TBC | TBC | 2024-07-01 | TBC | TBC
| N/A | LSS1 | Morgan Sindall | Plant Hire | PPP Plant Desk | tbc | MPP | TBC | TBC | 2022-10-01 | TBC | TBC
| SA 1 | LSS1 | Morgan Sindall | Catering -Site Welfare | MPP | tbc | Competition - NEC-A | TBC | TBC | 2021-10-01 | TBC | TBC
| n/a placed | RAP | Morgan Sindall | Extension to cable diversion work | ISA | tbc | TBC | 10000 | n/a | n/a | 2020-02-27 | 65087 Morgan Sindall Arup
| n/a placed | RAP | Sellafield | SNM Displacement group 2 | Framework | tbc | NEC3 Opt C - Target Cost | 900000 | n/a | n/a | 2019-10-03 | Nexus 376
| n/a placed | RAP | Sellafield | SNM Existing Facility Displacement - Group 1 - Fumehoods & Machinery | Framework | Medium | NEC -C | 1900000 | n/a | 2019-11-22 | 2020-07-27 | Nexus
| n/a placed | RAP | Sellafield | SNM Existing Facility Displacement - Group 3 - Office Relocation Phase 1 | Framework | Medium | NEC -C | 100000 | n/a | 2020-09-29 | 2020-11-04 | Nexus
| KDP 4 | RAP | Morgan Sindall | SNM Existing Facility Displacement - Group 3 - Office Relocation Phase 2 | MPP | tbc | NEC - C | 400000 | 2021-03-01 | 2021-04-21 | 2021-09-13 | tbc
| n/a placed | RAP | Sellafield | SNM Existing Facility Displacement - Group 5 - Muster Area phase 1 | Competitive Tender | Medium | NEC - C | 100000 | n/a | 2021-02-12 | 2021-05-12 | Nexus
| KDP 4 | RAP | Morgan Sindall | SNM Existing Facility Displacement - Group 5 - Muster Area phase 2. | MPP | tbc | NEC- C | 100000 | 2021-03-01 | TBC | 2021-10-04 | tbc
| KDP 4 | RAP | Morgan Sindall | SNM Existing Facility Displacement - Group 4 | MPP | tbc | NEC- C | 1000000 | 2021-03-01 | TBC | 2021-10-11 | tbc
| KDP - 5 | RAP | Morgan Sindall | SNM TCAO (Temporary Construction Access Opening) Phase 1 to support Group 4. Need Civils to confirm when the they can complete 1st 2 smaller TCAO's required for the group 4 package of works. | MPP | tbc | NEC- C | 100000 | n/a | 2021-04-08 | 2021-08-20 | tbc
| KDP - 5 | RAP | Morgan Sindall | SNM TCAO (Temporary Construction Access Opening) Phase 2 to support main demolition and installation works | MPP | tbc | NEC- C | 300000 | n/a | 2021-04-08 | 2021-09-13 | tbc
| KDP - 5 | RAP | Morgan Sindall | SNM Service Diversions | MPP | tbc | NEC- C | 1000000 | n/a | 2021-07-05 | 2021-12-06 | tbc
| n/a placed | RAP | Sellafield | Detail Design - Gloveboxes | Category Management | High | NEC - E | 6200000 | n/a | TBA | 2020-08-05 | Cavendish
| KDP - 5 | RAP | Morgan Sindall | SNM Strip Out | MPP | tbc | NEC - C | 500000 | n/a | 2021-10-29 | 2022-03-21 | tbc
| n/a | RAP | Morgan Sindall | Manufacture of Gloveboxes | Competitive Tender | tbc | NEC - A | 22600000 | n/a | TBA | 2022-08-15 | tbc
| KDP 4 | RAP | Morgan Sindall | SNM Demolition | MPP | tbc | NEC - tbc | 1400000 | 2021-03-01 | TBC | 2023-06-01 | tbc
| MPP - tbc | RAP | Morgan Sindall | SNM Construction | MPP | tbc | NEC - tbc | 17100000 | n/a | TBA | 2024-03-25 | tbc
| MPP- tbc | RAP | Morgan Sindall | SNM Installation | MPP | tbc | NEC - tbc | No estimate value available- tbc as part of MPTP | n/a | TBA | 2025-05-19 | tbc
| tbc | RAP | Morgan Sindall | Area 100 - CCTV System | Competitive Tender | tbc | NEC - tbc | No estimate value available- tbc as part of MPTP | tbc | 2023-01-31 | 2023-06-16 | tbc
| tbc | RAP | Morgan Sindall | Replacement of Plan Overview System PLC (System 105) | Competitive Tender | tbc | NEC - tbc | No estimate value available- tbc as part of MPTP | tbc | 2022-04-20 | 2022-09-02 | tbc
| tbc | RAP | Morgan Sindall | HAASC (system 131) | Competitive Tender | tbc | NEC - tbc | No estimate value available- tbc as part of MPTP | tbc | 2022-09-22 | 2023-02-10 | tbc
| tbc | RAP | Morgan Sindall | HA Cells 4 & 5 (System 134 & 135) | Competitive Tender | tbc | NEC - tbc | No estimate value available- tbc as part of MPTP | tbc | 2023-10-02 | 2024-02-20 | tbc
| tbc | RAP | Morgan Sindall | PTS (System 137) | Competitive Tender | tbc | NEC - tbc | No estimate value available- tbc as part of MPTP | tbc | 2023-07-25 | 2023-12-05 | tbc
| tbc | RAP | Morgan Sindall | Design & Manufacture Transfer System | Competitive Tender | tbc | NEC - tbc | 1300000 | tbc | 2023-04-26 | 2023-09-08 | tbc
| tbc | RAP | Morgan Sindall | Procure Prefabricated Fumehoods | Competitive Tender | tbc | NEC - tbc | 2800000 | tbc | 2023-04-26 | 2023-09-08 | tbc
| tbc | RAP | Morgan Sindall | Design & Manufacture Fire Supression Equipment | Competitive Tender | tbc | NEC - tbc | 100000 | tbc | 2023-04-26 | 2023-09-08 | tbc
| tbc | RAP | Morgan Sindall | Design & Manufacture MA Cells | Competitive Tender | tbc | NEC - tbc | 10100000 | tbc | 2023-04-26 | 2023-09-08 | tbc
| tbc | RAP | Morgan Sindall | Design & Manufacture Miscellaneous Tanks | Competitive Tender | tbc | NEC - tbc | 100000 | tbc | 2023-04-26 | 2023-09-08 | tbc
| n/a - placed | RAP | Morgan Sindall | Ground contamination survey ( Soil / Vapour) | Competitive Tender | tbc | NEC - B | 900000 | completed | 2020-06-19 | 2021-02-05 | Soil Engineering
| n/a - placed | RAP | Sellafield | In Active BMS Modifications Panel Installation (Align to Group 1 contract) | Framework | tbc | NEC - C | 100000 | n/a | 2020-03-31 | 2020-10-23 | Nexus
| n/a | RAP | Morgan Sindall | Mods to Fire alarm system | Competitive Tender | tbc | NEC - tbc | 100000 | tbc | TBA | TBA | tbc
| n/a-placed | RAP | Sellafield | Inactive Fire Damper Mods (Design) | Framework | tbc | NEC - E | 200000 | n/a | 2020-02-21 | 2020-07-24 | Nexus
| n/a placed | RAP | Sellafield | Inactive Fire Damper Mods (Build) | Framework | tbc | NEC - A | 200000 | n/a | - | 2021-04-14 | Nexus
| N/A | RAP | Morgan Sindall | Early Works Civil Framework Contract (3off Task Orders) | Competitive Tender | tbc | NEC - C | 150000 | n/a | 2021-09-29 | 2022-02-17 | tbc
| GDP - 5 | RAP | Morgan Sindall | Task Order 01: Construction Village, Must Hut, CSCP, CCTV Plinths, Temp Services | MPP | tbc | NEC - C | 390000 | n/a | 2021-03-26 | 2021-05-19 | tbc
| GDP - 4 | RAP | Morgan Sindall | Task Order 02: Bulk & Btl Gas Facility, B170.3, Retaining Walls | MPP | tbc | NEC - C | 581795.6 | n/a | 2022-04-14 | 2022-05-17 | tbc
| GDP - 4 | RAP | Morgan Sindall | Task Order 03: New South Extension Bulk Ex & Associated Serv Div | MPP | tbc | NEC - C | 760000 | n/a | 2022-04-14 | 2022-05-17 | tbc
| GSA 5 | RAP | Morgan Sindall | Mobilise for construction village (JL Cabins) | MPP | tbc | NEC - C | 87000 | 2021-03-01 | 2020-10-23 | 2021-08-16 | tbc
| n/a - placed | RAP | Morgan Sindall | Service Diversions (HV LV & other Electrical feeds) (Civil Draw Pit) | Competitive Tender | tbc | NEC - C | 530000 | completed | 2020-08-28 | 2021-02-16 | tbc
| MPP - tbc | RAP | Morgan Sindall | Demolition for existing B170.3 BMS | MPP | tbc | NEC - tbc | 77100 | n/a | tbc | 2023-06-05 | tbc
| KDP 4 | RAP | Morgan Sindall | Gas relocation ME& I - New Bulk Gas Facility (Inc Commissioning / Tie in) | MPP | tbc | NEC - tbc | 820000 | 2021-03-01 | 2022-03-03 | 2022-07-20 | tbc
| KDP 4 | RAP | Morgan Sindall | Gas relocation ME& I - New Bottle Gas Facility (Inc Commissioning / Tie in) | MPP | tbc | NEC - tbc | 285000 | 2021-03-01 | 2022-03-03 | 2022-07-20 | tbc
| KDP 4 | RAP | Morgan Sindall | Mox Chiller replacement | MPP | tbc | NEC - tbc | 105000 | 2021-03-01 | 2022-03-03 | 2022-07-20 | tbc
| n/a | RAP | Morgan Sindall | New B170.3 / BMS / Switch room Procurement (Design and Build) | Competitive Tender | tbc | NEC - tbc | 482500 | completed | 2021-03-30 | 2021-08-16 | tbc
| n/a | RAP | Morgan Sindall | MEI installation contractor for B170.3 | Competitive Tender | tbc | NEC - tbc | 285000 | completed | 2022-03-03 | 2022-07-20 | tbc
| GSA 5 | RAP | Morgan Sindall | Construction Village Build Manufacture & Build | MPP | tbc | NEC - tbc | 2650000 | 2021-03-01 | 2020-09-25 | 2021-04-14 | tbc
| KDP 4 | RAP | Morgan Sindall | Replacement / Relocation of Emergency / Criticality Re-Entry Point | MPP | tbc | NEC - tbc | 20000 | 2021-03-01 | 2021-07-01 | 2021-10-01 | tbc
| n/a already placed | RAP | Sellafield | TAIM - New Import Export Crane (Design) | Category Management | tbc | NEC - tbc | 33070.5 | n/a | TBA | 2020-10-23 | Taim
| KDP - 2 | RAP | Morgan Sindall | Sub-structure -New Build Services Building | MPP | tbc | NEC - tbc | 350000 | n/a | TBA | TBA | tbc
| n/a - placed | RAP | Morgan Sindall | Bundle 4 - Develop & nuclearise 24 off instruments | Competitive Tender | High | NEC - tbc | 572566 | completed | 2020-03-03 | 2021-02-19 | NIS
| n/a placed | RAP | Morgan Sindall | Bundle 5 - Develop & nuclearise 13 off instruments | Competitive Tender | High | NEC - tbc | 4681761.6 | completed | 2020-03-03 | 2021-03-31 | Orano
| n/a placed | RAP | Morgan Sindall | Bundle 6 - Develop & nuclearise 11 off instruments | Competitive Tender | High | NEC - tbc | 3657817 | completed | 2020-03-03 | 2021-03-31 | Aquila
| GSA 3 | RAP | Morgan Sindall | Bundle 1, Instrument Category - Unmodified commercial off the shelf (COTS) instruments. | MPP | Low | NEC - tbc | 185885 | n/a | 2022-10-03 | 2022-12-12 | tbc
| GSA 3 | RAP | Morgan Sindall | Bundle 2, Instrument Category - Unmodified commercial off the shelf (COTS) instruments. | MPP | Low | NEC - tbc | 699963 | n/a | 2022-10-03 | 2022-12-12 | tbc
| GSA 3 | RAP | Morgan Sindall | Bundle 3, Instrument Category - Simple modified instruments (COTS) with minor modifications. | MPP | Low | NEC - tbc | 74550 | n/a | 2022-10-03 | 2022-12-12 | tbc
| n/a | RAP | Morgan Sindall | Mock-up Facility | Competitive Tender | tbc | NEC - tbc | 300000 | n/a | TBA | TBA | tbc
| n/a | RAP | Jacobs | E&I Design Support x 10 individuals | Competitive Tender | tbc | NEC - PSC | 2000000 | tba | tba | tba | tbc
| N/A | PPP Services | KBR | Business Support | Framework | N/A | Framework Contract | 310000 | N/A | N/A | 2020-01-01 | Chrisopher Kilmurry Partnership Ltd (CKP)
| N/A | PPP Services | KBR | Recruitment services | Framework | N/A | Framework Contract | 500000 | N/A | N/A | 2019-05-01 | Thomas Thor
| N/A | PPP Services | KBR | Business Support | Framework | N/A | Framework Contract | 1000000 | N/A | N/A | 2019-05-01 | Concerto
| N/A | PCCS / RAP | KBR | Quantity Surveying / Post Contract Management | Framework | N/A | Framework Contract | 500000 | N/A | N/A | 2019-09-01 | Gardiner & Theobald LLP
| N/A | PCCS | KBR | Commerical / Contract Management | Framework | N/A | Framework Contract | 9000000 | N/A | N/A | 2020-01-01 | Hargreaves Jones
| N/A | PCCS | KBR | Commerical / Contract Management | Framework | N/A | Framework Contract | 15000000 | N/A | N/A | 2020-02-01 | Mott MacDonald
| N/A | PPP Services | KBR | Integration Support | Complete | N/A | Framework Contract | 100000 | N/A | 2020-02-01 | 2020-05-01 | Acorn Coaching & Development
| N/A | Multiple | KBR | PPP supply chain tool (EPMS) | Competitive Tender | N/A | Bespoke | 90100 | N/A | N/A | Est Feb-21 | Asite

## REMOVED SCOPE (hidden)
Project Scope / Trade Packs Description | WBS | WBS No | WBS Category | Trade Pack No | Contract Strategy | Contractual Consideration | Fab /proc Doosan Babcock Package No | Combine with fab / proc pack | Installation Pack No | Package Discipline
Process Condensate Return & CO2 | Internal SIXEP Mod's | 600 | A - Brownfield Mods | 616 | 1 Contract Supply & Install | REMOVED | REMOVED | REMOVED | REMOVED | REMOVED