## Instructions
Issued for Information

## Procurement Plan
Unique Ref | Project | Procuring Partner | Project Scope / Trade Packs Description | Category | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
PWP-08-02 | BEPPS2 | Morgan Sindall | CO981 Welfare - Design and Fit out | Construction | Project - Competitive Tender | NEC 4 ECC | D | 2024-02-01 | 2024-04-01 | 2025-06-01 | Not Awarded | Not Awarded
KBR-71 | PPP Services | KBR | Coaching and Mentoring services | Support Services | Project - Competitive Tender | PSC Shortform | A | 2024-05-01 | 2024-11-01 | 2025-07-01 | Not Awarded | Not Awarded
KBR-72a | PPP Services | KBR | Mediation services - FWA 1 | Support Services | Project - Competitive Tender | PSC Shortform | A | 2024-05-01 | 2024-11-01 | 2025-07-01 | Not Awarded | Not Awarded
KBR-67 | PPP Services | KBR | Specialist commercial training - NEC4 PM training | Training | Project - Competitive Tender | Supplier T&Cs | A | 2024-10-01 | 2024-10-01 | 2025-08-01 | Not Awarded | Not Awarded
SCP-C3 | SCP | Altrad Babcock | Site emergency response team | Construction | Project - Competitive Tender | NEC 4 ECC | E | 2025-04-01 | 2025-05-01 | 2025-08-01 | Not Awarded | Not Awarded
AMTM-43B | PPP Services | Amentum | MP Engineering Design DSN | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2024-07-01 | 2024-08-01 | 2025-09-01 | Not Awarded | Not Awarded
SRP-139L.1 | SRP | Morgan Sindall | Services Building - Securiclad Internal Liner | Construction | Project - Competitive Tender | NEC 4 ECC | E | 2025-05-01 | 2025-07-01 | 2025-12-01 | Not Awarded | Not Awarded
PWP-17 | BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-01 | 2025-06-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-147 | SRP | Morgan Sindall | Security Fence | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2024-11-01 | 2025-04-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-171C | SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Cleaning | Facilities Management | Project - Competitive Tender | NEC | B | 2024-02-01 | 2024-05-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-168 | SRP | Morgan Sindall | Site Temporary Accommodation - Demoltion | Construction | Project - Competitive Tender | NEC | D | 2025-11-01 | 2026-02-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-173 | SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2024-08-01 | 2024-10-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-171A | SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | NEC | D | 2024-02-01 | 2024-05-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-203 | SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | D | 2023-10-01 | 2024-01-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-151 | SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC 4 ECC | D | 2023-06-01 | 2023-11-01 | 2026-07-01 | Not Awarded | Not Awarded
SRP-176 | SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | C | 2026-02-01 | 2026-04-01 | 2026-10-01 | Not Awarded | Not Awarded
PWP-25 | BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2024-02-01 | 2024-05-01 | 2027-10-01 | Not Awarded | Not Awarded
ECI-PWP25-1A | BEPPS2 | Morgan Sindall | Shield Door Inc Liners ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | A | 2024-09-01 | 2024-02-01 | 2024-05-01 | 2024-05-01 | Asturfeito SA
SRP-119 | SRP | Morgan Sindall | Glove Port Covers, Frames & Interlocks | Precision Engineering | Project - Competitive Tender | NEC 4 ECC | E | 2021-06-01 | 2022-02-01 | 2024-05-01 | 2024-05-01 | Fort Vale Nuclear Limited
ECI-PWP25-1 | BEPPS2 | Morgan Sindall | Shield Door Inc Liners ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | A | 2024-09-01 | 2024-02-01 | 2024-06-01 | 2024-06-01 | JGC Engineering & Technical Services Limited
SRP-191B | SRP | Morgan Sindall | PCM Monitors | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 Supply Contract | E | 2023-01-01 | 2023-06-01 | 2024-06-01 | 2024-06-01 | Mirion Technologies (Canberra) Uk Limited
KBR-64 | PPP Services | KBR | Health & Safety Training | Health & Safety | Project - Competitive Tender | Purchase Order | A | 2024-04-01 | 2024-05-01 | 2024-07-01 | 2024-07-01 | Highfield Awarding Body for Compliance Limited
JAC-38 | SCP | Jacobs | Fire Stopping Design | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | D | 2023-09-01 | 2023-10-01 | 2024-08-01 | 2024-08-01 | GRJ Contracting Limited
KBR-61 | PPP Services | KBR | Human Performance | Training | Project - Competitive Tender | Framework | E | 2024-04-01 | 2024-06-01 | 2024-10-01 | 2024-10-01 | GMR Human Performance Limited
ECI-PWP25-04 | BEPPS2 | Morgan Sindall | Shield Door Hose Reel ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSSC | A | 2024-02-01 | 2024-03-01 | 2024-11-01 | 2024-11-01 | Metreel Limited
PWP-10 | BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | NEC | G | 2024-01-01 | 2024-03-01 | 2024-12-01 | 2024-12-01 | Mitie FM Limited
KBR-68 | PPP Services | KBR | Specialist commercial training - APM Project Management Training | Training | Project - Competitive Tender | Framework | B | 2024-09-01 | 2024-09-01 | 2024-12-01 | 2024-12-01 | 20/20 Business Insight Limited
ECI-PWP24 | BEPPS2 | Morgan Sindall | CMA Maintenance Crane ECI | Engineering | Project - Competitive Tender | NEC 4 PSSC | B | 2024-01-01 | 2024-03-01 | 2025-01-01 | 2025-01-01 | SCX Special Projects Ltd
PPPG-DCL-056 | CDE | KBR | Planning Tool - Professional Services (Licences by SL) | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2024-07-01 | 2024-07-01 | 2025-02-01 | 2025-02-01 | Hyde Park Solutions Limited
KBR-74 | CDE | KBR | Video/animation creation platform | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2024-11-01 | 2024-12-01 | 2025-02-01 | 2025-02-01 | Omniplex Group Limited
KBR-42 | PPP Services | KBR | MP Project Controls | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2023-09-01 | 2024-07-01 | 2025-02-01 | 2025-02-01 | Adept, Mott, Prima Uno, Blueprint, Equib, Optimise, G&T.
MSAB01 | PPP Services | Morgan Sindall & Altrad Babcock | MP Commissioning & Pre-Ops | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2024-06-01 | 2024-09-01 | 2025-03-01 | 2025-02-01 | Bilfinger Uk Ltd, Cumbria O&M Services Ltd, PPS Electrical Ltd
AMTM-43A | PPP Services | Amentum | MP Engineering Design Partner | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | A | 2024-07-01 | 2024-10-01 | 2025-03-01 | 2025-03-01 | Cyclife UK Limited, Mott Macdonlad Limited
PPPG-DCL-048 | CDE | KBR | 4D Planning and Scheduling - Professional Services | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2025-03-01 | 2025-03-01 | 2025-05-01 | 2025-05-01 | Oakwood Engineering solutions Limited
KBR-77 | CDE | KBR | ITHC (IT Health Check) services FWA | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2024-08-01 | 2025-02-01 | 2025-05-01 | 2025-05-01 | Advent IM Limited
KBR-72b | PPP Services | KBR | Mediation services - FWA 2 | Support Services | Project - Competitive Tender | PSC Shortform | A | 2024-05-01 | 2024-11-01 | 2025-07-01 | 2025-06-01 | Wilson and Wilson Learning Ltd