## Procurement Plan
Project | Procuring Partner | Project Scope / Trade Packs Description | Category 1 | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
SCP | Altrad Babcock | Interconnecting Pipework and pipe bridge sumps (East &West Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | G | Complete | 2022-04-01 | 2023-01-23 | 2023-01-23 | Shepley Engineers Limited
RAP | Morgan Sindall | Bundle 5 (WO2) Prototype and Detailed Design | Engineering | Framework | NEC | E | N/A | 2022-08-23 | 2023-03-13 | 2023-04-30 | Aquila Nuclear Engineering Limited
BEPPS2 | Morgan Sindall | Surveys (Pre September 2022, Topo etc) | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | B | 2022-10-22 | 2023-01-20 | 2023-03-31 | 2023-03-30 | CatSurveys Limited
ILW EZ | Morgan Sindall | Preparatory Civils Works - accommodation/compound/laydown | Construction | Project - Competitive Tender | NEC 4 ECC | B | 2021-12-07 | 2022-03-07 | 2023-04-14 | 2023-04-28 | Stobbarts Ltd
SRP | Morgan Sindall | Glovebox lifting | Mechanical & Pipework | Project - Competitive Tender | NEC | A | Complete | Complete | 2023-04-28 | 2023-04-11 | SCX Special Projects Ltd
ILW EZ | Morgan Sindall | Earthworks and Civil Construction Works inc P9 Raw/Potable Water | Construction | Project - Competitive Tender | NEC 4 ECC | G | 2022-05-21 | 2022-08-19 | 2023-05-31 | 2023-05-22 | Keltbray Limited
CDE | KBR | PDF viewing, signatures and commenting | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | Complete | Complete | 2023-06-11 | 2023-05-26 | Apex Network Solutions
SCP | Altrad Babcock | Out Cell Crane Assembly | Construction | Project - Competitive Tender | NEC 4 ECC | D | Complete | Complete | 2023-06-23 | 2023-06-23 | SCX Special Projects Ltd
RAP | Morgan Sindall | Internal Transfer System optioneering contract | Engineering | Project - Competitive Tender | NEC PSC | A | Complete | 2022-11-09 | 2023-06-30 | 2023-08-08 | Bilfinger UK Limited
SRP | Morgan Sindall | Services Building - Slabs/FRC | Construction | Project - Competitive Tender | NEC 3 ECC | A | Complete | Complete | 2023-07-03 | 2023-07-03 | Kier Infrastructure and Overseas Limited
SRP | Morgan Sindall | Services Building - Earthworks | Construction | Project - Competitive Tender | NEC 3 ECC | F | Complete | Complete | 2023-07-03 | 2023-07-03 | Kier Infrastructure and Overseas Limited
CDE | KBR | Commissioning and Completions (CMS) | IT Hardware and Software | Project - Competitive Tender | Bespoke | E | 2022-10-31 | 2022-11-30 | 2023-07-31 | 2023-06-14 | Omega Subsea Uk Limited
SRP | Morgan Sindall | Test Cans | Engineering | Project - Competitive Tender | NEC 3 Supply Contract | D | Complete | Complete | 2023-08-29 | 2023-09-01 | Graham Engineering Limited
RAP | Morgan Sindall | Bundle 6 (WO2) Prototyping and Detailed Design | Engineering | Framework | NEC | F | N/A | 2022-10-20 | 2023-08-30 | 2023-08-08 | Orano Limited
RAP | Morgan Sindall | Bulk & Bottled Gas Civils (Phase 2 Civils) | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2022-05-06 | 2022-08-04 | 2023-08-31 | 2023-09-21 | DSD Construction Ltd
SRP | Morgan Sindall | Sealer Coat | Construction | Project - Competitive Tender | NEC 3 ECC | E | Complete | Complete | 2023-09-13 | 2023-09-13 | 3i (Shepley, Jacobs Clean Energy, Altrad Support Services)
CDE | KBR | Autodesk interface support / clash management / etc | IT Hardware and Software | Project - Competitive Tender | Bespoke | E | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Laser scans model converter | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Basic CAD Drawing | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Intelligent Building Design | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Intelligent Civils Design with vehicle tracking | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Intelligent Mechanical Design | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Model File & Deliverable Manager | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Multi-Purpose .DWG file Graphic Viewer / Converter | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Consolidated 3D Model Viewer Manager | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
SRP | Morgan Sindall | Tank Farm | Construction | Project - Competitive Tender | NEC | C | Complete | 2021-12-21 | 2023-10-27 | 2024-01-11 | BOC Limited
RAP | Morgan Sindall | Construction Village FM Contract | Facilities Management | Project - Competitive Tender | NEC | B | N/A | N/A | 2023-11-30 | 2023-11-07 | Mitie Limited
CDE | KBR | EDMS - Comprehensive Document Management system | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | 2021-11-30 | 2022-06-06 | 2024-01-25 | 2024-01-25 | Hexagon (Intergraph (UK) Ltd
BEPPS2 | Morgan Sindall | Westlake's Office Refurbishment | Construction | Project - Competitive Tender | ECSS | B | N/A | N/A | 2024-02-09 | 2024-02-16 | Domino Commercial Interiors Limited
PPP Services | KBR | Developing Inclusive Leadership Behaviours | Training | Project - Competitive Tender | PSC Shortform | A | N/A | N/A | 2024-02-16 | 2024-02-14 | National Centre for Diversity
PPP Services | KBR | Developing Inclusive Leadership Behaviours | Training | Project - Competitive Tender | PSC Shortform | A | N/A | N/A | 2024-02-16 | 2024-02-14 | Steps Drama
LSS1 | Morgan Sindall | Main Build Modular Accommodation | Construction | Project - Competitive Tender | Not Awarded | D | 2023-07-01 | 2023-09-01 | 2024-03-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | CM&I Modules (not standalone package - will be part of the doors/windows packages) | Engineering | Project - Competitive Tender | Not Awarded | B | 2023-09-01 | 2023-11-01 | 2024-03-01 | TBC | Not Awarded
SRP | Morgan Sindall | Mech Installation Package Transfer Installation (incl's 000/100/200 IWT & SAT support) | Mechanical & Pipework | Project - Competitive Tender | NEC | G | Complete | 2022-05-06 | 2024-03-19 | 2024-02-27 | Hyde Group Nuclear Ltd
LSS1 | Morgan Sindall | Welfare & Maintenance Services | Support Services | Project - Competitive Tender | Not Awarded | D | 2023-01-23 | 2023-09-23 | 2024-03-21 | TBC | Not Awarded
LSS1 | Morgan Sindall | Architectural Doors | Engineering | Project - Competitive Tender | Not Awarded | D | 2023-08-01 | 2023-10-01 | 2024-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Radiometric's Equipment | Engineering | Project - Competitive Tender | Not Awarded | B | 2023-10-01 | 2023-12-01 | 2024-04-01 | TBC | Not Awarded
SCP | Altrad Babcock | interconnecting Pipework and pipe bridge sumps (North services Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | D | 2023-11-01 | 2023-12-01 | 2024-04-08 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Masonry / Blockwork | Construction | Project - Competitive Tender | NEC 3 ECC | E | 2022-02-14 | 2022-02-18 | 2024-04-12 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Glove Port Covers, Frames & Interlocks | Precision Engineering | Project - Competitive Tender | Not Awarded | E | 2021-06-15 | 2022-02-04 | 2024-04-29 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Shield Door Inc Liners ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | A | N/A | 2024-02-10 | 2024-04-30 | Not Awarded | Not Awarded
RAP | Morgan Sindall | Internal Transfer System - ECI | Plant & Equipment and Materials | Project - Competitive Tender | NEC | C | N/A | 2023-12-15 | 2024-04-30 | Not Awarded | Not Awarded
SCP | Jacobs | Fire Stopping Design | Design Services / Support | Project - Competitive Tender | Not Awarded | F | 2023-09-01 | 2023-10-16 | 2024-04-30 | Not Awarded | Not Awarded
LSS1 | Morgan Sindall | Universal Shield Blocks | Engineering | Project - Competitive Tender | Not Awarded | G | 2023-09-01 | 2023-11-01 | 2024-05-01 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | B927.1 Replacement accommodation | Construction | Project - Competitive Tender | NEC 4 Supply Contract | TBC | N/A | 2024-02-09 | 2024-05-14 | Not Awarded | Not Awarded
RAP | Morgan Sindall | Process CCTV - Design | Electrical & Instrumentation | Project - Competitive Tender | NEC | A | 2024-12-01 | 2024-01-09 | 2024-05-31 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Alimak Hoist Operators | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | Complete | 2023-05-16 | 2024-05-31 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - External Doors | Construction | Project - Competitive Tender | Not Awarded | D | 2024-01-02 | 2024-02-29 | 2024-06-20 | Not Awarded | Not Awarded
CDE | KBR | Decision Empowerment / Process mapping and activity linkage | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-04-30 | 2023-05-31 | 2024-06-21 | Not Awarded | Not Awarded
RAP | Morgan Sindall | Tower Craneage - ECI / Design | Plant & Equipment and Materials | Project - Competitive Tender | NEC | B | Complete | N/A | 2024-06-30 | Not Awarded | Not Awarded
LSS1 | Morgan Sindall | Digital Construction | IT Hardware and Software | Project - Competitive Tender | Not Awarded | A | 2023-07-01 | 2023-09-01 | 2024-07-01 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | Not Awarded | G | 2024-01-02 | 2024-03-01 | 2024-07-10 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | Not Awarded | D | 2023-10-19 | 2024-01-11 | 2024-07-17 | Not Awarded | Not Awarded
LSS1 | Morgan Sindall | Commissioning and Testing (provided by the programme) | Engineering | Project - Competitive Tender | Not Awarded | A | 2023-09-29 | 2023-12-28 | 2024-08-26 | TBC | Not Awarded
LSS1 | Morgan Sindall | SHEF Services | Support Services | Project - Competitive Tender | Not Awarded | E | 2022-12-01 | 2023-08-01 | 2024-09-01 | TBC | Not Awarded
SRP | Morgan Sindall | Maintenance Equipment e.g. Pallet Trucks, MEWP's | Plant & Equipment and Materials | Project - Competitive Tender | Not Awarded | TBC | 2023-12-14 | 2024-03-07 | 2024-09-04 | Not Awarded | Not Awarded
CDE | KBR | Cost control systems | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2023-05-31 | 2024-09-10 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | Not Awarded | D | 2024-02-09 | 2024-05-03 | 2024-09-20 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building Epoxy Floors | Construction | Project - Competitive Tender | Not Awarded | C | 2024-01-02 | 2024-05-17 | 2024-10-04 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Temporary Electric Services | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | C | 2024-01-16 | 2024-04-15 | 2024-10-07 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Shielding Blocks | Plant & Equipment and Materials | Project - Competitive Tender | Not Awarded | B | 2023-10-24 | 2024-04-23 | 2024-10-13 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building- IsoClad | Construction | Project - Competitive Tender | Not Awarded | C | 2024-03-20 | 2024-06-20 | 2024-12-17 | Not Awarded | Not Awarded
CDE | KBR | Construction Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-06-30 | 2023-07-31 | 2025-01-25 | Not Awarded | Not Awarded
CDE | KBR | Benefits Realization / Social Impact Records | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-07-31 | 2023-08-31 | 2025-01-25 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - Securiclad Internal Liner | Construction | Project - Competitive Tender | Not Awarded | TBC | 2024-06-01 | 2024-08-01 | 2025-02-04 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - Lifts | Construction | Project - Competitive Tender | Not Awarded | TBC | 2024-04-20 | 2023-07-24 | 2025-02-12 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | Not Awarded | A | 2024-02-26 | 2024-05-20 | 2025-02-21 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - Fixtures and Fittings | Construction | Project - Competitive Tender | Not Awarded | TBC | 2024-07-02 | 2024-09-02 | 2025-02-27 | Not Awarded | Not Awarded
CDE | KBR | Simple organisation chart production from PPP SharePoint lists | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-08-30 | 2023-09-30 | 2025-03-27 | Not Awarded | Not Awarded
CDE | KBR | Learning Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-08-30 | 2023-09-30 | 2025-03-27 | Not Awarded | Not Awarded
CDE | KBR | Permit management | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-09-30 | 2023-09-30 | 2025-03-27 | Not Awarded | Not Awarded
CDE | KBR | Personnel tracking on site | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-09-30 | 2023-09-30 | 2025-03-27 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - Washrooms | Construction | Project - Competitive Tender | Not Awarded | A | 2024-09-01 | 2024-11-04 | 2025-04-10 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - General Finishes floors and walls | Construction | Project - Competitive Tender | Not Awarded | TBC | 2024-09-05 | 2024-12-02 | 2025-05-03 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | Not Awarded | E | 2024-08-07 | 2024-10-30 | 2025-05-04 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building- Ceilings | Construction | Project - Competitive Tender | Not Awarded | TBC | 2024-12-09 | 2024-12-02 | 2025-06-10 | Not Awarded | Not Awarded
SCP | Altrad Babcock | Pipeflush for the Services and Process building (linked) | Facilities Management | Project - Competitive Tender | NEC 4 ECC | TBC | 2024-11-30 | 2025-03-30 | 2025-06-30 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | Not Awarded | D | 2023-06-01 | 2023-11-22 | 2025-07-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - Desks and furniture | Construction | Project - Competitive Tender | NEC | TBC | 2024-11-05 | 2025-02-23 | 2025-07-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building - Signage | Construction | Project - Competitive Tender | Not Awarded | TBC | 2025-01-05 | 2025-03-01 | 2025-08-04 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building -Doors | Construction | Project - Competitive Tender | Not Awarded | TBC | 2025-01-05 | 2025-03-01 | 2025-08-04 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-18 | 2025-06-16 | 2025-09-30 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Security Fence | Construction | Project - Competitive Tender | NEC 4 ECC | F | Not Awarded | Not Awarded | 2025-11-11 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Shielded windows inc liners (liners required earlier for construction) | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-18 | 2025-06-16 | 2025-12-16 | Not Awarded | Not Awarded
RAP | Morgan Sindall | Plant Overview System | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | Not Awarded | Not Awarded | 2025-12-17 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2024-02-20 | 2024-05-20 | 2026-02-06 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Site Temporary Accommodation - Demolition | Construction | Project - Competitive Tender | Not Awarded | TBC | 2025-11-19 | 2026-02-11 | 2026-04-27 | Not Awarded | Not Awarded
SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | E | 2026-02-01 | 2026-04-16 | 2026-10-13 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Test weights and equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | B | 2028-03-08 | 2028-06-06 | 2027-12-07 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2027-01-23 | 2027-04-23 | 2028-01-10 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | CM&I Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | A | 2028-12-19 | 2029-03-19 | 2029-09-10 | Not Awarded | Not Awarded
RAP | Morgan Sindall | Secondary Decontamination Unit - ECI | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Secondary Decontamination Unit | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Fire Suppression | Health & Safety | Project - Competitive Tender | Not Awarded | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | HA Transfer Area | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Transfer Area Crane - (A1120) | Maintenance | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Radiometrics works | Electrical & Instrumentation | Project - Competitive Tender | Not Awarded | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Analytical CAT A1, A2, B & C - Bundles 1 & 2 | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Site Cranes - Supply/Delivery | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Tower Cranes - Supply / Delivery | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Lifts South Extension - SEB | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Import / Export Bay Crane | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | HA Commissioning Hall | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | HA Secondary Decontamination Cell | Construction | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
RAP | Morgan Sindall | Internal Transfer System | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | Not Awarded | Not Awarded | Not Awarded | Not Awarded | Not Awarded
SRP | Morgan Sindall | Mech Installation Package Transfer Installation (incl's 000/100/200 IWT & SAT support) | Mechanical & Pipework | Project - Competitive Tender | Not Awarded | TBC | Complete | Not Awarded | Not Awarded | Not Awarded | Not Awarded
PPP Services | KBR | MP Commercial | Consultancy | Project - Competitive Tender | Framework | D | 2024-09-01 | 2024-11-01 | Q1 '25 | Not Awarded | Not Awarded
PPP Services | KBR | MP Project Leadership / Management | Consultancy | Project - Competitive Tender | Framework | D | 2024-09-01 | 2024-11-01 | Q1 '25 | Not Awarded | Not Awarded
PPP Services | Morgan Sindall & Altrad Babcock | MP Construction | Consultancy | Project - Competitive Tender | Framework | D | 2024-09-01 | 2024-11-01 | Q1 '25 | Not Awarded | Not Awarded
Multiple | Jacobs | MP Engineering Design | Consultancy | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | Q4 '24 | Not Awarded | Not Awarded
Multiple | Jacobs | Engineering Design Resource Framework | Design Services / Support | Project - Competitive Tender | Framework | H | 2024-04-30 | 2024-06-30 | Q4 '24 | Not Awarded | Not Awarded
PPP Services | KBR | MP Project Controls | Consultancy | Project - Competitive Tender | Framework | D | 2023-09-07 | 2024-05-17 | Q4 '24 | Not Awarded | Not Awarded
PPP Services | KBR | MP EHSS&Q | Consultancy | Project - Competitive Tender | Framework | D | 2024-03-01 | 2024-05-17 | Q4 '24 | Not Awarded | Not Awarded
PPP Services | KBR | MP Commissioning & Pre-Ops | Consultancy | Project - Competitive Tender | Framework | D | 2024-03-01 | 2024-05-17 | Q4 '24 | Not Awarded | Not Awarded