## Instructions
Evolution of the Procurement Plan 2024-2025 and use of CompeteFor
This update of the Procurement Plan captures proocurements by the PPP Lot Partners only.
PPP will are evolving the approach to procurememt planning and
advertising and will be:
a) Developing the Procurement Plan to include procurements from the
Key Delivery Partners (KDPs) so that any KDP requirements are visible
to the supply chain.
Issued for Information
b) Partnering with the CompeteFor platform competefor.com so that all
opportunities from either the PPP Lot Partners or Key Delivery Partners
will be advertised on CompeteFor. PPP and CompeteFor will run sessions
educate the supply chain in how to use CompeteFor, however please feel
free to visit the CompeteFor webiste and register your business

## Procurement Plan
Unique Ref | Project | Procuring Partner | Project Scope / Trade Packs Description | Category | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
PWP-08-02 | BEPPS2 | Morgan Sindall | CO981 Welfare - Design and Fit out | Construction | Project - Competitive Tender | NEC 4 ECC | D | 2024-02-17 | 2024-04-17 | 2025-05-31 | Not Awarded | Not Awarded
PWP-17 | BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-18 | 2025-06-16 | 2025-09-30 | Not Awarded | Not Awarded
PPPG-DCL-048 | CDE | KBR | 4D Planning and Scheduling - Professional Services | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2025-03-03 | 2025-03-03 | 2025-06-11 | Not Awarded | Not Awarded
PWP-25 | BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2024-02-20 | 2024-05-20 | 2026-02-06 | Not Awarded | Not Awarded
PPPG-DCL-065 | CDE | KBR | Estimating | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2024-08-19 | 2025-06-30 | Not Awarded | Not Awarded
PPPG-DCL-112 | CDE | KBR | People Resource Management | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-09-30 | 2025-03-08 | 2025-07-06 | Not Awarded | Not Awarded
PWP_ECI_013 | LSS1 | Morgan Sindall | Main ECI Phase - Universal Shield Blocks | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 PSC | A | 2025-07-30 | 2025-11-12 | 2026-02-18 | Not Awarded | Not Awarded
KBR-67 | PPP Services | KBR | Specialist commercial training - NEC4 PM training | Training | Project - Competitive Tender | Not Awarded | A | 2024-10-01 | 2024-10-01 | 2025-07-01 | Not Awarded | Not Awarded
KBR-71 | PPP Services | KBR | Coaching and Mentoring services | Support Services | Project - Competitive Tender | PSC Shortform | A | 2024-05-01 | 2024-11-21 | 2025-07-01 | Not Awarded | Not Awarded
KBR-72 | PPP Services | KBR | Mediation services | Support Services | Project - Competitive Tender | PSC Shortform | A | 2024-05-01 | 2024-11-21 | 2025-07-01 | Not Awarded | Not Awarded
AMTM-43A | PPP Services | Amentum | MP Engineering Design Partner | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | A | 2024-07-15 | 2024-10-07 | 2025-03-28 | Not Awarded | Not Awarded
AMTM-43B | PPP Services | Amentum | MP Engineering Design DSN | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2024-07-15 | 2024-08-26 | 2025-09-30 | Not Awarded | Not Awarded
SCP-C3 | SCP | Altrad Babcock | Site emergency response team | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2025-04-06 | 2025-05-31 | 2025-06-06 | Not Awarded | Not Awarded
SRP-151 | SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC 4 ECC | D | 2023-06-01 | 2023-11-22 | 2025-07-24 | Not Awarded | Not Awarded
SRP-147 | SRP | Morgan Sindall | Security Fence | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2024-11-30 | 2025-04-14 | 2025-11-11 | Not Awarded | Not Awarded
SRP-171C | SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Cleaning | Facilities Management | Project - Competitive Tender | NEC | B | 2024-02-09 | 2024-05-03 | 2026-04-24 | Not Awarded | Not Awarded
SRP-168 | SRP | Morgan Sindall | Site Temporary Accommodation - Demoltion | Construction | Project - Competitive Tender | NEC | D | 2025-11-19 | 2026-02-11 | 2026-04-22 | Not Awarded | Not Awarded
SRP-173 | SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2024-08-07 | 2024-10-30 | 2026-04-24 | Not Awarded | Not Awarded
SRP-171A | SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | NEC | D | 2024-02-09 | 2024-05-03 | 2026-04-24 | Not Awarded | Not Awarded
SRP-203 | SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | D | 2023-10-19 | 2024-01-11 | 2026-04-24 | Not Awarded | Not Awarded
SRP-176 | SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | C | 2026-02-01 | 2026-04-16 | 2026-10-13 | Not Awarded | Not Awarded
SRP-139L.1 | SRP | Morgan Sindall | Services Building - Securiclad Internal Liner | Construction | Project - Competitive Tender | NEC 4 ECC | E | 2025-05-08 | 2025-07-31 | 2025-09-08 | Not Awarded | Not Awarded
SRP-135 | SRP | Morgan Sindall | Mech Installation Package Transfer Installation (incl's 000/100/200 IWT & SAT support) | Mechanical & Pipework | Project - Competitive Tender | NEC 4 ECC | F | Complete | 2022-05-06 | 2024-03-19 | 2024-03-19 | NIS Limited
SRP-169H | SRP | Morgan Sindall | Construction Fire Risk Assessment Support | Professional Service | Project - Competitive Tender | NEC PSC | A | 2023-08-10 | 2023-08-31 | 2024-03-21 | 2024-03-21 | Hydrock Consultants Limited
SRP-169I | SRP | Morgan Sindall | Laser Scan Surveys | Professional Service | Project - Competitive Tender | NEC PSC | C | 2023-09-01 | 2023-09-13 | 2024-03-21 | 2024-03-21 | Atkinsrealis UK Limited
PBIBEPPS17 | BEPPS2 | Morgan Sindall | 4D Modelling | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | B | 2023-08-30 | 2024-01-09 | 2024-04-30 | 2024-04-08 | Oakwood Engineering solutions Limited
SRP-119 | SRP | Morgan Sindall | Glove Port Covers, Frames & Interlocks | Precision Engineering | Project - Competitive Tender | NEC 4 ECC | E | 2021-06-15 | 2022-02-04 | 2024-05-28 | 2024-05-25 | Fort Vale Nuclear Limited
ECI-PWP25-1A | BEPPS2 | Morgan Sindall | Shield Door Inc Liners ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | A | 2024-09-10 | 2024-02-10 | 2024-05-30 | 2024-05-30 | Asturfeito SA
SRP-191B | SRP | Morgan Sindall | PCM Monitors | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 Supply Contract | E | 2023-01-27 | 2023-06-05 | 2024-06-12 | 2024-06-12 | Mirion Technologies (Canberra) Uk Limited
ECI-PWP25-1 | BEPPS2 | Morgan Sindall | Shield Door Inc Liners ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | A | 2024-09-10 | 2024-02-10 | 2024-06-30 | 2024-06-28 | JGC Engineering & Technical Services Limited
KBR-64 | PPP Services | KBR | Health & Safety Training | Health & Safety | Project - Competitive Tender | Purchase Order | A | 2024-04-15 | 2024-05-15 | 2024-07-31 | 2024-07-10 | Highfield Awarding Body for Compliance Limited
JAC-38 | SCP | Jacobs | Fire Stopping Design | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | D | 2023-09-01 | 2023-10-16 | 2024-08-30 | 2024-08-31 | GRJ Contracting Limited
KBR-61 | PPP Services | KBR | Human Performance | Training | Project - Competitive Tender | Framework | E | 2024-04-18 | 2024-06-05 | 2024-10-16 | 2024-10-16 | GMR Human Performance Limited
ECI-PWP25-04 | BEPPS2 | Morgan Sindall | Shield Door Hose Reel ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSSC | A | 2024-02-03 | 2024-03-30 | 2024-11-30 | 2024-11-25 | Metreel Limited
KBR-68 | PPP Services | KBR | Specialist commercial training - APM Project Management Training | Training | Project - Competitive Tender | Framework | B | 2024-09-04 | 2024-09-04 | 2024-12-03 | 2024-12-03 | 20/20 Business Insight Limited
PWP-10 | BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | NEC | G | 2024-01-02 | 2024-03-01 | 2024-12-11 | 2024-12-11 | Mitie FM Limited
ECI-PWP24 | BEPPS2 | Morgan Sindall | CMA Maintenance Crane ECI | Engineering | Project - Competitive Tender | NEC 4 PSSC | B | 2024-01-30 | 2024-03-30 | 2025-01-31 | 2025-01-13 | SCX Special Projects Ltd
KBR-74 | CDE | KBR | Video/animation creation platform | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2024-11-01 | 2024-12-12 | 2025-02-11 | 2025-02-11 | Omniplex Group Limited
PPPG-DCL-056 | CDE | KBR | Planning Tool - Professional Services (Licences by SL) | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2024-07-01 | 2024-07-25 | 2025-02-13 | 2025-02-13 | Hyde Park Solutions Limited
KBR-42 | PPP Services | KBR | MP Project Controls | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2023-09-07 | 2024-07-26 | 2025-02-28 | 2025-02-28 | Adept, Mott, Prima Una, Blueprint, Equib, Optimise, G&T.
MSAB01 | PPP Services | Morgan Sindall & Altrad Babcock | MP Commissioning & Pre-Ops | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2024-06-10 | 2024-09-20 | 2025-03-31 | 2025-02-28 | Bilfinger, C-OMS, PPS