## Instructions
Issued for Information

## Procurement Plan
Unique Ref | Project | Procuring Partner | Project Scope / Trade Packs Description | Category | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
AMTM-43B | PPP Services | Amentum | MP Engineering Design DSN | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2025-07-01 | 2025-10-01 | 2026-03-01 | Not Awarded | Not Awarded
WP05 | SWMRF | Altrad Babcock | Compact Substation 51 | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 Supply Contract | D | 2025-11-01 | 2025-12-01 | 2026-03-01 | Not Awarded | Not Awarded
SRP-173 | SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 | E | 2025-08-01 | 2025-10-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-203 | SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC 4 | D | 2025-10-01 | 2026-01-01 | 2026-04-01 | Not Awarded | Not Awarded
SRP-139L.1 | SRP | Morgan Sindall | Services Building - Securiclad Internal Liner | Construction | Project - Competitive Tender | NEC 4 ECC | E | 2025-05-01 | 2025-07-01 | 2026-04-01 | Not Awarded | Not Awarded
WP09 | SWMRF | Altrad Babcock | Welfare Village for Team & Contractors | Facilities Management | Project - Competitive Tender | NEC 4 ECC | E | 2026-01-01 | 2026-02-01 | 2026-04-01 | Not Awarded | Not Awarded
KBR-80 | PPP Services | KBR | CSCS Training Courses | Support Services | Project - Competitive Tender | PSC Shortform | A | 2025-11-01 | 2025-11-01 | 2026-05-01 | Not Awarded | Not Awarded
KBR-81 | PPP Services | KBR | NEBOSH Training Courses | Support Services | Project - Competitive Tender | PSC Shortform | A | 2026-04-30 | 2026-04-30 | 2026-06-01 | Not Awarded | Not Awarded
PWP-10-03 | BEPPS2 | Morgan Sindall | Hard FM Building CO981 | Facilities Management | Project - Competitive Tender | NEC 4 Supply Contract | A | 2026-04-01 | 2026-04-01 | 2026-06-01 | Not Awarded | Not Awarded
KBR-82 | PPP Services | KBR | SMSTS Training Courses | Support Services | Project - Competitive Tender | PSC Shortform | A | 2026-05-31 | 2026-05-31 | 2026-07-01 | Not Awarded | Not Awarded
PWP-20 | BEPPS2 | Morgan Sindall | Through Wall Lights | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 | E | 2026-03-01 | 2026-06-01 | 2026-08-01 | Not Awarded | Not Awarded
KBR-67 | PPP Services | KBR | Specialist commercial training - NEC4 PM training | Training | Project - Competitive Tender | Supplier T&Cs | A | 2026-04-01 | 2026-07-01 | 2026-08-01 | Not Awarded | Not Awarded
PWP-25 | BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2026-02-19 | 2026-05-20 | 2026-09-01 | Not Awarded | Not Awarded
SRP-147 | SRP | Morgan Sindall | Security Fence | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2025-11-01 | 2026-04-01 | 2026-09-01 | Not Awarded | Not Awarded
SRP-176 | SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | C | 2026-02-01 | 2026-04-01 | 2026-09-01 | Not Awarded | Not Awarded
PWP-18.1 | BEPPS2 | Morgan Sindall | Large Shielded Plug Liners | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 | A | 2026-03-01 | 2026-06-01 | 2026-11-01 | Not Awarded | Not Awarded
PWP_ECI_034 | LSS1 | Morgan Sindall | Temporary Welfare Accommodation | Facilities Management | Project - Competitive Tender | NEC 4 ECC | F | 2026-08-01 | 2026-10-01 | 2027-03-01 | Not Awarded | Not Awarded
PWP_ECI_012 | LSS1 | Morgan Sindall | ECI Universal Shielding Blocks | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2026-10-01 | 2026-12-01 | 2027-04-01 | Not Awarded | Not Awarded
PWP-18 | BEPPS2 | Morgan Sindall | Large Shielded Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 | B | 2026-03-01 | 2026-06-01 | 2027-05-01 | Not Awarded | Not Awarded
PWP_ECI_018 | LSS1 | Morgan Sindall | Main ECI Phase - Inspection Modules | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2026-12-01 | 2027-01-01 | 2027-05-01 | Not Awarded | Not Awarded
PWP_ECC_038 | LSS1 | Morgan Sindall | Maintenacne hard FM temp welface accomodation | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2027-04-01 | 2027-05-01 | 2027-09-01 | Not Awarded | Not Awarded
PWP_ECC_039 | LSS1 | Morgan Sindall | Service connections for temp welfare accommodation | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | A | 2027-04-01 | 2027-05-01 | 2027-09-01 | Not Awarded | Not Awarded
PWP_ECC_040 | LSS1 | Morgan Sindall | Soft FM services for temp welfare | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2027-04-01 | 2027-05-01 | 2027-09-01 | Not Awarded | Not Awarded
PWP-23 | BEPPS2 | Morgan Sindall | CM&I Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | B | 2027-09-01 | 2027-12-01 | 2028-02-01 | Not Awarded | Not Awarded
PWP-22 | BEPPS2 | Morgan Sindall | Vent Covers, CMW Sliding platform & Mobile Gamma Gate | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 | D | 2027-08-01 | 2027-11-01 | 2028-03-01 | Not Awarded | Not Awarded
PWP_ECC_022 | LSS1 | Morgan Sindall | Doors (Personnel, Maintenance, Transporter) & Turnstiles | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2027-11-01 | 2028-01-01 | 2028-05-01 | Not Awarded | Not Awarded
PWP_ECI_019 | LSS1 | Morgan Sindall | Main ECI Phase - Environmental Monitoring Stillages and DCCs | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2027-11-01 | 2028-01-01 | 2028-05-01 | Not Awarded | Not Awarded
PWP-24 | BEPPS2 | Morgan Sindall | CMA Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 PSSC | E | 2027-01-01 | 2027-04-01 | 2028-08-01 | Not Awarded | Not Awarded
SRP-140 | SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 Supply Contract | A | 2028-01-03 | 2028-02-04 | 2028-08-01 | Not Awarded | Not Awarded
PWP-19 | BEPPS2 | Morgan Sindall | Mech fabrications | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 | B | 2028-03-01 | 2028-06-01 | 2028-09-01 | Not Awarded | Not Awarded
PWP_ECI_036 | LSS1 | Morgan Sindall | ECI Permanent Welfare Module, Services, Accommodation & Furniture | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2028-03-01 | 2028-05-01 | 2028-09-01 | Not Awarded | Not Awarded
PWP_ECC_031 | LSS1 | Morgan Sindall | Universal Shield Blocks | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2028-03-01 | 2028-05-01 | 2028-09-01 | Not Awarded | Not Awarded
PWP-27 | BEPPS2 | Morgan Sindall | Test weights and equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | B | 2028-03-01 | 2028-06-01 | 2028-10-01 | Not Awarded | Not Awarded
SRP-151 | SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC 4 ECC | D | 2028-06-01 | 2028-08-01 | 2028-11-01 | Not Awarded | Not Awarded
PWP_ECC_027 | LSS1 | Morgan Sindall | Environmental Monitoring Stillages & DCCs | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2028-07-01 | 2028-09-01 | 2029-01-01 | Not Awarded | Not Awarded
PWP_ECI_017 | LSS1 | Morgan Sindall | Main ECI Phase - Miscellaneous Lifting Equipment | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2028-09-01 | 2028-11-01 | 2029-03-01 | Not Awarded | Not Awarded
PWP_ECC_023 | LSS1 | Morgan Sindall | Doors Hatches Platforms | Construction | Project - Competitive Tender | NEC 4 ECC | G | 2029-04-01 | 2029-05-01 | 2029-09-01 | Not Awarded | Not Awarded
PWP_ECC_024 | LSS1 | Morgan Sindall | Additional Lifting Equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | A | 2029-04-01 | 2029-06-01 | 2029-10-01 | Not Awarded | Not Awarded
PWP_ECC_020 | LSS1 | Morgan Sindall | ECC Cladding | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2029-04-01 | 2029-06-01 | 2029-10-01 | Not Awarded | Not Awarded
PWP_ECC_025 | LSS1 | Morgan Sindall | Crane Rails | Engineering | Project - Competitive Tender | NEC 4 ECC | A | 2029-09-01 | 2029-11-01 | 2030-03-01 | Not Awarded | Not Awarded
PWP_ECC_026 | LSS1 | Morgan Sindall | Inspection Modules | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2029-09-01 | 2029-11-01 | 1930-03-01 | Not Awarded | Not Awarded
PWP-21 | BEPPS2 | Morgan Sindall | Vault floor plates and support system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 | E | 2029-10-01 | 2030-01-01 | 2030-04-01 | Not Awarded | Not Awarded
PWP_ECC_021 | LSS1 | Morgan Sindall | ECC Main order - Fit out | Construction | Project - Competitive Tender | NEC 4 ECC | A | 1930-04-01 | 1930-05-01 | 1930-09-01 | Not Awarded | Not Awarded
PPPG-DCL-056 | CDE | KBR | Planning Tool - Professional Services (Licences by SL) | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2024-07-01 | 2024-07-01 | 2025-02-01 | 2025-02-01 | Hyde Park Solutions Limited
KBR-74 | CDE | KBR | Video/animation creation platform | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2024-11-01 | 2024-12-01 | 2025-02-01 | 2025-02-01 | Omniplex Group Limited
KBR-42 | PPP Services | KBR | MPP Project Controls | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2023-09-01 | 2024-07-01 | 2025-02-01 | 2025-02-01 | Adept, Mott, Prima Uno, Blueprint, Equib, Optimise, G&T, Movar (Jan-26)
MSAB01 | PPP Services | Morgan Sindall & Altrad Babcock | MP Commissioning & Pre-Ops | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2024-06-01 | 2024-09-01 | 2025-03-01 | 2025-02-01 | Bilfinger Uk Ltd, Cumbria O&M Services Ltd, PPS Electrical Ltd
AMTM-43A | PPP Services | Amentum | MP Engineering Design Partner | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | A | 2024-07-01 | 2024-10-01 | 2025-03-01 | 2025-03-01 | Cyclife UK Limited, Mott Macdonald Limited
PPPG-DCL-048 | CDE | KBR | 4D Planning and Scheduling - Professional Services | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2025-03-01 | 2025-03-01 | 2025-05-01 | 2025-05-01 | Oakwood Engineering solutions Limited
KBR-77 | CDE | KBR | ITHC (IT Health Check) services FWA | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2024-08-01 | 2025-02-01 | 2025-05-01 | 2025-05-01 | Advent IM Limited
PWP-08-02 | BEPPS2 | Morgan Sindall | CO981 Welfare - Design and Fit out | Construction | Project - Competitive Tender | NEC 4 ECC | D | 2024-02-01 | 2024-04-01 | 2025-08-01 | 2025-08-01 | DAQS Group Limited
PWP-05 | BEPPS2 | Morgan Sindall | Minor Civils Care and Maintenance | Maintenance | Project - Competitive Tender | NEC 4 ECC | E | 2025-10-01 | 2025-10-01 | 2026-03-01 | 2026-02-01 | G & A M Lawson Limited