## Instructions
Evolution of the Procurement Plan 2024-2025 and use of CompeteFor
This update of the Procurement Plan captures proocurements by the PPP Lot Partners only.
PPP will are evolving the approach to procurememt planning and
advertising and will be:
a) Developing the Procurement Plan to include procurements from the
Key Delivery Partners (KDPs) so that any KDP requirements are visible
to the supply chain.
Issued for Information
b) Partnering with the CompeteFor platform competefor.com so that all
opportunities from either the PPP Lot Partners or Key Delivery Partners
will be advertised on CompeteFor. PPP and CompeteFor will run sessions
educate the supply chain in how to use CompeteFor, however please feel
free to visit the CompeteFor webiste and register your business

## Procurement Plan
Project | Procuring Partner | Project Scope / Trade Packs Description | Category 1 | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
BEPPS2 | Morgan Sindall | 4D Modelling | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | B | 2023-08-30 | 2024-01-09 | 2024-04-30 | 2024-04-08 | Oakwood Engineering solutions Limited
BEPPS2 | Morgan Sindall | 4D Modelling | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | B | 2023-08-30 | 2024-01-09 | 2024-04-30 | 2024-04-08 | Oakwood Engineering solutions Limited
SRP | Morgan Sindall | Glove Port Covers, Frames & Interlocks | Precision Engineering | Project - Competitive Tender | NEC 4 ECC | E | 2021-06-15 | 2022-02-04 | 2024-05-28 | 2024-05-25 | Fort Vale Nuclear Limited
BEPPS2 | Morgan Sindall | Shield Door Inc Liners ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | A | 2024-09-10 | 2024-02-10 | 2024-05-30 | 2024-05-30 | Asturfeito SA
SRP | Morgan Sindall | PCM Monitors | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 Supply Contract | E | 2023-01-27 | 2023-06-05 | 2024-06-12 | 2024-06-12 | Mirion Technologies (Canberra) Uk Limited
BEPPS2 | Morgan Sindall | Shield Door Inc Liners ECI | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | A | 2024-09-10 | 2024-02-10 | 2024-06-30 | 2024-06-28 | JGC Engineering & Technical Services Limited
PPP Services | KBR | Health & Safety Training | Health & Safety | Project - Competitive Tender | Purchase Order | A | 2024-04-15 | 2024-05-15 | 2024-07-31 | 2024-07-10 | Highfield Awarding Body for Compliance Limited
SCP | Jacobs | Fire Stopping Design | Design Services / Support | Project - Competitive Tender | NEC 4 PSC | D | 2023-09-01 | 2023-10-16 | 2024-08-30 | 2024-08-31 | GRJ Contracting Limited
BEPPS2 | Morgan Sindall | CM&I Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | A | 2028-12-19 | 2029-03-19 | 2029-09-10 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2027-01-23 | 2027-04-23 | 2028-01-10 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Test weights and equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | B | 2028-03-08 | 2028-06-06 | 2027-12-07 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2024-02-20 | 2024-05-20 | 2026-02-06 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Shielded windows inc liners (liners required earlier for construction) | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-18 | 2025-06-16 | 2025-12-16 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-18 | 2025-06-16 | 2025-09-30 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | NEC | G | 2024-01-02 | 2024-03-01 | 2024-12-11 | Not Awarded | Not Awarded
PPP Services | KBR | MP Project Controls | Professional Services | Project - Competitive Tender | NEC 4 PSSC FW | E | 2023-09-07 | 2024-07-26 | 2025-01-31 | Not Awarded | Not Awarded
PPP Services | KBR | MP Commissioning & Pre-Ops | Professional Services | Project - Competitive Tender | NEC 4 PSSC FW | E | 2024-06-10 | 2024-09-20 | 2025-03-07 | Not Awarded | Not Awarded
PPP Services | Jacobs | MP Engineering Design Partner | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | H | 2024-07-15 | 2024-10-07 | 2025-03-28 | Not Awarded | Not Awarded
PPP Services | Jacobs | MP Engineering Design DSN | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | H | 2024-07-15 | 2024-08-26 | 2024-12-20 | Not Awarded | Not Awarded
CDE | KBR | Simple organisation chart production from PPP SharePoint lists | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-08-30 | 2024-07-11 | 2025-02-20 | Not Awarded | Not Awarded
CDE | KBR | Construction Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-06-30 | 2024-09-03 | 2025-03-24 | Not Awarded | Not Awarded
CDE | KBR | Planning Tool | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | 2024-07-01 | 2024-07-25 | 2024-10-23 | Not Awarded | Not Awarded
CDE | KBR | Cost control systems | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2024-07-25 | 2024-12-03 | Not Awarded | Not Awarded
CDE | KBR | Estimating | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2024-08-19 | 2025-02-19 | Not Awarded | Not Awarded
CDE | KBR | Permit management (Linked to PPP-DCL-059) | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-09-30 | 2024-08-07 | 2025-03-19 | Not Awarded | Not Awarded
CDE | KBR | Personnel tracking on site | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-09-30 | 2024-09-27 | 2025-02-21 | Not Awarded | Not Awarded
CDE | KBR | Decision Empowerment / Process mapping and activity linkage (Data and Architecture Insight) | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-04-30 | 2024-08-20 | 2024-11-11 | Not Awarded | Not Awarded
SCP | Altrad Babcock | Pipeflush for the Services and Process building (linked) | Support Services | Project - Competitive Tender | NEC 4 ECC | A | 2024-11-30 | 2025-03-30 | 2025-06-30 | Not Awarded | Not Awarded
SCP | Altrad Babcock | interconnecting Pipework and pipe bridge sumps (North services Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC 4 ECC | D | 2023-11-01 | 2024-05-01 | 2024-11-30 | Not Awarded | Not Awarded
SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | E | 2026-02-01 | 2026-04-16 | 2026-10-13 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Site Temporary Accommodation - Demoltion | Construction | Project - Competitive Tender | NEC | A | 2025-11-19 | 2026-02-11 | 2026-04-27 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Security Fence | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2024-11-30 | 2025-04-14 | 2025-11-11 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC | D | 2023-06-01 | 2023-11-22 | 2025-07-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2024-02-26 | 2024-05-20 | 2025-02-21 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building- Isoclad | Construction | Project - Competitive Tender | NEC 4 ECC | C | 2024-03-20 | 2024-06-20 | 2024-12-17 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2024-08-07 | 2024-10-30 | 2026-04-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | NEC | D | 2024-02-09 | 2024-05-03 | 2026-04-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | D | 2023-10-19 | 2024-01-11 | 2026-04-24 | Not Awarded | Not Awarded
PPP Services | KBR | Human Performance | Training | Project - Competitive Tender | PSC Shortform | A | 2024-04-18 | 2024-06-05 | 2024-09-30 | Not Awarded | Not Awarded
PPP Services | KBR | Commercial proffesion training / capability | Training | Project - Competitive Tender | Not Awarded | A | 2024-09-01 | 2024-09-30 | 2024-12-31 | Not Awarded | Not Awarded
PPP Services | KBR | Specialist commercial training | Training | Project - Competitive Tender | Not Awarded | A | 2024-10-01 | 2024-10-01 | 2024-12-31 | Not Awarded | Not Awarded
PPP Services | KBR | Specialist commercial training | Training | Project - Competitive Tender | Not Awarded | A | 2024-09-04 | 2024-09-04 | 2024-09-30 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | CM&I Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | A | 2028-12-19 | 2029-03-19 | 2029-09-10 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2027-01-23 | 2027-04-23 | 2028-01-10 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Test weights and equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | B | 2028-03-08 | 2028-06-06 | 2027-12-07 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2024-02-20 | 2024-05-20 | 2026-02-06 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Shielded windows inc liners (liners required earlier for construction) | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-18 | 2025-06-16 | 2025-12-16 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | E | 2025-03-18 | 2025-06-16 | 2025-09-30 | Not Awarded | Not Awarded
BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | NEC | G | 2024-01-02 | 2024-03-01 | 2024-12-11 | Not Awarded | Not Awarded
PPP Services | KBR | MP Project Controls | Professional Services | Project - Competitive Tender | NEC 4 PSSC FW | E | 2023-09-07 | 2024-07-26 | 2025-01-31 | Not Awarded | Not Awarded
PPP Services | KBR | MP EHSS&Q | Professional Services | Project - Competitive Tender | NEC 4 PSSC FW | D | 2024-08-19 | 2024-09-20 | 2025-03-07 | Not Awarded | Not Awarded
PPP Services | KBR | MP Commissioning & Pre-Ops | Professional Services | Project - Competitive Tender | NEC 4 PSSC FW | E | 2024-06-10 | 2024-09-20 | 2025-03-07 | Not Awarded | Not Awarded
PPP Services | KBR | MP Commercial | Professional Services | Project - Competitive Tender | NEC 4 PSSC FW | D | 2024-09-02 | 2024-10-04 | 2025-03-21 | Not Awarded | Not Awarded
PPP Services | KBR | MP Project Leadership / Management | Professional Services | Project - Competitive Tender | NEC 4 PSSC FW | D | 2024-10-07 | 2024-11-08 | 2025-04-25 | Not Awarded | Not Awarded
PPP Services | Jacobs | MP Engineering Design Partner | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | H | 2024-07-15 | 2024-10-07 | 2025-03-28 | Not Awarded | Not Awarded
PPP Services | Jacobs | MP Engineering Design DSN | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | H | 2024-07-15 | 2024-08-26 | 2024-12-20 | Not Awarded | Not Awarded
PPP Services | Morgan Sindall & Altrad Babcock | MP Construction | Professional Services | Project - Competitive Tender | NEC 4 Framework Contract | D | 2024-11-25 | 2025-01-10 | 2025-06-02 | Not Awarded | Not Awarded
CDE | KBR | Simple organisation chart production from PPP SharePoint lists | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-08-30 | 2024-07-11 | 2025-02-20 | Not Awarded | Not Awarded
CDE | KBR | Construction Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-06-30 | 2024-09-03 | 2025-03-24 | Not Awarded | Not Awarded
CDE | KBR | Planning Tool | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | 2024-07-01 | 2024-07-25 | 2024-10-23 | Not Awarded | Not Awarded
CDE | KBR | Cost control systems | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2024-07-25 | 2024-12-03 | Not Awarded | Not Awarded
CDE | KBR | Estimating | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2024-08-19 | 2025-02-19 | Not Awarded | Not Awarded
CDE | KBR | Permit management (Linked to PPP-DCL-059) | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-09-30 | 2024-08-07 | 2025-03-19 | Not Awarded | Not Awarded
CDE | KBR | Personnel tracking on site | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-09-30 | 2024-09-27 | 2025-02-21 | Not Awarded | Not Awarded
CDE | KBR | Decision Empowerment / Process mapping and activity linkage (Data and Architecture Insight) | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-04-30 | 2024-08-20 | 2024-11-11 | Not Awarded | Not Awarded
SCP | Altrad Babcock | Pipeflush for the Services and Process building (linked) | Support Services | Project - Competitive Tender | NEC 4 ECC | A | 2024-11-30 | 2025-03-30 | 2025-06-30 | Not Awarded | Not Awarded
SCP | Altrad Babcock | interconnecting Pipework and pipe bridge sumps (North services Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC 4 ECC | D | 2023-11-01 | 2024-05-01 | 2024-11-30 | Not Awarded | Not Awarded
SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | E | 2026-02-01 | 2026-04-16 | 2026-10-13 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Site Temporary Accommodation - Demoltion | Construction | Project - Competitive Tender | NEC | A | 2025-11-19 | 2026-02-11 | 2026-04-27 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Security Fence | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2024-11-30 | 2025-04-14 | 2025-11-11 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC | D | 2023-06-01 | 2023-11-22 | 2025-07-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2024-02-26 | 2024-05-20 | 2025-02-21 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Services Building- Isoclad | Construction | Project - Competitive Tender | NEC 4 ECC | C | 2024-03-20 | 2024-06-20 | 2024-12-17 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2024-08-07 | 2024-10-30 | 2026-04-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | NEC | D | 2024-02-09 | 2024-05-03 | 2026-04-24 | Not Awarded | Not Awarded
SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | D | 2023-10-19 | 2024-01-11 | 2026-04-24 | Not Awarded | Not Awarded
PPP Services | KBR | Human Performance | Training | Project - Competitive Tender | PSC Shortform | A | 2024-04-18 | 2024-06-05 | 2024-09-30 | Not Awarded | Not Awarded
PPP Services | KBR | Commercial proffesion training / capability | Training | Project - Competitive Tender | Not Awarded | A | 2024-09-01 | 2024-09-30 | 2024-12-31 | Not Awarded | Not Awarded
PPP Services | KBR | Specialist commercial training | Training | Project - Competitive Tender | Not Awarded | A | 2024-10-01 | 2024-10-01 | 2024-12-31 | Not Awarded | Not Awarded
PPP Services | KBR | Specialist commercial training | Training | Project - Competitive Tender | Not Awarded | A | 2024-09-04 | 2024-09-04 | 2024-09-30 | Not Awarded | Not Awarded