## Instructions
Issued for Information

## Procurement Plan
Unique Ref | Project | Procuring Partner | Project Scope / Trade Packs Description | Category | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
PWP-25 | BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2026-02-19 | 2026-05-20 | 2026-10-15 | Not Awarded | Not Awarded
ILWEZ-1B-00001 | ILWEZ-1B | Morgan Sindall | Temporary Welfare Accommodation (Hire Contract) | Professional Services | Project - Competitive Tender | Hire / Lease Agreement | A | 2026-04-22 | 2026-04-22 | 2026-10-18 | Not Awarded | Not Awarded
SNMAP-COM-CON-00003 | SNM-AP | Altrad Babcock | Training & Familirasation Facility | Construction | Project - Competitive Tender | NEC4 ECSC | C | 2026-07-01 | 2026-07-01 | 2026-10-30 | Not Awarded | Not Awarded
WP05 | SWMEW | Altrad Babcock | Compact Substation 51 | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 Supply Contract | C | 2025-11-01 | 2025-12-19 | 2026-10-31 | Not Awarded | Not Awarded
PWP-10-03 | BEPPS2 | Morgan Sindall | Hard FM Building CO981 | Facilities Management | Project - Competitive Tender | NEC 4 Supply Contract | A | 2026-04-02 | 2026-04-02 | 2026-11-28 | Not Awarded | Not Awarded
KBR-82 | PPP Services | KBR | SMSTS Training Courses | Support Services | Project - Competitive Tender | PSC Shortform | A | 2026-05-31 | 2026-05-31 | 2026-11-30 | Not Awarded | Not Awarded
SRP-139L.1 | SRP | Morgan Sindall | Services Building - Securiclad Internal Liner | Construction | Project - Competitive Tender | NEC 4 ECC | E | 2026-01-08 | 2026-02-28 | 2026-12-11 | Not Awarded | Not Awarded
TBC-4 | BEPPS2 | Morgan Sindall | Firestopping Design consultancy | Design Services / Support | Project - Competitive Tender | NEC 4 | A | 2026-05-31 | 2026-08-29 | 2026-12-14 | Not Awarded | Not Awarded
TBC-1 | BEPPS2 | Morgan Sindall | Building 927 Re-Clad | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 | B | 2026-02-01 | 2026-05-02 | 2026-12-18 | Not Awarded | Not Awarded
KBR-59 | PPP Services | KBR | MPP Commercial | Professional Services | Project - Competitive Tender | NEC 4 PSSC | D | 2027-01-05 | 2027-01-31 | 2027-03-31 | Not Awarded | Not Awarded
KBR-69 | PPP Services | KBR | MPP 4D Modelling / Planning | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2026-11-01 | 2026-11-19 | 2027-03-31 | Not Awarded | Not Awarded
PPP-MW-0001 | Multiple | Morgan Sindall & Altrad Babcock | MPP Minor Works | Construction | Project - Competitive Tender | NEC 4 Framework Contract | H | 2026-07-24 | 2026-11-27 | 2027-03-31 | Not Awarded | Not Awarded
PWP_ECI_012 | LSS1 | Morgan Sindall | ECI Universal Shielding Blocks | Professional Services | Project - Competitive Tender | NEC 4 PSC | D | 2026-10-29 | 2026-12-18 | 2027-04-04 | Not Awarded | Not Awarded
PWP_ECC_034 | LSS1 | Morgan Sindall | Temporary Welfare Accommodation | Facilities Management | Project - Competitive Tender | NEC 4 ECC | E | 2026-08-31 | 2026-10-27 | 2027-04-06 | Not Awarded | Not Awarded
SRP-173 | SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2027-01-15 | 2027-04-09 | 2027-07-02 | Not Awarded | Not Awarded
PWP-24 | BEPPS2 | Morgan Sindall | CMA Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 PSSC | E | 2027-03-01 | 2027-05-30 | 2027-09-09 | Not Awarded | Not Awarded
SRP-147 | SRP | Morgan Sindall | Security Fence | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2025-11-30 | 2026-04-14 | 2027-09-30 | Not Awarded | Not Awarded
PWP_ECC_038 | LSS1 | Morgan Sindall | Maintenance hard FM temp welface accomodation | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2027-04-11 | 2027-05-11 | 2027-10-19 | Not Awarded | Not Awarded
PWP_ECC_039 | LSS1 | Morgan Sindall | Service connections for temp welfare accommodation | Electrical & Instrumentation | Project - Competitive Tender | NEC 4 ECC | A | 2027-04-11 | 2027-05-11 | 2027-10-19 | Not Awarded | Not Awarded
PWP-29 | BEPPS2 | Morgan Sindall | PA Doors | Plant & Equipment and Materials | Project - Competitive Tender | Bespoke | D | 2026-10-18 | 2027-01-16 | 2027-11-02 | Not Awarded | Not Awarded
PWP_ECC_040 | LSS1 | Morgan Sindall | Soft FM services for temp welfare | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2027-04-20 | 2027-05-20 | 2027-12-31 | Not Awarded | Not Awarded
PWP_ECI_018 | LSS1 | Morgan Sindall | Main ECI Phase - Inspection Modules | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2026-12-04 | 2027-01-23 | 2028-02-02 | Not Awarded | Not Awarded
PWP_ECI_019 | LSS1 | Morgan Sindall | Main ECI Phase - Environmental Monitoring Stillages and DCCs | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2027-11-17 | 2028-01-06 | 2028-06-15 | Not Awarded | Not Awarded
SRP-140 | SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 Supply Contract | A | 2028-01-03 | 2028-02-04 | 2028-08-04 | Not Awarded | Not Awarded
SRP-203 | SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | D | 2028-01-31 | 2028-04-24 | 2028-10-01 | Not Awarded | Not Awarded
PWP_ECC_031 | LSS1 | Morgan Sindall | Universal Shield Blocks | Construction | Project - Competitive Tender | NEC 4 ECC | F | 2028-03-15 | 2028-05-04 | 2028-10-12 | Not Awarded | Not Awarded
PWP_ECI_036 | LSS1 | Morgan Sindall | ECI Permanent Welfare Module, Services, Accommodation & Furniture | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2028-03-23 | 2028-05-12 | 2028-10-20 | Not Awarded | Not Awarded
SRP-151 | SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC 4 ECC | D | 2028-06-01 | 2028-08-22 | 2028-12-16 | Not Awarded | Not Awarded
PWP_ECC_027 | LSS1 | Morgan Sindall | Environmental Monitoring Stillages & DCCs | Professional Services | Project - Competitive Tender | NEC 4 PSC | B | 2028-07-11 | 2028-09-09 | 2029-02-17 | Not Awarded | Not Awarded
PWP_ECI_017 | LSS1 | Morgan Sindall | Main ECI Phase - Miscellaneous Lifting Equipment | Professional Services | Project - Competitive Tender | NEC 4 PSC | A | 2028-09-20 | 2028-11-09 | 2029-04-19 | Not Awarded | Not Awarded
PWP_ECC_023 | LSS1 | Morgan Sindall | Doors Hatches Platforms | Construction | Project - Competitive Tender | NEC 4 ECC | A | 2029-04-02 | 2029-05-22 | 2029-10-30 | Not Awarded | Not Awarded
PWP_ECC_020 | LSS1 | Morgan Sindall | ECC Cladding | Construction | Project - Competitive Tender | NEC 4 ECC | E | 2029-04-23 | 2029-06-12 | 2029-11-10 | Not Awarded | Not Awarded
PWP_ECC_021 | LSS1 | Morgan Sindall | ECC Main order - Fit out | Construction | Project - Competitive Tender | NEC 4 ECC | D | 2030-04-24 | 2030-05-08 | 2029-11-21 | Not Awarded | Not Awarded
PWP_ECC_022 | LSS1 | Morgan Sindall | Doors (Personnel, Maintenance, Transporter) & Turnstiles | Construction | Project - Competitive Tender | NEC 4 ECC | D | 2027-11-17 | 2028-01-06 | 2029-11-21 | Not Awarded | Not Awarded
PWP_ECC_024 | LSS1 | Morgan Sindall | Additional Lifting Equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC 4 ECC | G | 2029-04-30 | 2029-06-19 | 2029-11-27 | Not Awarded | Not Awarded
PWP_ECC_026 | LSS1 | Morgan Sindall | Inspection Modules | Professional Services | Project - Competitive Tender | NEC 4 PSC | F | 2029-09-14 | 2029-11-04 | 2030-04-14 | Not Awarded | Not Awarded
PWP-05 | BEPPS2 | Morgan Sindall | Minor Civils Care and Maintenance | Maintenance | Project - Competitive Tender | NEC 4 ECC | E | 2025-10-01 | 2025-10-31 | 2026-02-28 | 2026-02-28 | G & A M Lawson Limited
AMTM-43B | PPP Services | Amentum | MP Engineering Design DSN | Professional Services | Project - Competitive Tender | NEC 4 PSSC | A | 2025-07-28 | 2025-10-26 | 2026-03-30 | 2026-03-30 | Awarded
KBR-80 | PPP Services | KBR | CSCS Training Courses | Support Services | Project - Competitive Tender | PSC Shortform | A | 2026-04-01 | 2026-04-29 | 2026-09-25 | 2026-09-23 | Lawsons Training Centre Ltd
KBR-81 | PPP Services | KBR | NEBOSH Training Courses | Support Services | Project - Competitive Tender | PSC Shortform | A | 2026-04-30 | 2026-04-30 | 2026-09-25 | 2026-09-25 | The Rapid Results College Limited