## Procurement_Plan
		Dounreay, a division of Magnox Limited - Procurement Plan February 2024
For further information contact Dounreay at commercial.services@dounreay.com
☆ Record Ref	Business Unit	Sourcing to Contract: Record Name	☆ Published Description	Procurement Route (If Known)	Contract Type	Commercial Strategy	Desired Contract Start Date	Desired Contract End Date	Value Range	Contract Owner	Ops Project Manager	Previous Contract Ref
C15382	Operations - Maintenance & Engineering Support	Steam Generator Building West Wall Façade Replacement Design	Design of the Prototype Fast Reactor Steam Generator Building West Wall Facade Replacement	Framework - Further Competition	Services		09/02/2024	26/07/2024	< £100k	Jade Plowman	Kevin Morris
C17115	Operations - Reactor	Prototype Fast Reactor Removal of Surge Tanks	Prototype Fast Reactor Argon Blanket Decommissioning Removal of Surge Tanks	Framework - Further Competition	Works		15/02/2024	22/03/2024	< £100k	Jade Plowman	James Campbell
C17672	Operations - Reactor	Reactor Vessel Water Vapour Nitrogen Commissioning Support	Prototype Fast Reactor Reactor Vessel Water Vapour Nitrogen Commissioning Support	Direct Award - Below Threshold	Services		23/02/2024	28/06/2024	< £100k	Jade Plowman	James Campbell
C14697	Operations - Waste	Reserved Procurement - Crushing and Screening of Concrete for D6500	RESERVED PROCUREMENT / Crushing and Screening of Concrete for D6500	Below Threshold - Competitive Tender	Works		12/02/2024	26/02/2024	< £100k	Hannah Budge	Douglas McGeachin
C12419	Finance	Business Case Development for the Dounreay Site	Professional support required to deliver Dounreay's critical business cases.	Framework - Further Competition	Services		12/02/2024	24/11/2028	≥ £1m to <£5m	Ilona Unger-Russell	Debbie Youngson
C16884	Operations - Reactor	Refit of IPM9 Monitor	Supply, Installation, Commissioning and Site Acceptance Testing of an IPM Rebuild Kit	Direct Award - Below Threshold	Works		12/02/2024	16/02/2025	< £100k	Lynsey Will	Chris Wratten
C13981	Operations - Waste	Replacement of two stationary automatic water Samplers	Replacement of two stationary automatic water Samplers - Low Level Waste Effluent Treatment Plant	Below Threshold - Competitive Tender	Supplies		12/02/2024	12/08/2024	< £100k	Sarah McCaughey	Morris Macleod
C17647	Operations - Waste	Finite Element Analysis of Waste Flasks	Finite Element Analysis of Waste Flasks	Framework - Further Competition	Services		14/02/2024	29/03/2024	≥ £100k to <£500k	Hannah Budge	Gary Armstrong
C17717	Operations - Fuel	Supply of Stainless Steel Boxes	Supply of Stainless Steel Boxes	Below Threshold - 3 Quotes	Supplies		16/02/2024	31/03/2024	< £100k	Erica Innes	Derek Manson
C16898	Operations - FCA Decommissioning	Provision of D1204 Safety Case Specialist Consultancy	The provision of Safety Case Consultancy Services to support D1204 within the Fuel Cycle Area at Dounreay.	Framework - Further Competition	Services	Re-procurement (same scope)	17/02/2024	31/01/2026	≥ £100k to <£500k	Erica Innes	Suzy Nellies	3300009932
C17177	Operations - Maintenance & Engineering Support	Legionella Risk Assessment	Legionella Risk Assessment	Direct Award - Below Threshold	Works		19/02/2024	31/03/2024	< £100k	Kelsey Bain	Matthew Hitchin
C9096	Operations - Waste	Waste Framework Agreement – Provision of Waste Skips to Support Waste Generation	Waste Framework Agreement – Provision of Waste Skips to Support Waste Generation	Framework Agreement – Set up of a new Framework	Services		26/02/2024	31/12/2027	≥ £500k to <£1m	Janet Rosie	Douglas McGeachin
C17646	Operations - FCA Decommissioning	D1206 Safety Case Consultancy Services	The provision of Safety Case Consultancy Services to support D1206 within the Fuel Cycle Area at Dounreay.	Framework - Further Competition	Services		26/02/2024	31/12/2025	≥ £100k to <£500k	Alex Wood	Michael L Tait
C8608	Strategic Programme	iCase Sponsorship	iCase Sponsorship	Direct Award - Below Threshold	Services		26/02/2024	28/06/2024	< £100k	Lesley-Ann Crombie	Gordon Tait
C1121	Operations - Reactor	Prototype Fast Reactor Effluent Treatment Plant Pipework Replacement and Perform	Prototype Fast Reactor Effluent Treatment Plant Pipework Replacement and Performance Upgrades	Below Threshold - Competitive Tender	Works		01/03/2024	31/10/2025	≥ £1m to <£5m	Lynsey Will	James Campbell
C14389	Strategic Programme	Behaviour and transport of industrial particles in sand beds mobilised by waves	Behaviour and transport of industrial particles in sand beds mobilised by waves	Direct Award - Below Threshold	Services		01/03/2024	31/10/2025	≥ £100k to <£500k	Fraser Bruce	Christopher Sneddon
C17227	Finance	Internet Resilience Project	Wide Area Network connectivity/ Internet Feeding requirement	Framework - Direct Award	Services		01/03/2024	20/01/2025	< £100k	Ilona Unger-Russell	Rob Bohee
C6606	Operations - Maintenance & Engineering Support	D1403 Replacement Standby Generator	D1403 Replacement Standby Generator	Framework - Further Competition	Services		01/03/2024	30/09/2024	< £100k	Fraser Bruce	Kevin Morris
C1093	Operations - Waste	Supply of Fume Cupboards for D1310 Labs	15 Fume Cupboards - D1310 and D1215 Upgrade Projects	Below Threshold - Competitive Tender	Supplies		01/03/2024	01/09/2024	≥ £100k to <£500k	Hannah Budge	Michael Bailey
C12888	Operations - Waste	Manufacturing and Delivery of the D1215 Red Extract System Fans	Manufacturing and Delivery of the D1215 Red Extract System Fans	Below Threshold - Competitive Tender	Supplies		01/03/2024	21/06/2024	≥ £100k to <£500k	Hannah Budge	Michael Bailey
C1156	Operations - Maintenance & Engineering Support	Calibration & Repair of Dounreay Site Weigh Scale Equipment	Calibration & Repair of Dounreay Site Weigh Scale Equipment	Below Threshold - Competitive Tender	Services	Re-procurement (same scope)	01/03/2024	28/02/2028	≥ £100k to <£500k	Kelsey Bain	Laurence Campbell	3300025052
C1224	Operations - Maintenance & Engineering Support	Gamma Calibration Facility Upgrade	Gamma Calibration Facility Upgrade	Direct Award - PCR Single Source (Reg 32)	Supplies		04/03/2024	31/12/2024	≥ £100k to <£500k	Fraser Bruce	Avril Fell
C17011	Operations - Reactor	Prototype Fast Reactor Effluent Treatment Plant Pipework Manufacturing Drawings	Prototype Fast Reactor Effluent Treatment Plant Pipework Manufacturing Drawings	Framework - Further Competition	Services		08/03/2024	27/05/2024	< £100k	Jade Plowman	James Campbell
C10537	Security and Resilience	Supply of a Fire Appliance	Supply of a Fire Appliance	Open Procedure	Supplies		12/03/2024	30/09/2025	≥ £100k to <£500k	Lauren J Mackay	Rob Bly
C16824	Operations - Fuel	Procurement of 40 x Waste Crates	Procurement of 40 x Waste Crates	Below Threshold - 3 Quotes	Supplies		15/03/2024	30/05/2024	< £100k	Erica Innes	Derek Manson
C16095	Strategic Programme	Advanced Transition Works - Mock-up and Removal of Shaft Slab Cover	Shaft & Silo - Dismantle Existing Shaft Headworks. Dismantling the existing supplementary concrete Cover Slab below and then the original concrete Capping Slab. The capping slab is recorded as being constructed in two lifts.	Below Threshold - Competitive Tender	Works		29/03/2024	25/06/2025	≥ £500k to <£1m	John Johnstone	Willie Ross
C17690	Strategic Programme	Ongoing Support to SPOT Robot	Ongoing Support Contract for SPOT Robot System	Direct Award - Below Threshold	Services		29/03/2024	31/03/2025	< £100k	Robert McDonald	Heather Fairweather
C17460	Finance	Recruitment Process Unit 4 Platform	Applicant Tracking System for recruitment	Direct Award - Below Threshold	Services	Re-procurement (same scope)	31/03/2024	27/03/2027	< £100k	Ilona Unger-Russell	Calum Mackay	3300018757
C16984	Assurance	Replacement of Wound Monitor and Supporting Equipment	This procurement is to supply a replacement Wound Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Below Threshold - Competitive Tender	Supplies		01/04/2024	31/12/2024	< £100k	Fraser Bruce	Avril Fell
C10632	Assurance	Replacement of the Whole Body Monitor and Supporting Equipment	This procurement is to supply a replacement Whole Body Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Open Procedure	Supplies		01/04/2024	31/12/2024	≥ £100k to <£500k	Fraser Bruce	Avril Fell
C14411	Operations - FCA Decommissioning	D1206 Breathing Air Containerised System	D1206 Breathing Air Containerised System	Open Procedure	Services		01/04/2024	01/12/2024	≥ £100k to <£500k	Erica Innes	Iona Fraser
C15245	Finance	Hardware Refresh- 600 laptops and Docking Stations	Hardware Refresh- 600 Laptops and Docking Stations	Framework - Further Competition	Supplies	Re-procurement (same scope)	01/04/2024	01/05/2024	≥ £1m to <£5m	Louise Gunn	Calum Mackay	3300020765
C14394	Assurance	Provision of Criticality Software MONK & Visual Workshop	Provision of Criticality Software MONK & Visual Workshop	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	01/04/2024	31/03/2029	≥ £100k to <£500k	Kelsey Bain	Mike Potts	3300031908
C17478	Operations - Reactor	Prototype Fast Reactor Water Vapour Nitrogen Commissioning Support	Commissioning Support Services to enable the Commissioning of the Prototype Fast Reactor Water Vapour Nitrogen Systems	Framework - Further Competition	Services		01/04/2024	31/03/2025	≥ £100k to <£500k	Robert McDonald	James Campbell
C13979	Operations - General Site Areas	Provision of Electricity for Dounreay Main Site, D3100 and Car Park - 2024/25	Provision of Electricity for Dounreay Main Site, D3100 and Car Park - 2024/25	Framework - Further Competition	Supplies	Re-procurement (same scope)	01/04/2024	31/03/2025	≥ £5m to <£10m	Debbie Weir	Valerie Jappy	3300032090
C17219	Finance	Programmatic Change Work	Information Technology (IT) Transformation Project Work	Framework - Further Competition	Services		01/04/2024	31/03/2025	≥ £500k to <£1m	Louise Gunn	Calum Mackay
C14907	Strategic Programme	Dounreay and Sellafield Beach Monitoring and Sellafield Environmental Monitoring	Detection, Mapping and Retrieval of Radioactive Particles from Beach Environments and Environmental Monitoring	Open Procedure	Services	Re-procurement (same scope)	01/04/2024	31/03/2034	≥ £10m to <£25m	Fraser Bruce	Audrey D Chalmers	3300020535
C17165	Finance	Information Technology (IT) Intelligent Customer (IC) Leadership Service	Support to the Dounreay Leadership Information Technology (IT) Intelligent Customer (IC) function.	Framework - Further Competition	Services	Re-procurement (same scope)	01/04/2024	31/03/2025	≥ £100k to <£500k	Louise Gunn	Calum Mackay	3300033837
C17164	Finance	Dounreay Information Technology (IT) Intelligent Customer (IC) Support Service	This services acts as an extension to Dounreay's internal Information Technology (IT) Intelligent Customer Team and includes: / *Technology Demand Management / *IT Portfolio Management / *Technical Design Authority / *Application Management and Governance	Framework - Further Competition	Services	Re-procurement (same scope)	01/04/2024	31/03/2025	≥ £500k to <£1m	Louise Gunn	Calum Mackay	3300031906
C1096	Strategic Programme	Non Active Drain Water Treatment Plant Works	Non Active Drain Water Treatment Plant Works	Below Threshold - Competitive Tender	Works		01/04/2024	28/02/2025	≥ £1m to <£5m	Dawn Sewell	Adreain Gill
C6616	Operations - FCA Decommissioning	Reserved Procurement - Removal of Redundant Fuel Cycle Area Pipe Bridge	Note: Reserved Contract.	Below Threshold - Competitive Tender	Works		01/04/2024	01/04/2026	< £100k	Dawn Sewell	Matthew Swanson
C15129	Assurance	Supply of Electronic Personal Dosimeters	Supply of Electronic Personal Dosimeters	Direct Award - PCR Single Source (Reg 32)	Supplies		01/04/2024	31/03/2026	≥ £500k to <£1m	Emma Gordon	Anthony Ridgley
C1072	Strategic Programme	Shaft and Silo Process Cell and Waste Transfer System	Shaft and Silo Process Cell and Waste Transfer System	Framework - Further Competition	Services		01/04/2024	29/09/2026	≥ £10m to <£25m	Heidi Warner	Iain Lyall
C1134	Strategic Programme	Supply of Aggregate	Supply of Aggregate	Below Threshold - Competitive Tender	Supplies		01/04/2024	06/12/2024	< £100k	Heidi Warner	Jason Park
C1149	Strategic Programme	Site Closure and Environmental Restoration - Peer Review	Site Closure and Environmental Restoration - Peer Review	Framework - Further Competition	Services		01/04/2024	31/12/2024	< £100k	Kelsey Bain	Adreain Gill
C1151	Strategic Programme	Low Level Waste Pits - Review and development of the Environmental Safety Case	Low Level Waste Pits - Review and development of the Environmental Safety Case	Framework - Further Competition	Services		01/04/2024	31/03/2025	< £100k	Kelsey Bain	Adreain Gill
C1150	Strategic Programme	Development of Individual Component Environmental Safety Cases	Development of Individual Component Environmental Safety Cases	Framework - Further Competition	Services		01/04/2024	31/12/2024	< £100k	Kelsey Bain	Adreain Gill
C15920	Strategic Programme	Laboratory Analysis Services	Laboratory Analysis Services	Open Procedure	Services	Re-procurement (same scope)	01/04/2024	31/03/2034	≥ £5m to <£10m	Kelsey Bain	Audrey D Chalmers	3300029029
C1160	Operations - Maintenance & Engineering Support	Annual Maintenance (2 Visits per Annum) of AC12 Security Alarm Panels	Annual Maintenance (2 Visits per Annum) of AC12 Security Alarm Panels	Below Threshold - Competitive Tender	Services		01/04/2024	31/03/2029	< £100k	Kelsey Bain	Laurence Campbell
C13729	Strategic Programme	ArcGIS software maintenance	Maintenance of ArcGIS Platform & 2 x ArcGIS Desktop Basic (Single Use) & 1 x ArcGIS Desktop Advanced	Direct Award - Below Threshold	Services	Re-procurement (same scope)	01/04/2024	31/03/2025	< £100k	Kerrie Mackay	Adreain Gill	3300031778
C14956	Operations - Waste	Reserved Procurement - Provision of Ad-hoc Haulage Services	Provision of ad-hoc haulage services	Below Threshold - Competitive Tender	Services		01/04/2024	31/03/2025	< £100k	Lesley-Ann Crombie	Stephen Mackie
C9905	Operations - Waste	Mechanical Design Services	Mechanical Design Services	Framework - Further Competition	Services		01/04/2024	31/03/2025	< £100k	Sonja Sinclair	Michael Gray
C9877	Operations - Waste	Area 300 Main Immobilisation Line installation	Area 300 Main Immobilisation Line installation	Below Threshold - Competitive Tender	Works		01/04/2024	01/10/2024	≥ £100k to <£500k	Sonja Sinclair	Michael Gray
C9890	Operations - Waste	Stillage Transfer System- Gantry Crane & Frame	Works on the Stillage Transfer System- the Gantry Crane and Frame only	Below Threshold - Competitive Tender	Works		01/04/2024	11/11/2024	≥ £100k to <£500k	Sonja Sinclair	Michael Gray
C9887	Operations - Waste	Area 400 Internal Ventilation	To be coordinated with the installation of Area 300 and Area 400 Fan and Filter Rooms	Direct Award - Below Threshold	Works		01/04/2024	10/05/2024	< £100k	Sonja Sinclair	Michael Gray
C6404	Operations - Waste	Stillage Transfer System- Civil and groundworks	Civil and groundworks including levelling at DN253 and foundations for gantry crane	Below Threshold - Competitive Tender	Works		01/04/2024	02/09/2024	< £100k	Sonja Sinclair	Michael Gray
C9874	Operations - Waste	Area 500 - Internal Secondary Steelwork	Area 500 - Internal Secondary Steelwork	Direct Award - Below Threshold	Works		01/04/2024	01/07/2024	< £100k	Sonja Sinclair	Michael Gray
C9897	Operations - Waste	Stillage Transfer System - Control System Modifications	Control system Modifications design and implementation	Below Threshold - Competitive Tender	Works		01/04/2024	11/11/2024	< £100k	Sonja Sinclair	Michael Gray
C9900	Operations - Waste	Area 500 Electrical Equipment Procurement	Area 500 Electrical Equipment Procurement	Below Threshold - 3 Quotes	Works		01/04/2024	01/05/2024	< £100k	Sonja Sinclair	Michael Gray
C9903	Operations - Waste	Electrical Control and Instrumentation Services	Electrical Control and Instrumentation Services	Framework - Further Competition	Services		01/04/2024	31/03/2025	≥ £100k to <£500k	Sonja Sinclair	Michael Gray
C9919	Operations - Waste	Stillage Transfer System - Changing Room	Stillage Transfer System - Changing Room	Below Threshold - Competitive Tender	Works		01/04/2024	11/11/2024	< £100k	Sonja Sinclair	Suzanne Griffiths
C1239	Operations - Waste	65 tonne Bogie Modifications Package	65 tonne Bogie Modifications Package	Below Threshold - Competitive Tender	Works		01/04/2024	16/08/2024	≥ £100k to <£500k	Sonja Sinclair	Suzanne Griffiths
C1142	Operations - Waste	Manufacture and Design Ammonium Dirurante Floc Transport Stillage Lifting Beam	Manufacture and Design of Ammonium Dirurante Floc Transport Stillage Lifting Beam	Below Threshold - Competitive Tender	Services		01/04/2024	11/11/2024	≥ £100k to <£500k	Sonja Sinclair	Suzanne Griffiths
C9871	Operations - Waste	Area 600 Caustic Line D2700 to DN253	Area 600 Caustic Line D2700 to DN253	Direct Award - Below Threshold	Works		06/04/2024	31/05/2024	< £100k	Sonja Sinclair	Michael Gray
C14046	Operations - Waste	D1208 Peer Review	D1208 Peer Review	Framework - Further Competition	Services		08/04/2024	28/03/2025	< £100k	Lesley-Ann Crombie	Andrew Cormack
C12769	Operations - Fuel	Irradiated Fuel Replacement Grabs Design	Irradiated Fuel Replacement Grabs Design	Framework - Further Competition	Services		09/04/2024	08/10/2024	< £100k	Jade Plowman	Vicki Edmunds
C10405	Operations - Waste	48 tonne Forklift Replacement	48 tonne Forklift Replacement	Open Procedure	Supplies		15/04/2024	30/04/2025	≥ £100k to <£500k	Janet Rosie	Stephen Mackie
C12889	Operations - Waste	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Open Procedure	Services		15/04/2024	01/11/2024	≥ £100k to <£500k	Lesley-Ann Crombie	Michael Bailey
C17300	Operations - Maintenance & Engineering Support	Annual Grounds Maintenance	Annual Grounds Maintenance	Open Procedure	Services	Re-procurement (same scope)	17/04/2024	16/04/2034	≥ £500k to <£1m	Kelsey Bain	Peter Swanson	3300008447
C1143	Operations - FCA Decommissioning	Raffinate Room Concept Design and Safety and Environmental Overview Report	Raffinate Room Concept Design and Safety and Environmental Overview Report	Framework - Further Competition	Services		30/04/2024	06/05/2025	< £100k	Dawn Sewell	Andrew Hamilton
C12623	Security and Resilience	Firefighter and Officer Related Training	Firefighter and Officer Related Training	Open Procedure	Services		01/05/2024	30/04/2029	≥ £500k to <£1m	Lauren J Mackay	Rob Bly
C8624	Operations - Waste	Low Level Waste Effluent Treatment Plant Ventilation System Upgrade	Low Level Waste Effluent Treatment Plan Ventilation System Upgrade	Below Threshold - Competitive Tender	Works		01/05/2024	30/09/2024	< £100k	Donna Stewart	Morris Macleod
C16201	Operations - Maintenance & Engineering Support	Purchase of 2 x new Tipper / Gritter Lorries	Purchase of 2 x new Tipper / Gritter Lorries	Open Procedure	Supplies		01/05/2024	30/04/2025	≥ £100k to <£500k	Fraser Bruce	Ian Mackay
C1157	Operations - Maintenance & Engineering Support	Maintenance of Air Compressors	Maintenance of Air Compressors	Open Procedure	Services	Re-procurement (same scope)	01/05/2024	30/04/2027	≥ £100k to <£500k	Fraser Bruce	Laurence Campbell	3300024069
C1168	Strategic Programme	Waste Optimisation - Waste Optimisation Improvements	Waste Optimisation - Waste Optimisation Improvements	Framework - Further Competition	Services		01/05/2024	31/03/2025	< £100k	Janet Rosie	Alan Mowat
C1171	Strategic Programme	Lower Activity Waste - Strategy Support	Lower Activity Waste - Strategy Support	Framework - Further Competition	Services		01/05/2024	30/04/2025	< £100k	Janet Rosie	Alan Mowat
C16823	Operations - FCA Decommissioning	Procurement of a Non-Destructive Assay System	Procurement of a Non-Destructive Assay System	Open Procedure	Supplies		01/05/2024	30/06/2025	≥ £100k to <£500k	Robert McDonald	Derek Manson
C1122	Operations - Waste	D3000 Switchboard	D3000 Switchboard	Open Procedure	Supplies		06/05/2024	31/01/2025	≥ £100k to <£500k	Donna Stewart	Morris Macleod
C13987	Operations - Waste	D3000 Generator	D3000 Generator	Below Threshold - Competitive Tender	Supplies		06/05/2024	01/11/2024	< £100k	Donna Stewart	Morris Macleod
C16843	Operations - Waste	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Framework - Further Competition	Services		06/05/2024	28/06/2024	< £100k	Donna Stewart	Morris Macleod
C8637	Operations - Waste	Dounreay Cementation Plant Engineering Substantiation	Dounreay Cementation Plant Engineering Substantiation	Framework - Further Competition	Services		06/05/2024	27/06/2025	≥ £100k to <£500k	Donna Stewart	Frank Simmons
C1248	Operations - Waste	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Direct Award - PCR Single Source (Reg 32)	Supplies		11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C1247	Operations - Waste	Alpha Spectrometry Analyst Controller Units	Alpha Spectrometry Analyst Controller Units (1 and 6 Dual Packs Alpha Spectrometer)	Direct Award - Below Threshold	Supplies		11/05/2024	17/11/2024	< £100k	Donna Stewart	Jeremy Andrew
C1254	Operations - Waste	D2176 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	D2176 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	Direct Award - Below Threshold	Supplies		11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C1211	Operations - Waste	D1310 - Gas Chromatography - Mass Spectrometer	D1310 - Gas Chromatography - Mass Spectrometer	Below Threshold - Competitive Tender	Supplies		11/05/2024	17/11/2024	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C15664	Operations - Maintenance & Engineering Support	Refurbishment Works - Prototype Fast Reactor on 8 Transformers at T25 – T32	Refurbishment Works on the 8 Transformers T25 – T32 at the Prototype Fast Reactor / Replacing the cooling fins on four of the Transformers, T25, T26, T29 and T30	Direct Award - Below Threshold	Works		15/05/2024	15/11/2024	≥ £100k to <£500k	Fraser Bruce	Greg McEwan
C12887	Operations - Waste	D1215 Glove box Manufacturing and Delivery	D1215 Glove box Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		20/05/2024	29/11/2024	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C15173	Operations - Waste	Reserved Procurement - Air Handling Unit Design	Reserved Procurement - Air Handling Unit Design	Below Threshold - Competitive Tender	Services		20/05/2024	30/08/2024	< £100k	Donna Stewart	Michael Bailey
C6605	Operations - Maintenance & Engineering Support	Prototype Fast Reactor Steam Generator Building West Wall Facade Replacement	Construction of the Prototype Fast Reactor Steam Generator Building West Wall Face Replacement.	Below Threshold - Competitive Tender	Works		27/05/2024	30/08/2024	≥ £1m to <£5m	Jade Plowman	Kevin Morris
C1222	Operations - Maintenance & Engineering Support	Prototype Fast Reactor Transformers	Prototype Fast Reactor Transformers	Below Threshold - Competitive Tender	Supplies		01/06/2024	31/12/2024	≥ £100k to <£500k	Fraser Bruce	Laurence Campbell
C1109	Operations - Fuel	Reserved Procurement - D1203 Ventilation System	The Manufacture and Installation and Site Acceptance of the D1203 Ventilation System	Below Threshold - Competitive Tender	Works		01/06/2024	30/06/2025	≥ £1m to <£5m	Alex Wood	Hugh J Tunn
C16228	Operations - Maintenance & Engineering Support	Provision of 8 x Vans	The provision of 8 x Vans for the Dounreay Site	Below Threshold - 3 Quotes	Services	Re-procurement (same scope)	01/06/2024	31/05/2028	≥ £100k to <£500k	Kelsey Bain	Craig Murray	3300008297, 3300008492, 3300008493, 3300008494, 3300008501, 3300008502, 3300008503, 3300009430
C13682	Organisational Excellence	Provide a Graduate & Apprentice Learning & Development Programme	Provide a Graduate & Apprentice Learning & Development Programme at Loch Eil	Direct Award - Below Threshold	Services	Re-procurement (same scope)	01/06/2024	31/10/2024	< £100k	Lauren J Mackay	Rhona Gill	3300030924
C13986	Operations - Waste	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Below Threshold - Competitive Tender	Services		03/06/2024	29/11/2024	≥ £100k to <£500k	Donna Stewart	Morris Macleod
C12893	Operations - Waste	Fit-out and Commissioning of Glovebox and Extract Systems	Electrical, Control and Instrumentation Fit-out and Commissioning of Glovebox and Extract Systems	Open Procedure	Services		05/06/2024	06/06/2025	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C16547	Operations - Waste	Low Level Waste Pits - Provision of Cover Building	Low Level Waste Pits - Provision of Cover Building	Below Threshold - Competitive Tender	Supplies		07/06/2024	31/10/2024	< £100k	Janet Rosie	Suzanne Griffiths
C1238	Operations - Waste	Lid Lifting Frame and Bedplate Frame Package including castel key interlocking	Lid Lifting Frame and Bedplate Frame Package including castel key interlocking	Below Threshold - Competitive Tender	Works		14/06/2024	31/12/2024	< £100k	Sonja Sinclair	Michael Gray
C1246	Operations - Maintenance & Engineering Support	The supply of Cameras, Camera Encoders & Server Upgrade & supporting maintenance	- The supply and delivery of Cameras, Camera Encoders and Server Upgrade. / - Maintenance of Titan Vision Control Equipment.	Direct Award - PCR Single Source (Reg 32)	Supplies		01/07/2024	30/06/2028	≥ £1m to <£5m	Kelsey Bain	Douglas Mackenzie
C12897	Operations - Waste	Mechanical Fit-out and Commissioning of Glovebox and extract systems	Mechanical Fit-out and Commissioning of Glovebox and extract systems	Open Procedure	Services		03/07/2024	04/07/2025	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C1165	Strategic Programme	Remote Handled Intermediate Level Waste Letter of Compliance (Ion Exchange)	Remote Handled Intermediate Level Waste Letter of Compliance (Ion Exchange)	Framework - Direct Award	Services		03/07/2024	31/07/2025	< £100k	Robert McDonald	Duncan Gray
C15305	Operations - Waste	Low Level Waste Pits - Resurfacing	Low Level Waste Pits - Resurfacing	Below Threshold - Competitive Tender	Works		05/07/2024	31/10/2024	≥ £100k to <£500k	Janet Rosie	Suzanne Griffiths
C12385	Operations - Waste	Dounreay Cementation Plant Peer Review	Dounreay Cementation Plant Peer Review	Framework - Further Competition	Services		05/07/2024	28/10/2025	< £100k	Lesley-Ann Crombie	Frank Simmons
C1200	Operations - Reactor	Prototype Fast Reactor Manufacture Prototype Containment and Cutting Tool	Prototype Fast Reactor Manufacture Prototype Containment and Cutting Tool for Argon Gas Blanket	Below Threshold - Competitive Tender	Services		17/08/2024	31/10/2024	≥ £100k to <£500k	Lynsey Will	James Robertson
C17121	Operations - Waste	Dampers Manufacturing and Delivery	Dampers Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		31/08/2024	31/01/2025	< £100k	Lesley-Ann Crombie	Michael Bailey
C1114	Operations - Waste	Low Level Waste Metals Diversion Projects	Low Level Waste Metals Diversion Projects	Framework - Further Competition	Services		02/09/2024	31/03/2025	≥ £100k to <£500k	Carly Erridge	Stephen Mackie
C12886	Operations - Waste	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	Below Threshold - Competitive Tender	Services		02/09/2024	28/03/2025	< £100k	Donna Stewart	Michael Bailey
C1113	Operations - Waste	Voidage and Container Assessments	Voidage and Container Assessments	Framework - Further Competition	Services		02/09/2024	31/08/2025	≥ £100k to <£500k	Donna Stewart	Stephen Mackie
C12892	Operations - Waste	Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Below Threshold - Competitive Tender	Services		09/09/2024	28/03/2025	< £100k	Donna Stewart	Michael Bailey
C12890	Operations - Waste	D1215 Ductwork Manufacturing and Delivery	D1215 Ductwork Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		09/09/2024	31/01/2025	≥ £100k to <£500k	Donna Stewart	Michael Bailey
C1129	Operations - FCA Decommissioning	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility for Testing	Below Threshold - Competitive Tender	Works		19/09/2024	30/03/2025	≥ £100k to <£500k	Alex Wood	Leslie D M Mackay
C1102	Operations - Fuel	Irradiated Fuels Multi-functional Rig and Fixtures Scheme	Irradiated Fuels Multi-functional Rig and Fixtures Scheme and Detailed Design	Framework - Further Competition	Services		30/09/2024	30/10/2025	≥ £500k to <£1m	Lynsey Will	Vicki Edmunds
C1177	Operations - FCA Decommissioning	Design for Active Filter Change Replacement Robot Implementation	Design for Active Filter Change Replacement Robot Implementation	Framework - Further Competition	Services		01/10/2024	02/11/2025	< £100k	Alex Wood	Graham Carle
C9673	Operations - Waste	Telehandler	Telehandler	Below Threshold - Competitive Tender	Supplies		01/10/2024	31/01/2025	< £100k	Donna Stewart	Stephen Mackie
C1249	Operations - Waste	D1310 Auto-Analyser Spectrophotometers - Gallery - 2 off	D1310 Auto-Analyser Spectrophotometers - Gallery - 2 off	Direct Award - Below Threshold	Supplies		23/10/2024	31/03/2025	≥ £100k to <£500k	Donna Stewart	Jeremy Andrew
C1110	Operations - Fuel	Irradiated Fuels Consolidated Furniture Scheme and Detail	Irradiated Fuels Consolidated Furniture Scheme and Detailed Design	Framework - Further Competition	Services		29/11/2024	27/06/2025	≥ £100k to <£500k	Lynsey Will	Vicki Edmunds
C1172	Strategic Programme	Repair of Steelwork	Repair of Steelwork	Below Threshold - Competitive Tender	Works		30/11/2024	30/11/2025	≥ £100k to <£500k	Heidi Warner	Jason Park
C1173	Strategic Programme	Design of Steelwork Repair	Design of Steelwork Repair	Framework - Further Competition	Services		30/11/2024	14/03/2025	≥ £100k to <£500k	Heidi Warner	Jason Park
C15329	Strategic Programme	Shaft & Silo Waste Retrieval System	Procurement of a Silo Retrieval System for the Shaft & Silo programme - Detail Design, Manufacture, Installation & Commissioning,.	Restricted Procedure	Works		15/01/2025	15/01/2031	≥ £10m to <£25m	Lee Parnell	Grant Coghill
C15131	Operations - Maintenance & Engineering Support	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/05/2025	30/04/2029	≥ £1m to <£5m	Carly Erridge	Mick Moore	CFA/21/0002-0010
C1155	Operations - Waste	Supply of Heavy Weight Towing Vehicle	Supply of Heavy Weight Towing Vehicle	Open Procedure	Supplies	Re-procurement (same scope)	01/05/2025	01/04/2026	≥ £100k to <£500k	Carly Erridge	Stephen Mackie	3300028934
C1167	Strategic Programme	Fuel Cycle Area North Concept Decommissioning Planning	Fuel Cycle Area North Concept Decommissioning Planning	Framework - Further Competition	Services		01/05/2025	30/05/2026	≥ £1m to <£5m	Robert McDonald	Duncan Gray
C1120	Strategic Programme	Supply of Half Height ISO Low Level Waste Containers Framework Agreement	Framework Agreement for the Manufacture and Supply of Half Height ISO Low Level Waste Containers	Framework Agreement – Set up of a new Framework	Supplies	Re-procurement (same scope)	01/07/2025	30/06/2029	≥ £10m to <£25m	Janet Rosie	Alistair Ross	CFA/12/0048 - CFA/12/0049
C11262	Finance	U4BW Software as a Service	Unit4 Business World (U4BW) Software as a Service (SaaS).	Framework - Direct Award	Services	Re-procurement (same scope)	01/07/2025	30/06/2028	≥ £500k to <£1m	Louise Gunn	Amanda Petrie	3300026361
C13988	Operations - Waste	Gravity Receipt Tank Ladder Replacement	Gravity Receipt Tank Ladder Replacement	Below Threshold - Competitive Tender	Works		08/07/2025	08/01/2026	< £100k	Donna Stewart	Morris Macleod
C1108	Operations - Fuel	Thorium Nitrate, Manufacture, Integrated Works Testing, Installation	Thorium Nitrate Procurement, Manufacture, Integrated Works Testing, Installation and Commissioning	Framework - Further Competition	Works		01/08/2025	31/05/2026	≥ £500k to <£1m	Dawn Sewell	Derek Manson
C1073	Operations - Fuel	Thorium Nitrate Drums Final Letter of Compliance	Thorium Nitrate Drums Final Letter of Compliance	Framework - Further Competition	Services		01/08/2025	01/05/2026	< £100k	Dawn Sewell	Robert McKiddie
C1252	Finance	Programme Controls Support	Programme Controls Support	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	11/08/2025	11/08/2028	≥ £500k to <£1m	Louise Gunn	Neil Cook	3300027789
C1097	Operations - Reactor	Prototype Fast Reactor Intermediate Level Waste Size Reduction Facility Scheme,	Prototype Fast Reactor Intermediate Level Waste Size Reduction Facility Scheme, Detail Design and Build	Framework - Further Competition	Works		01/09/2025	23/04/2029	≥ £10m to <£25m	Adam Scott	Vicki Edmunds
C1124	Strategic Programme	Waste Treatment Plant - Scheme Design & Safety Assessment	Waste Treatment Plant - Scheme Design & Safety Assessment	Framework - Further Competition	Services		01/09/2025	30/09/2026	≥ £100k to <£500k	Heidi Warner	Gary Armstrong
C1099	Operations - Fuel	D2001 Irradiated Fuels Detailed Design and Build	D2001 Irradiated Fuels Detailed Design and Build	Framework - Further Competition	Works		01/09/2025	31/07/2028	≥ £25m to <£50m	Adam Scott	Derek Manson
C1100	Operations - Fuel	D2001 Irradiated Fuels Containers Manufacture	D2001 Irradiated Fuels Containers Manufacture	Framework - Further Competition	Services		01/09/2025	30/01/2028	≥ £1m to <£5m	Erica Innes	Andrew Hamilton
C1098	Strategic Programme	Waste Treatment Plant - Detail Design and Build	Waste Treatment Plant - Detail Design and Build	Framework - Further Competition	Works		01/09/2025	01/07/2028	≥ £5m to <£10m	Heidi Warner	Gary Armstrong
C13989	Operations - Waste	Break Tank Improvements	Break Tank Improvements	Below Threshold - Competitive Tender	Works		02/09/2025	02/03/2026	< £100k	Hannah Budge	Morris Macleod
C1136	Operations - Reactor	Prototype Fast Reactor Delivery and Design Phase for the Prototype Fast Reactor	Prototype Fast Reactor Delivery and Design Phase for the Prototype Fast Reactor Secondary Cold Trap Loop 1 and 2	Framework - Further Competition	Services		02/10/2025	12/12/2025	< £100k	Lynsey Will	James Campbell
C1144	Operations - Reactor	Treatment and Disposal of Sodium and Sodium Contaminated Waste	Prototype Fast Reactor Treatment and Disposal of Sodium and Sodium Contaminated Waste	Innovation Partnership (IP)	Services		07/10/2025	07/10/2030	≥ £5m to <£10m	Robert McDonald	Andrew Macinnes